## PMSummary
[10 empty] | Prioritization of categories | # of tasks | Primary Assignee
Tab Name | # of tasks | Estimated # of Hours | Completed # of Hours | % Completed | % Remaining | #hrs remaining | Code review time |  | 1 | Authentication & Authorization | 22 | Chandan
Components | 104 | 629 | 145.75 | 23.17% | 76.83% | 483.25 | 25.75 | 171.5 | 2 | Visualization Generation | 59 | Michael
Services | 49 | 200.25 | 82 | 40.95% | 59.05% | 118.25 |  | 82 | 3 | Visualization Navigation | 1 | Michael
Utilities | 24 | 192.75 | 0 | 0% | 100% | 192.75 |  | 0 | 4 | View Dashboard | 9 | Daya
Pipes | 17 | 13.25 | 0 | 0% | 100% | 13.25 |  | 0 | 5 | Commonly Used | 33 | Chandan
Directives | 9 | 14.5 | 0 | 0% | 100% | 14.5 |  | 0 | 6 | Visualization Legend | 5 | Daya
Misc. | 10 | 21.5 | 0 | 0% | 100% | 21.5 |  | 0 | 7 | Location Filter | 0 | Daya
Auth0 | 15
TOTALS | 228 | 1071.25 | 227.75 | 21.26% | 78.74% | 843.5 |  | 253.5 | 8 | Entity Filters | 0 | Chandan
[9 empty] | 9 | Service Line Filters | 0 | Chandan
[9 empty] | 10 | Labels | 0 | Daya
[9 empty] | 11 | Time Filters | 0 | Michael
Staffing |  | hrs per week | Unit test creation | Code review hours | # of weeks | Total capacity |  |  | 12 | LOB Filters | 0 | Daya
Michael |  | 30 | 25 | 5 | 6 | 180 |  |  | 13 | Filter Convenience Features | 0 | Chandan
Daya |  | 40 |  |  | 4 | 160 |  |  | 14 | Filters or Visualization Navigation Convenience features | 1 | Chandan
Chandan |  | 40 |  |  | 6 | 240 |  |  | 15 | Benchmark settings customization & Benchmark Calculation | 8 | Daya
TOTAL | [5 empty] | 580 | 352.25 |  | 16 | Save or export Visualization | 8 | Michael
[9 empty] | 17 | Dataset upload and management | 13 | Daya
Tab |  | # of tasks | Services | Utilities | Pipes | Directives | Misc.
Components
Services
Utilities
Pipes
Directives
Misc.
Auth0

## Components
|  |  |  | 629 | [5 empty] | 25.75 | 145.75
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id
Visualization Generation | graph-view.component.ts | 3 | 2,2.1,2.3,2.4,2.5 | 86.5 | 80 |  | 86.5 | 0.5 | 6 |  | N | Several methods are no longer called. This would cut down on the total Unit Test estimation but time would have to be spent on Code Cleanup to determine what should be removed. Move checkGraphFilters method to utils. |  |  |  |  | Sprint 5, Sprint 6 | 2021-04-26 | 2021-05-07 | Michael | PP-705
Visualization Generation | blank-view.component.ts | 3.1.2 |  | 1.5 | 0.25 |  | 1.5 | 1 | 0.25 |  | N | [5 empty] | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-706
Visualization Generation | map-view.component.ts | 4 | 2,2.2,2.3,2.4,2.5,2.9 | 13 | 10 | 4 | 17 | 0.5 | 2.5 | 2.25 | N | Move checkGraphFilters method to utils. | 94 | 82 | 96 | 94 | Sprint 3 |  |  | Daya | PP-707
View Dashboard | o2-view-list.ts | 9.1 | 9 | 1.5 | 0 |  | 1.5 | 0 | 1.5 |  | N | Unit tests completed but some improvements and DTOs can be added if time permits. |  |  |  |  | Sprint 7 | 2021-05-19 | 2021-05-19 | Chandan | PP-708
Visualization Generation | scatter-plot.component.ts | 5.1 |  | 22.75 | 21 |  | 22.75 | 0.75 | 1 |  | N | Time needs to be spent researching D3 specific testing methods for majority of functions and logic. |  |  |  |  | Sprint 4 | 2021-04-14 | 2021-04-18 | Daya | PP-709
Visualization Generation | scatter-plot-parent.component.ts | 5 |  | 20.25 | 16 |  | 20.25 | 0.75 | 3.5 |  | N | Move checkGraphFilters method to utils. |  |  |  |  | Sprint 4 | 2021-04-12 | 2021-04-14 | Daya | PP-710
Visualization Generation | node-tooltip.component.ts | 3.2.4 | 2 | 2.25 | 0.25 | 0 | 2.25 | 1.5 | 0.5 |  | N |  | 100 | 100 | 100 | 100 | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-711
View Dashboard | side-view-root.component.ts | 9.3 |  | 1.25 | 0.5 | 0 | 1.25 | 0.5 | 0.25 | 0.75 | Y | [9 empty] | PP-712
View Dashboard | header-view-root.component | 9.4 |  | 0.5 | 0 |  | 0.5 | 0 | 0.5 |  | Y | Look into TODOs and moving, combining, or removing DTOs. | [8 empty] | PP-713
Dataset upload and management | select-dataset.component.ts | 11.4 | 11.1 | 17.5 | 14 | 8 | 25.5 | 1 | 2.5 | 3 | Y | Dataset Selector and Dataset Details should also be tested/added. | 99.12% | 93.53% | 98.67% | 99.12% |  |  |  |  | PP-714
Dataset upload and management | o2-dataset-selector.component.ts | 11.5 | 11.1 | 5.75 | 3.5 | 4 | 9.75 | 1.25 | 1 | 1 | Y | Added to go with Select Dataset tests. | [8 empty] | PP-715
Dataset upload and management | o2-dataset-details.component.ts | 11.6 | 11.1 | 8.5 | 4.5 | 4 | 12.5 | 2 | 2 | 1 | Y | Added to go with Select Dataset tests. | [8 empty] | PP-716
Filters - Entity filters | entity-filter.component.ts | 7.3 | 2,7 | 27 | 23 |  | 27 | 1 | 3 |  | N | [5 empty] | Sprint 6 | 2021-05-10 | 2021-05-14 | Michael | PP-717
Filters - Location filters | location-filter.component.ts | 6.6 |  | 28.5 | 24 |  | 28.5 | 1.5 | 3 |  | N | Some logic and tests might overlap with other filter components. |  |  |  |  | Sprint 6 | 2021-05-03 | 2021-05-10 | Chandan | PP-718
Filters - Service Line filters | service-line-filter.component.ts | 8.2 | 8 | 28 | 23 |  | 28 | 1.5 | 3.5 |  | N | Some logic and tests might overlap with other filter components. |  |  |  |  | Sprint 6 | 2021-05-12 | 2021-05-17 | Daya | PP-719
Filters - Time filters | time-filter.component.ts | 14.1.2 |  | 24.75 | 24 |  | 24.75 | 0.75 | 3-4? |  | N | [5 empty] | Sprint 8 | 2021-06-01 | 2021-06-07 | Michael | PP-720
Filters - Time filters | time-filter-applied.component.ts | 14.6 |  | 3.75 | 2 |  | 3.75 | 1.25 | 0.5 |  | N | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 8 | 2021-06-01 | 2021-06-01 | Michael | PP-721
Filters - Time filters | time-filter-list.component.ts | 14.4 |  | 12.5 | 9.5 |  | 12.5 | 0.5 | 2.5 |  | N | [5 empty] | Sprint 8 | 2021-06-07 | 2021-06-08 | Michael | PP-722
Filters - Time filters | time-filter-map.component.ts | 14.5 |  | 0 | N/A |  | 0 | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-723
Filters - Time filters | time-filter-search.component.ts | 14.7 |  | 0 | N/A |  | 0 | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-724
Filters - Time filters | time-frame.component.ts | 14.8 |  | 0 | N/A |  | 0 | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-725
Label settings | label-styles.component.ts | 8.2.1 |  | 8.25 | 7.5 |  | 8.25 |  | 0.75 | 3 | Y |  | 89.4 | 80 | 92.86 | 90.26 |  |  |  | Daya | PP-726
Label settings | order-styles.component.ts | 8.2.2 |  | 5.5 | 4.5 | 0 | 5.5 |  | 1 | 1.5 | Y |  | 94.94 | 81.25 | 100 | 94.52 |  |  |  | Daya | PP-727
Filters - Convenience features | horizontal-bar-chart.component.ts | 14.9 |  | 35 | 30 |  | 35 | 2.5 | 2.5 |  | N | Need to research testing these specific D3 methods. Some minor unit tests were previously done by Jared in another branch. |  |  |  |  | Sprint 8 | 2021-05-26 | 2021-06-02 | Daya | PP-728
Benchmark settings customization & Benchmark Calculation | o2-autocomplete.component.ts | 7.5.3 |  | 0 | 0 | 0 | 0 | N/A | 0 |  | Y | Already completed. | [8 empty] | PP-729
Benchmark settings customization & Benchmark Calculation | o2-autocomplete-multiselect.component.ts | 7.5.4 |  | 2.5 | 2.5 |  | 2.5 | N/A |  |  | N | [5 empty] | Sprint 7 | 2021-05-18 | 2021-05-18 | Michael | PP-730
Benchmark settings customization & Benchmark Calculation | o2-autocomplete-search-filter.component.ts | 7.5.5 |  | 1.5 | 0 |  | 1.5 | N/A | 1.5 |  | N | Discuss TODOs for code cleanup. |  |  |  |  | Sprint 7 | 2021-05-18 | 2021-05-18 | Michael | PP-731
Filters - Convenience features | o2-bread-crumb.component.ts | 10.2 | 10 | 0.75 | 0.25 |  | 0.75 | 0.5 |  |  | N | [5 empty] | Sprint 7 | 2021-05-17 | 2021-05-17 | Michael | PP-732
Filters - Convenience features | o2-bread-crumb-sidenav.component.ts | 10.1 | 10 | 5 | 2 |  | 5 | 3 | 0 |  | N | [5 empty] | Sprint 7 | 2021-05-17 | 2021-05-17 | Michael | PP-733
Benchmark settings customization & Benchmark Calculation | o2-choice.component.ts | 7.5.6 |  | 0 | 0 |  | 0 | N/A | 0 |  | N | [9 empty] | PP-734
Visualization Navigation | o2-context-menu.component.ts | 3.2.5 |  | 0 | 0 | 0 | 0 | N/A | 0 |  | Y | Already completed. | [8 empty] | PP-735
Dataset upload and management | o2-data-statistic.component.ts | 11.5 |  | 1.25 | 0.25 |  | 1.25 | 0.75 | 0.25 |  | N | Verify previous TODO. |  |  |  |  | Sprint 7 | 2021-05-18 | 2021-05-18 | Daya | PP-736
Dataset upload and management | o2-data-statistic-case.component.ts | 11.6 |  | 1 | 0.25 |  | 1 | 0.75 |  |  | N | Check if TODO in O2 Data Statistic component impacts this as well. |  |  |  |  | Sprint 7 | 2021-05-18 | 2021-05-18 | Daya | PP-737
Visualization Generation | distribution-map.component.ts | 4.5.1 |  | 0.5 | 0 |  | 0.5 | 0.5 | 0 |  | N | Tests not really needed since it just passes map details to child components. |  |  |  |  | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-738
Visualization Generation | radius-map.component.ts | 4.1 | 2, | 19.5 | 17 | 0 | 19.5 | 0.5 | 2 | 3 | Y | Need to research testing Component Factory injection. Should we not test code that might be replaced in the future for faster rendering? Some methods aren't used anymore and can be removed to reduce the total unit test time. | 82.52 | 80 | 80.39 | 82.35 | Sprint 4 |  |  | Daya | PP-739
Visualization Generation | map-slider.component.ts | 4.2 |  | 5 | 3 | 0 | 5 | 0.5 | 1.5 | 0.5 | Y |  | 91.45 | 80 | 88.89 | 91.3 | Sprint 3 |  |  | Daya | PP-740
Visualization Generation | map-label.component.ts | 4.4 |  | 7 | 5.5 |  | 7 | 0.5 | 1 | 0.5 | Y |  | 98.4 | 95.18 | 100 | 98.37 | Sprint 3 |  |  | Daya | PP-741
Visualization Generation | map-cluster-label.component.ts | 4.5 |  | 5 | 4 |  | 5 | 0.5 | 0.5 | 0.5 | Y |  | 98.72 | 96.3 | 100 | 98.67 | Sprint 3 |  |  | Daya | PP-742
Save or export Visualization | o2-download-graph.component.ts | 13.5 | 13.1 | 27.5 | 22 | 6 | 33.5 | 3.5 | 2 | 1.75 | Y | There are some unit tests written but I don't believe they were done properly for code coverage before. Time to complete based on how much is actually covered and can be reused. | 90 | 80 | 91 | 80 | Sprint 3 | 2021-03-31 | 2021-04-05 | Daya | PP-743
Save or export Visualization | o2-download-graph-page.component.ts | 13.6 | 13.1 | 2 | 0 |  | 2 | 2 | 0 |  | N | No functional unit tests needed. |  |  |  |  | Sprint 7 | 2021-05-19 | 2021-05-19 | Daya | PP-744
View Dashboard | search.component.ts | 9.4 |  | 0 | N/A |  | 0 | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-745
Filters - Convenience features | o2-spiral-graph.component.ts | 13.6.1 |  | 30 | 28 |  | 30 | 0 | 2 |  | N | A lot of D3 code used here. |  |  |  |  | Sprint 7 | 2021-05-20 | 2021-05-25 | Daya | PP-746
Filters - Convenience features | o2-star-chart.component.ts | 7.5 |  | 0 | N/A |  | 0 | N/A | N/A |  | N | Not currently used in Quality Filter. | [8 empty] | PP-747
Filters - Convenience features | o2-tooltip.component.ts | 7.4 |  | 1 | 0 |  | 1 | N/A | 1 |  | N | Already completed. Verify TODOs and watch for any bugs from changes. |  |  |  |  | Sprint 6 | 2021-05-14 | 2021-05-14 | Michael | PP-748
Dataset upload and management | o2-upload-file.component.ts | 11.7 |  | 4.75 | 3 |  | 4.75 | 1.25 | 0.5 |  | N | [5 empty] | Sprint 7 | 2021-05-18 | 2021-05-18 | Daya | PP-749
Dataset upload and management | o2-shareview.component.ts | 11.6 |  | 0 | N/A |  | 0 | N/A | N/A |  | N | Shareview is hidden in the Select Dataset panel currently. | [8 empty] | PP-750
Visualization Generation | base-chart.component.ts | 5.3 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | This component isn't used anywhere in the current code. | [8 empty] | PP-751
Visualization Legend | benchmark-legend.component.ts | 3.1.4 |  | 2.75 | 1 | 0 | 2.75 | 1.25 | 0.5 | 0.75 | Y |  | 100 | 100 | 100 | 100 | Sprint 3 |  |  | Daya | PP-752
Visualization Generation | chart-wrapper.component.ts | 5.4 |  | 0.75 | 0.25 |  | 0.75 | 0.5 | 0 |  | N | [5 empty] | Sprint 5 | 2021-04-19 | 2021-04-19 | Daya | PP-753
Visualization Legend | legend-label.component.ts | 3.1.2 |  | 5.75 | 3.5 |  | 5.75 | 1.25 | 1 | 0.5 | Y |  | 98 | 98 | 100 | 98 | Sprint 3 |  |  | Daya | PP-754
Visualization Legend | legend-label-item.component.ts | 3.1.3 |  | 2 | 0.5 | 0 | 2 | 1.5 | 0 | 0.25 | Y |  | 100 | 100 | 100 | 100 | Sprint 3 |  |  | Daya | PP-755
Filters - Convenience features | o2-selected-filter.component.ts | 7.6 |  | 1 | 0.5 |  | 1 | 0.5 | 0 |  | N | [5 empty] | Sprint 6 | 2021-05-11 | 2021-05-11 | Chandan | PP-756
Commonly Used | inline-alert.component.ts | 9.4.7 |  | 0 | N/A |  | 0 | N/A | N/A |  | N | Only used in a component which isn't in use. | [8 empty] | PP-757
Filters - Convenience features | o2-search-filter.component.ts | 7.7 |  | 1 | 0.5 |  | 1 | 0.5 | 0 |  | N | [5 empty] | Sprint 6 | 2021-05-11 | 2021-05-11 | Chandan | PP-758
Filters - Location filters | o2-radius-selector.component.ts | 6.4 |  | 20 | 13 | -2 | 18 | 4 | 3 | 1.5 | N |  | 99 | 87 | 96 | 98 | Sprint 4 | 2021-04-06 | 2021-04-08 | Daya | PP-759
Filters - Location filters | o2-radius-component.ts | 6.3 |  | 0 | N/A |  | 0 | N/A | N/A |  | N | Replaced by O2 Radius Selector. No longer used. | [8 empty] | PP-760
Visualization Generation | node-graph.component.ts | 3.1 | 2,2.4 | 10.25 | 7.5 | 1.25 | 11.5 | 1.25 | 1.5 | 1 | N |  | 98.94% | 91.25% | 97.37% | 98.91% | Sprint 3 | 2021-03-23 | 2021-03-25 | Michael | PP-761
Visualization Generation | node.component.ts | 3.2 | 2,2.1,2.4 | 24.5 | 20 | -1.25 | 23.25 | 1.5 | 3 | 2 | N | Depends on how long it takes to write tests for HTML string creation. | 98.27% | 94.72% | 95.24% | 98.48% | Sprint 3 | 2021-03-17 | 2021-03-23 | Michael | PP-762
Visualization Generation | node-label.component.ts | 3.3 | 2,2.4 | 6.5 | 4.5 | -2 | 4.5 | 0 | 2 |  | N |  | 100% | 100% | 100% | 100% | Sprint 3 | 2021-03-29 | 2021-03-29 | Michael | PP-763
Visualization Generation | node-details.component.ts | 3.4 | 2,2.4 | 19 | 18 |  | 19 | 0 | 1 |  | N | Need to fix compile errors and check code coverage. |  |  |  |  | Sprint 4 | 2021-04-15 | 2021-04-19 | Michael | PP-764
Visualization Generation | node-details-list-row.component.ts | 3.5 | 2.4 | 0.75 | 0.25 |  | 0.75 | 0 | 0.5 |  | N | Need to fix compile errors and check code coverage. |  |  |  |  | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-765
Visualization Generation | node-details-map.component.ts | 3.6 |  | 2 | 1.5 |  | 2 | 0 | 0.5 |  | N | Some design tests were previously written but none for functionality. |  |  |  |  | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-766
Visualization Generation | node-details-panel.component.ts | 3.7 |  | 1 | 0.5 |  | 1 | 0 | 0.5 |  | N | Need to fix compile errors and check code coverage. |  |  |  |  | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-767
Visualization Generation | node-details-paragraph.component.ts | 3.8 |  | 1.5 | 1 |  | 1.5 | 0 | 0.5 |  | N | Need to fix compile errors and check code coverage. |  |  |  |  | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-768
Visualization Generation | node-details-paragraph-list.component.ts | 3.9 |  | 0.5 | 0 |  | 0.5 | 0 | 0.5 |  | N | Need to fix compile errors and check code coverage. |  |  |  |  | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-769
Visualization Generation | link.component.ts | 3.1.1 | 2,2.1,2.4 | 7.5 | 6 | 0.5 | 8 | 0.5 | 1 | 1 | N | Depends on how long it takes to write tests for HTML string creation. | 97.38% | 91.3% | 91.67% | 97.85% | Sprint 3 | 2021-03-25 | 2021-03-26 | Michael | PP-770
Label settings | tooltip.component.ts | 8.2.1 |  | 0 | N/A |  | 0 | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-771
Filters - Convenience features | o2-modal.component.ts | 7.8 |  | 0.5 | 0.5 |  | 0.5 | 0 | 0 |  | N | Design tests previously written but some minor tests can be added for functionality. |  |  |  |  | Sprint 6 | 2021-05-11 | 2021-05-11 | Chandan | PP-772
Filters - Location filters | o2-map-select-filter.component.ts | 6.6 |  | 38.25 | 35 |  | 38.25 | 1.25 | 2 |  | N | [5 empty] | Sprint 6 | 2021-05-05 | 2021-05-11 | Daya | PP-773
Filters - Convenience features | o2-list-button-filter.component.ts | 6.5 |  | 0 | 0 |  | 0 | 0 | 0 |  | Y | Already completed. Just verify TODOs. | [8 empty] | PP-774
Filters - Convenience features | o2-filter-container.component.ts | 6.5 |  | 6.5 | 4 |  | 6.5 | 1 | 1.5 |  | N | [5 empty] | Sprint 6 | 2021-05-04 | 2021-05-04 | Daya | PP-775
Filters - Convenience features | o2-filter-button.component.ts | 6.7 |  | 2 | 0 |  | 2 | 2 | 0 |  | Y | Already completed. | [7 empty] | Michael | PP-776
Save or export Visualization | o2-export-details.component.ts | 13.7 |  | 2.5 | 1.5 |  | 2.5 | 1 | 0 |  | N | [5 empty] | Sprint 6 | 2021-05-11 | 2021-05-11 | Chandan | PP-777
Save or export Visualization | o2-export.component.ts | 13.8 |  | 1 | 0.25 |  | 1 | 0.5 | 0.25 |  | N | [5 empty] | Sprint 6 | 2021-05-11 | 2021-05-11 | Chandan | PP-778
Commonly Used | o2-error-modal.component.ts | 9.4.6 |  | 0 | N/A |  | 0 | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-779
Label settings | o2-droppable-container.component.ts | 8.5.1 |  | 2.75 | 2 |  | 2.75 | 0.75 | 0 |  | N | [5 empty] | Sprint 7 | 2021-05-17 | 2021-05-17 | Michael | PP-780
Label settings | threshold-styles.component.ts | 8.9 |  | 0 | N/A |  |  | N/A | N/A |  | N | All usage of this component is commented out. | [8 empty] | PP-781
Commonly Used | logo.component.ts | 9.4.5 |  | 0.25 | 0 |  |  | 0.25 | 0 |  | N | [5 empty] | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan | PP-782
View Dashboard | report-name-input.component.ts | 9.7 |  | 2 | 1 |  |  | 0.5 | 0.5 |  | N | [5 empty] | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan | PP-783
Filters - Convenience features | sidenav.component.ts | 10.2 | 10 | 42.5 | 32.5 |  |  | 5 | 5 |  | N | [5 empty] | Sprint 7 | 2021-05-19 | 2021-05-28 | Michael | PP-784
Commonly Used | back-to-top.component.ts | 9.4.3 |  | 0.5 |  |  |  | 0 | 0.5 |  | N | Tests need to be copied over from Admin Panel and verified. |  |  |  |  | Sprint 7 | 2021-05-17 | 2021-05-17 | Chandan | PP-785
Benchmark settings customization & Benchmark Calculation | benchmark.component.ts | 4.1.1 | 2,2.3,2.4 | 41.5 | 38.5 |  |  | 2 | 1 |  | N | [5 empty] | Sprint 5 | 2021-04-20 | 2021-04-30 | Chandan | PP-786
Commonly Used | error-msg.component.ts | 9.4.4 |  | 0.5 | 0 |  |  | 0.5 | 0 |  | N | [5 empty] | Sprint 7 | 2021-05-17 | 2021-05-17 | Chandan | PP-787
Commonly Used | input.component.ts | 9.4.1 |  | 3.25 | 1.5 |  |  | 0.25 | 1.5 |  | N | [5 empty] | Sprint 7 | 2021-05-17 | 2021-05-17 | Chandan | PP-788
Commonly Used | select.component.ts | 9.4.2 |  | 0 | N/A |  |  | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-789
Commonly Used | header.component.ts | 9.5.1 |  | 0 | N/A |  |  | N/A | N/A |  | Y | Already completed. | [8 empty] | PP-790
Commonly Used | logout-modal.componeont.ts | 9.5.2 |  | 0 | N/A |  |  | N/A | N/A |  | Y | Already completed. | [8 empty] | PP-791
Filters - Convenience features | chips.component.ts | 10.7 |  | 0 | N/A |  |  | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-792
Filters - Convenience features | field-icon.component.ts | 10.6 |  | 0.5 | 0.25 |  |  | 0.25 | 0 |  | N | [5 empty] | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan | PP-793
Filters - Convenience features | fieldset.component.ts | 10.3 |  | 0.25 | 0 |  |  | 0.25 | 0 |  | N | [5 empty] | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan | PP-794
Filters - Convenience features | fieldset-body.component | 10.5 |  | 0 | 0 |  |  | 0 | 0 |  | N | Tests not required for this file. | [8 empty] | PP-795
Filters - Convenience features | fieldset-header.component.ts | 10.4 |  | 0 | 0 |  |  | 0 | 0 |  | N | Tests not required for this file. | [8 empty] | PP-796
Filters - Convenience features | incremental-input.component.ts | 10.8 |  | 0 | N/A |  |  | N/A | N/A |  | Y | Already completed. | [8 empty] | PP-797
Filters - Convenience features | state-button.component.ts | 10.9 |  | 0 | N/A |  |  | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-798
Filters - Convenience features | tab.component.ts | 6.8 |  | 0 | N/A |  |  | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-799
Filters - Convenience features | tabs.component.ts | 6.9 |  | 0 | N/A |  |  | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-800
Commonly Used | o2-choice.component.ts | 9.5 |  | 0 | N/A |  |  | N/A | N/A |  | Y | Already completed. | [8 empty] | PP-801
View Dashboard | card.component.ts | 9.6 | 9,9.1 | 0 | N/A |  |  | N/A | N/A |  | Y | Already completed. | [8 empty] | PP-802
Visualization Generation | patients-label.component.ts | 3.2.1 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code and should be removed from the source code. | [8 empty] | PP-803
Visualization Generation | rate-label.component.ts | 3.2.2 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code and should be removed from the source code. | [8 empty] | PP-804
Visualization Generation | readmission-label.component.ts | 3.2.3 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code and should be removed from the source code. | [8 empty] | PP-805
Label settings | threshold-line.component.ts | 8.9.1 |  | 3 | 2.5 |  |  | 0.5 | 0 |  | N | [5 empty] | Sprint 7 | 2021-05-17 | 2021-05-18 | Chandan | PP-806
Filters - Convenience features | o2-range-inputs.component.ts | 6.1.2 |  | 0 | N/A |  |  | N/A | N/A |  | N | This component isn't used anywhere in the current code. | [8 empty] | PP-807
Commonly Used | timeout-modal.component.ts | 9.5.3 |  | 2.5 | 1.75 |  |  | 0.5 | 0.25 |  | N | Requirement tests are done but not functionality. Possibly some can be added with o2-test tag. |  |  |  |  | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan | PP-808

## Services
|  |  |  | 200.25 | [6 empty] | 82
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Code Cleanup (Hrs) | Unit Test (Requirement) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id
Authentication & Authorization | user.service.ts | 12.6 |  | 1.75 | 1.5 |  | 3.25 | 0.25 |  |  | N | [5 empty] | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-809
Authentication & Authorization | click-capture.service.ts | 12.7 |  | 0.25 | 0.25 |  | 0.5 | 0 |  |  | N | [5 empty] | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-810
Authentication & Authorization | common-layout.service.ts | 12.4 |  | 0.5 | 0.5 |  | 1 | 0 |  |  | N | [5 empty] | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-811
Authentication & Authorization | http.service.ts | 12.1 |  | 2.5 | 2.5 |  | 5 | 0 |  |  | N | Some tests can be copied from Admin Panel project but there are differences between each method still. |  |  |  |  | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-812
Commonly Used | logging.service.ts | 12.5 |  | 0 | 0 |  | 0 | 0 |  |  | N | This file is empty. Can it be removed or updated? | [8 empty] | PP-813
Authentication & Authorization | session-timeout.service.ts | 12.3 |  | 2 | 2 |  | 4 | 0 |  |  | N | Have to look into testing event merge and switchMap. |  |  |  |  | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-814
Authentication & Authorization | account.service.ts | 12.2 |  | 0.5 | 0.5 |  | 1 | 0 |  |  | N | [5 empty] | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-815
Dataset upload and management | datasets.service.ts | 11 |  | 0 | 0 |  | 0 | 0 |  |  | Y | Already completed. | [8 empty] | PP-816
Filters - Entity filters | entity.service.ts | 7 |  | 2.5 | 1.5 |  | 4 | 1 |  | 1 | Y |  | 100% | 100% | 100% | 100% |  |  |  |  | PP-817
Filters - LOB filters | lob.service.ts | 15 |  | 0.25 | 0.25 |  | 0.5 | 0 |  |  | Y | Response models to be created. | 100% | 100% | 100% | 100% |  |  |  |  | PP-818
Filters - Location filters | location.service.ts | 6 |  | 2 | 1.5 |  | 3.5 | 0.5 |  | 1 | Y | Response models to be created. | 100% | 100% | 100% | 100% |  |  |  |  | PP-819
Filters - Service Line filters | service-line.service.ts | 8 |  | 3 | 2 |  | 5 | 1 |  | 1 | Y | Response models to be created. | 66.67% | 100% | 55.56% | 63.64% |  |  |  |  | PP-820
Filters - Time filters | time.service.ts | 14.2 |  | 2 | 1.5 |  | 3.5 | 0.5 |  | 1 | Y | Response models to be created. | 100% | 100% | 100% | 100% |  |  |  |  | PP-821
Visualization Generation | graph.service.ts (API-related) | 2.6 |  | 2.5 | 1.5 |  | 4 | 1 |  |  | N | Response models to be created. |  |  |  |  | Sprint 4 | 2021-04-09 | 2021-04-09 | Daya | PP-822
Visualization Generation | custom-tooltip.service.ts | 12.5.4 |  | 1.5 | 0 |  | 1.5 | 1.5 |  |  | Y | Need to verify TODO for hideTooltip method. | [8 empty] | PP-823
Visualization Generation | shared.service.ts | 2 |  | 29 | 25 |  | 54 | 4 |  | 4 | Y | Code cleanup includes finding which methods aren't used anymore. A few of the large methods aren't used and can be removed or commented out so time isn't wasted and can be reduced from Unit Test hours. | 94.86% | 81.93% | 90.91% | 95.56% | Spirint 3 |  |  | Michael | PP-824
Filters - Convenience features | sidenav-breadcrumb.service.ts | 2.5 |  | 14 | 14 |  | 28 | 0 |  |  | N | [5 empty] | Sprint 7 | 2021-05-28 | 2021-06-01 | Chandan | PP-825
Filters - Convenience features | o2-tooltip.service.ts | 12.5.6 |  | 0.25 | 0 |  | 0.25 | 0.25 |  |  | Y | Already completed. |  |  |  |  | Sprint 7 | 2021-05-25 | 2021-05-25 | Chandan | PP-826
Filters - Convenience features | tooltip.service | 12.5.3 |  | 3 | 3 |  | 6 | 0 |  |  | N | Unsure how to write test for HTML string creation. |  |  |  |  | Sprint 7 | 2021-05-25 | 2021-05-25 | Chandan | PP-827
Visualization Generation | p2-tooltip.service.ts | 12.5.2 |  | 2.5 | 2.5 |  | 5 | 0 |  |  | N | Unsure how to write test for HTML string creation. |  |  |  |  | Sprint 7 | 2021-05-25 | 2021-05-25 | Chandan | PP-828
Visualization Generation | graph-view.service.ts | 2.1 | 2 | 4 | 2 |  | 6 | 2 |  |  | N | Half of file not used. Decent amount of linting to be done. |  |  |  |  | Sprint 4 | 2021-04-09 | 2021-04-09 | Daya | PP-829
Visualization Generation | map-view.service.ts | 2.2 | 2 | 2.5 | 1.5 |  | 4 | 1 |  |  | N | Half of file not used. |  |  |  |  | Sprint 4 | 2021-04-09 | 2021-04-09 | Daya | PP-830
View Dashboard | o2-view-list.service.ts | 9 |  | 0 | 0 |  | 0 | 0 |  |  | Y | Already completed. | [8 empty] | PP-831
Dataset upload and management | select-dataset.service.ts | 11.1 |  | 2.5 | 1.5 |  | 4 | 1 |  |  | N | [5 empty] | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-832
Filters - Entity filters | entity-filter.service.ts | 7.1 |  | 2.5 | 1.5 |  | 4 | 1 |  |  | Y | Majority of file not used. | 100% | 100% | 100% | 100% |  |  |  |  | PP-833
Filters - Location filters | location-filter.service.ts | 6.1 |  | 4 | 2 |  | 6 | 2 |  |  | N | Some overlap with LocationService file with similar named functions. This is somewhat confusing when using across the project. | 90.48% | 94.12% | 71.43% | 90.24% | Sprint 6 | 2021-05-10 | 2021-05-10 | Chandan | PP-834
Filters - Service Line filters | service-line-filter.service.ts | 8.1 |  | 2.5 | 1.5 |  | 4 | 1 |  | 1 | Y | Majority of file not used. | 100% | 100% | 100% | 100% | Sprint 6 | 2021-05-17 | 2021-05-17 | Daya | PP-835
Filters - Time filters | time-filter.service.ts | 14.1 |  | 0.5 | 0 |  | 0.5 | 0.5 |  |  | N | File is more or less empty (commented out). It can be removed or cleaned up. |  |  |  |  | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-836
Commonly Used | validation.service.ts | 12.8 |  | 0.5 | 0 |  | 0.5 | 0.5 |  |  | N | Updates to file need to be copied over from Admin Panel repo and ran with updated import paths. |  |  |  |  | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-837
Dataset upload and management | data-statisticcase.service.ts | 11.2 |  | 0 | N/A |  | 0 | N/A |  |  | N | Service not used anywhere. | [8 empty] | PP-838
Visualization Generation | shareview.service.ts | 11.3 |  | 0 | N/A |  | 0 | N/A |  |  | N | Nothing in this file is being used. | [8 empty] | PP-839
Save or export Visualization | export.service.ts | 13 |  | 64 | 60 |  | 124 | 4 |  |  | N | [5 empty] | Sprint 8 | 2021-06-03 | 2021-06-15 | Daya | PP-840
Label settings | drag-and-drop.service.ts | 8.5 |  | 2 | 2 |  | 4 | 0 |  |  | N | [5 empty] | Sprint 7 | 2021-05-21 | 2021-05-21 | Chandan | PP-841
Visualization Generation | link-selection.service.ts | 2.1.2 |  | 1 | 0.75 | 0 | 1.75 | 0.25 |  |  | Y |  | 100% | 100% | 100% | 100% | Sprint 3 | 2021-03-26 | 2021-03-26 | Michael | PP-842
Visualization Generation | query-data.service.ts | 2.3 |  | 6 | 5 | -1.5 |  | 1 |  |  | N | Some code cleanup done when working with Node, Link, and Node Graph components. | 70 | 50 | 46 | 70 | Sprint 4 | 2021-04-08 | 2021-04-08 | Daya | PP-843
Filters - Convenience features | sidenav.service.ts | 10 |  | 0.5 | 0.25 |  |  | 0.25 |  |  | N | [5 empty] | Sprint 7 | 2021-05-25 | 2021-05-25 | Chandan | PP-844
Commonly Used | google-analytics.service.ts | 12.1.4 |  | 1 | 1 |  |  | 0 |  |  | N | [5 empty] | Sprint 7 | 2021-05-21 | 2021-05-21 | Chandan | PP-845
Benchmark settings customization & Benchmark Calculation | benchmark.service.ts | 2.1.1 | 2,2.3,2.4 | 15 | 14 |  |  | 1 |  |  | N | [5 empty] | Sprint 5 | 2021-04-21 | 2021-04-23 | Daya | PP-846
Filters - LOB filters | lob-filter.service.ts | 14.2 |  | 3.5 | 3 |  |  | 0.5 |  |  | N | [5 empty] | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-847
Filters - LOB filters | quality-filter.service.ts | 14.3 |  | 2 | 1.5 |  |  | 0.5 |  |  | N | Quality Filter not enabled in current P2. |  |  |  |  | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-848
Dataset upload and management | data-statistic.service.ts | 11.1 |  | 0 | N/A |  |  | N/A |  |  | N | Not being used. | [8 empty] | PP-849
Visualization Generation | graph.service.ts (Graph Interaction) | 2.1.2 |  | 8 | 7 |  |  | 1 |  |  | N | Not entirely sure how to test logic which has d3 dependencies. |  |  |  |  | Sprint 4 | 2021-04-11 | 2021-04-11 | Daya | PP-850
Commonly Used | data-storage.service.ts | 12.1.3 |  | 0 | N/A |  |  | N/A |  |  | N | No tests required for this file. | [8 empty] | PP-851
View Dashboard | views.service.ts | 9.1.2 |  | 2.25 | 2 |  |  | 0.25 |  |  | N | [5 empty] | Sprint 7 | 2021-05-21 | 2021-05-21 | Chandan | PP-852
Commonly Used | graphql-common.service.ts | 12.5.1 |  | 0.25 | 0 |  |  | 0.25 |  |  | N | Need to copy over from Admin Panel. |  |  |  |  | Sprint 7 | 2021-05-24 | 2021-05-24 | Chandan | PP-853
Commonly Used | p2.service.ts | 12.1.3 |  | 3.25 | 3 |  |  | 0.25 |  |  | N | [5 empty] | Sprint 7 | 2021-05-24 | 2021-05-24 | Chandan | PP-854
Save or export Visualization | png.service.ts | 13.1 |  | 1 | 0.5 |  |  | 0.5 |  |  | N | [5 empty] | Sprint 7 | 2021-05-24 | 2021-05-24 | Chandan | PP-855
Commonly Used | data-access.service.ts | 12.1.1 |  | 1.25 | 1.25 |  |  | 0 |  |  | N | [5 empty] | Sprint 7 | 2021-05-24 | 2021-05-24 | Chandan | PP-856
Commonly Used | storage.service.ts | 12.1.2 |  | 0.25 | 0 |  |  | 0.25 |  |  | N | Need to copy over from Admin Panel. |  |  |  |  | Sprint 7 | 2021-05-24 | 2021-05-24 | Chandan | PP-857

## Utilities
|  |  |  | 192.75 | [6 empty] | 0
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | Code Cleanup (Hrs) | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id
Visualization Generation | axes.utils.ts | 5.7 |  | 2 | 1.5 |  | 0.5 |  |  |  | N | [5 empty] | Sprint 5 | 2021-04-19 | 2021-04-19 | Daya | PP-858
Visualization Generation | axesareas.utils.ts | 5.8 |  | 6.5 | 6 |  | 0.5 |  |  |  | N | Look into unit testing D3. |  |  |  |  | Sprint 5 | 2021-04-20 | 2021-04-20 | Daya | PP-859
Visualization Generation | benchmark.utils.ts | 2.7 |  | 8.5 | 8 |  | 0.5 |  |  |  | N | Look into unit testing D3. |  |  |  |  | Sprint 5 | 2021-04-19 | 2021-04-20 | Michael | PP-860
Visualization Legend | legends.utils.ts | 5.6 |  | 5 | 5 |  | 0 |  |  |  | N | [5 empty] | Sprint 6 | 2021-04-26 | 2021-04-26 | Daya | PP-861
Visualization Generation | quadrants.utils.ts | 5.1 |  | 2.25 | 2 |  | 0.25 |  |  |  | N | Look into unit testing D3. |  |  |  |  | Sprint 5 | 2021-04-21 | 2021-04-21 | Daya | PP-862
Visualization Generation | renderEntity.utils.ts | 5 | 2,2.1.1 | 19 | 18 |  | 1 |  |  |  | N | Look into unit testing D3. |  |  |  |  | Sprint 5 | 2021-04-22 | 2021-04-26 | Daya | PP-863
Visualization Generation | request2D.utils.ts | 5.4 |  | 6 | 6 |  | 0 |  |  |  | N | [5 empty] | Sprint 5 | 2021-04-21 | 2021-04-21 | Daya | PP-864
Visualization Generation | shapes.utils.ts | 5.3 |  | 1 | 1 |  | 0 |  |  |  | N | [5 empty] | Sprint 5 | 2021-04-19 | 2021-04-19 | Daya | PP-865
Visualization Generation | stacking.utils.ts | 5.2 |  | 40 | 35 |  | 5 |  |  |  | N | This contains all of the 2D graph stacking logic which is fairly complex. |  |  |  |  | Sprint 6 | 2021-04-26 | 2021-05-03 | Daya | PP-866
Visualization Generation | title.utils.ts | 5.9 |  | 2 | 1.5 |  | 0.5 |  |  |  | N | Single method that isn't called anywhere. |  |  |  |  | Sprint 5 | 2021-04-19 | 2021-04-19 | Daya | PP-867
Visualization Generation | node-graph.utils.ts | 2.4 | 2,2.3 | 60 | 55 | -41 | 5 |  |  | 1 | N |  | 34.69% | 31.6% | 32.11% | 35.23% | Sprint 3, Sprint 4 | 2021-03-30 | 2021-04-12 | Michael | PP-868
Visualization Navigation | o2-context-menu.utils.ts | 11 |  | 0 | 0 |  | 0 |  |  |  | Y | Already completed. | [8 empty] | PP-869
Filters - Location filters | location-filter.utils.ts | 6.2 |  | 10 | 8.5 |  | 1.5 |  |  |  | N | [5 empty] | Sprint 6 | 2021-05-12 | 2021-05-13 | Daya | PP-870
Filters - Time filters | time-filter.utils.ts | 14.3 |  | 0.5 | 0.5 |  | 0 |  |  |  | N |  | The single util method in this file is not used anywhere. |  |  |  | Sprint 7 | 2021-06-09 | 2021-06-10 | Michael | PP-871
Commonly Used | logout.utils.ts | 10 |  | 0.5 |  |  | 0.5 |  |  |  | N | Copy over tests from Admin Panel and verify code coverage. |  |  |  |  | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-872
Visualization Generation | graph.utils.ts | 2.8 |  | 1.5 | 1.25 |  | 0.25 |  |  |  | N | [5 empty] | Sprint 4 | 2021-04-13 | 2021-04-13 | Michael | PP-873
Visualization Generation | p2-filters.utils | 2.9 |  | 4 | 3.5 |  | 0.5 |  |  |  | N | [5 empty] | Sprint 4 | 2021-04-14 | 2021-04-14 | Michael | PP-874
Visualization Generation | query-data.utils.ts | 2.3.1 |  | 4 | 3.5 |  | 0.5 |  |  |  | N | [5 empty] | Sprint 4 | 2021-04-13 | 2021-04-13 | Michael | PP-875
Commonly Used | user.utils.ts | 12.1.4 |  | 5 | 4.5 |  | 0.5 |  |  |  | N | [5 empty] | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-876
Commonly Used | data-storage.utils.ts | 12.1.5 |  | 3.5 | 3 |  | 0.5 |  |  |  | N | [5 empty] | Sprint 7 | 2021-06-07 | 2021-06-08 | Chandan | PP-877
Dataset upload and management | datasets.utils.ts | 11.3 |  | 6.5 | 6 |  | 0.5 |  |  |  | N | [5 empty] | Sprint 7 | 2021-06-09 | 2021-06-10 | Michael | PP-878
View Dashboard | views.utilts.ts | 9.2 |  | 0 | N/A |  | N/A |  |  |  | Y | Already completed. | [8 empty] | PP-879
Commonly Used | client.utils.ts | 12.1.6 |  | 1 | 0.5 |  | 0.5 |  |  |  | N | I believe most can be copied over and verified from Admin Panel. |  |  |  |  | Sprint 7 | 2021-06-08 | 2021-06-08 | Chandan | PP-880
Commonly Used | session.utils.ts | 12.1.7 |  | 4 | 3.5 |  | 0.5 |  |  |  | N | [5 empty] | Sprint 7 | 2021-06-08 | 2021-06-08 | Chandan | PP-881

## Pipes
|  |  |  | 13.25 | [6 empty] | 0
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id
Filters - Convenience features | breadcrumb-button-order.pipe.ts | 12.6.7 |  | 3.5 | 3.5 |  |  |  | 0 |  | N | Should unused methods have tests written? | [8 empty] | PP-882
Visualization Legend | benchmark-legend.pipe.ts | 12.6.8 |  | 0.25 | 0.25 |  |  |  | 0 |  | N | [9 empty] | PP-883
Commonly Used | counter-to-array.pipe | 12.6.5 |  | 0.25 | 0.25 |  |  |  | 0 |  | N | I don't believe this is used anywhere. | [8 empty] | PP-884
Filters - Convenience features | filter-tag.pipe.ts | 12.6.4 |  | 1.5 | 1.5 |  |  |  | 0 |  | N | [9 empty] | PP-885
Benchmark settings customization & Benchmark Calculation | iterate-over-object.pipe.ts | 7.5.2 |  | 0.25 | 0.25 |  |  |  | 0 |  | N | [9 empty] | PP-886
Visualization Generation | parent-child-order.pipe.ts | 12.6.4 |  | 2 | 1.5 |  |  |  | 0.5 |  | N | Possibly remove lodash package? |  |  |  |  | Sprint 4 | 2021-04-13 | 2021-04-13 | Michael | PP-887
Visualization Generation | rate-cost-item.pipe.ts | 12.6.3 |  | 0.75 | 0.75 |  |  |  | 0 |  | N | [5 empty] | Sprint 4 | 2021-04-13 | 2021-04-13 | Michael | PP-888
Filters - Time filters | time-filter-order.pipe.ts | 14.1.1 |  | 1.5 | 1 |  |  |  | 0.5 |  | N | [9 empty] | PP-889
Label settings | label-style.pipe.ts | 8.6 |  | 0.5 | 0.25 |  |  |  | 0.25 |  | N | Not used in code anywhere. | [8 empty] | PP-890
Benchmark settings customization & Benchmark Calculation | o2-autocomplete-search-filter.pipe.ts | 7.5.1 |  | 1 | 1 |  |  |  | 0 |  | N | [9 empty] | PP-891
Filters or Visualization Navigation Convenience features | o2-bread-crumb.pipe.ts | 12.6.2 |  | 0.25 | 0.25 |  |  |  | 0 |  | N | Not used in code anywhere. | [8 empty] | PP-892
Visualization Generation | validate-value.pipe.ts | 12.6.1 |  | 0.25 | 0.25 |  |  |  | 0 |  | N | [5 empty] | Sprint 4 | 2021-04-13 | 2021-04-13 | Michael | PP-893
Graph sorting setting options | order-style.pipe.ts | 12.6.9 |  | 0.75 | 0.5 |  |  |  | 0.25 |  | N | [9 empty] | PP-894
Save or export Visualization | kebab-case.pipe.ts | 13.4 |  | 0 | N/A |  |  |  | N/A |  | Y | I believe this is fully tested. | [8 empty] | PP-895
Save or export Visualization | sentence-case.pipe.ts | 13.5 |  | 0 | N/A |  |  |  | N/A |  | Y | I believe this is fully tested. | [8 empty] | PP-896
Filters - Geography (Location) filters | o2-radius-to-miles-pipe.ts | 7.2 |  | 0 | N/A |  |  |  | N/A |  | N | Not used in code anywhere. | [8 empty] | PP-897
Dataset upload and management | search-filter.pipe.ts | 11.1.1 |  | 0.5 | 0.5 |  |  |  | 0 |  | N | [9 empty] | PP-898

## Directives
|  |  |  | 14.5 | [6 empty] | 0
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id
Label settings | draggable.directive.ts [ediDraggableNode] | 8.7 |  | 1 | 1 |  |  |  | 0 |  | N | [5 empty] | Sprint 8 | 2021-06-11 | 2021-06-11 | Michael | PP-899
Label settings | draggable.directive.ts [o2Draggable] | 8.8 |  | 3 | 3 |  |  |  | 0 |  | N | [5 empty] | Sprint 8 | 2021-06-11 | 2021-06-11 | Michael | PP-900
Label settings | droppable.directive.ts | 8.9 |  | 5 | 5 |  |  |  | 0 |  | N | [5 empty] | Sprint 8 | 2021-06-11 | 2021-06-14 | Michael | PP-901
Commonly Used | autofocus.directive.ts [p2Autofocus] | 16.1 |  | 1.25 | 1.25 |  |  |  | 0 |  | N | [5 empty] | Sprint 8 | 2021-06-08 | 2021-06-08 | Chandan | PP-902
Commonly Used | click-redirect.directive.ts [p2ClickRedirect] | 16.2 |  | 1.25 | 1 |  |  |  | 0.25 |  | N | [5 empty] | Sprint 8 | 2021-06-08 | 2021-06-08 | Chandan | PP-903
Commonly Used | o2-click-outside.directive.ts | 16.3 |  | 0 | N/A |  |  |  | N/A |  | Y | Already completed. | [8 empty] | PP-904
Commonly Used | scroll.directive.ts [p2TrackScroll] | 16.4 |  | 1.5 | 0.5 |  |  |  | 1 |  | N | Compare with cleaned/updated version in Admin Panel. |  |  |  |  | Sprint 8 | 2021-06-08 | 2021-06-08 | Chandan | PP-905
Visualization Generation | zoomable.directive.ts | 16.7 |  | 0.5 | 0.5 |  |  |  | 0 |  | N | [5 empty] | Sprint 8 | 2021-06-08 | 2021-06-08 | Chandan | PP-906
Commonly Used | clickable.directive.ts | 16.8 |  | 1 | 1 |  |  |  | 0 |  | N | Have to look into testing timer Observable. |  |  |  |  | Sprint 8 | 2021-06-08 | 2021-06-08 | Chandan | PP-907

## Misc.
|  |  |  | 21.5 | [6 empty] | 0
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Cleanup (Story Points) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id
Commonly Used | error.handler.ts | 12.7 |  | 2 | 2 |  |  |  | Refactor to match updated handler in Admin Panel? |  | N | Have to look into testing error handler methods. |  |  |  |  | Sprint 8 | 2021-06-11 | 2021-06-11 | Chandan | PP-908
Commonly Used | http.interceptor.ts | 12.7.2 |  | 1.5 | 1.5 |  |  |  | Refactor to match updated interceptor in Admin Panel? |  | N | Have to look into testing interceptors. |  |  |  |  | Sprint 8 | 2021-06-11 | 2021-06-11 | Chandan | PP-909
Commonly Used | validators.ts | 12.7.3 |  | 2.25 | 2 |  |  |  | 0.25 |  | N | Updates to file need to be copied over from Admin Panel repo first. |  |  |  |  | Sprint 8 | 2021-06-11 | 2021-06-11 | Chandan | PP-910
Visualization Generation | arc.helper.ts | 12.7.4 |  | 2.75 | 2.5 |  |  |  | 0.25 |  | N | Unsure how much of this can be tested since it's just a file of variables as functions. |  |  |  |  | Sprint 9 | 2021-06-16 | 2021-06-16 | Daya | PP-911
Visualization Generation | size.helper.ts | 12.7.5 |  | 0 | N/A |  |  |  | N/A |  | N | Unsure how these would be tested. | [8 empty] | PP-912
Visualization Generation | transition.helper.ts | 12.7.6 |  | 2.5 | 2 |  |  |  | 0.5 |  | N | Unsure how much of this can be tested since it's just a file of variables as functions. |  |  |  |  | Sprint 9 | 2021-06-15 | 2021-06-15 | Michael | PP-913
Visualization Generation | distribution-map.dto.ts | 12.7.7 |  | 2.25 | 2 |  |  |  | 0.25 |  | N | [5 empty] | Sprint 9 | 2021-06-15 | 2021-06-15 | Michael | PP-914
Visualization Generation | graph-details.dto.ts | 12.7.8 |  | 4 | 3.5 |  |  |  | 0.5 |  | N | [5 empty] | Sprint 9 | 2021-06-15 | 2021-06-15 | Michael | PP-915
Visualization Generation | legend-label.dto.ts | 12.7.9 |  | 0.75 | 0.75 | [5 empty] | N | [5 empty] | Sprint 9 | 2021-06-16 | 2021-06-16 | Daya | PP-916
Visualization Generation | o2-base-chart.dto.ts | 12.7.1 |  | 3.5 | 3 |  |  |  | 0.5 |  | N | [5 empty] | Sprint 9 | 2021-06-16 | 2021-06-16 | Daya | PP-917

## Auth0
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id
Authentication & Authorization | Create sample application in Auth0 as SPA | 1.8.1 | [8 empty] | Y | [8 empty] | Chandan | PP-933
Authentication & Authorization | @auth0/auth0-angular library integration with p2 | 1.8.2 | [8 empty] | Y | [8 empty] | Chandan | PP-918
Authentication & Authorization | Create login authentication with Auth0 and retreive the token | 1.8.3 |  | 6 | [12 empty] | Sprint 4 | 2021-04-02 | 2021-04-02 | Chandan | PP-919
Authentication & Authorization | Configure audience details in auth0 | 1.8.4 |  | 8 | [12 empty] | Sprint 4 | 2021-04-05 | 2021-04-05 | Chandan | PP-920
Authentication & Authorization | Get the access token with audience info | 1.8.5 | 1.8.1 | 6 | [12 empty] | Sprint 4 | 2021-04-06 | 2021-04-06 | Chandan | PP-921
Authentication & Authorization | Use Auth0 classic login page to customize to make it closure to our login UI | 1.8.6 |  | 12 | [12 empty] | Sprint 4 | 2021-04-07 | 2021-04-09 | Chandan | PP-922
Authentication & Authorization | Write an interceptor to use the access token and send it across to API call | 1.8.7 |  | 10 | [15 empty] | Chandan | PP-923
Authentication & Authorization | Sample component which call Rep0 tokenort view API with valid Auth0 token | 1.8.8 |  | 4 | [13 empty] | 2021-04-12 | 2021-04-12 | Chandan | PP-924
Authentication & Authorization | Validate token at BE code for authorization | 1.9.1 | 1.8.5 | 4 | [12 empty] | Sprint 4 | 2021-04-06 | 2021-04-06 | Manoj | PP-925
Authentication & Authorization | Write util/decorator at BE to validate authorization for each API call | 1.9.2 |  | 8 | [12 empty] | Sprint 4 | 2021-04-06 | 2021-04-07 | Manoj | PP-926
Authentication & Authorization | Write HttpInterceptor at FE to send Auth0 token to each API call. | 1.9.3 |  | 10 | [12 empty] | Sprint 4 | 2021-04-12 | 2021-04-13 | Chandan | PP-927
Authentication & Authorization | Use AuthGaurd to protect component from unauthorize access | 1.9.3 |  | 12 | [12 empty] | Sprint 4 | 2021-04-13 | 2021-04-14 | Chandan | PP-928
Authentication & Authorization | Use customized Login screen for Auth0 login integration | 1.9.4 | [17 empty] | Chandan | PP-929
Authentication & Authorization | Implement forgot/reset password | 1.9.5 |  | 6 | [12 empty] | Sprint 4 | 2021-04-16 | 2021-04-16 | Chandan | PP-930
Authentication & Authorization | UI changes for forgot password | 1.9.6 |  | 12 | [15 empty] | Chandan | PP-931
Authentication & Authorization | How to configure different environments with different configurations | 1.9.7 | [18 empty] | PP-932