## Description
Design document: | Dataset Manager Technical Design
Jira project: | P2 next gen (PP)
Jira label: | Tests
Number of tasks:
Number of reported bugs:
Estimated development time [h] (designer):
Estimated development time [h] (reviewer):
Estimated development time [h] (pm):
Total time spent [h]:

## Tasks
WBS | Name | Description | Depends on | Estimated work time [h] |  |  |  | Assignee | Actual work time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment | planned dev time | qa/dev ratio [%]
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Make a cleanup in tests library | [12 empty] | PP-246
1.1 | ‘2D graph’ - finish and update the unfinished tests. |  |  | 20 | 20 | 16 | 20 | Swatantra | March 24, 2021, 1:00 PM | April 1, 2021, 2:59 PM | 56 |  |  | PP-301 |  | Sprint 3 | Abandoned
1.2 | Changes in columns |  |  | 1 | 2 | 4 | 4 | [6 empty] | PP-303 |  | Sprint 3 | Abandoned
1.3 | Update graph combination filter tests to use all existing types of filters | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 | 20 | Monika | March 19, 2021, 8:18 AM |  |  |  |  | PP-304 |  | Sprint 3 | Abandoned
1.4 | Update map view filter combination tests to use all existing filter types | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 | 20 | Monika | March 26, 2021, 8:26 AM |  |  |  |  | PP-305 |  | Sprint 3 | Abandoned
1.5 | Update 2D graph view filter combination tests to use all existing filter types | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 | 20 | Paulina | March 23, 2021, 8:51 AM | March 26, 2021, 8:51 AM | 15 |  |  | PP-306 |  | Sprint 3 | Abandoned
1.6 | Review and prune tests from Benchmark Average on Graph tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | 20 | Piotr | [5 empty] | PP-493 |  | Sprint 3 | Abandoned
1.7 | Review and prune tests from Benchmark Perecentile on Graph tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | 20 | [6 empty] | PP-494 |  | Sprint 3 | Abandoned
1.8 | Review and prune tests from Benchmark Average&Percentile_Map tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | 20 | [6 empty] | PP-495 |  | Sprint 3 | Abandoned
1.9 | Review and prune tests from Dataset Management tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | 20 | Paulina | March 18, 2021, 3:56 PM | March 26, 2021, 8:26 AM | 12 |  |  | PP-457 |  | Sprint 3 | Abandoned
1.10 | Review and prune tests from Labels tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 16 | 16 | 20 | 20 | Kamil | March 18, 2021, 4:16 PM |  |  |  |  | PP-459 |  | Sprint 3 | Abandoned
1.11 | Prepare statistics of automated testcases for old suite | [5 empty] | 0 | [6 empty] | PP-498 |  | Sprint 3 | Added during sprint
1.11.1 | Statistics for 1st part of the testcases |  |  |  |  | 8 | 8 | Kamil | March 24, 2021, 8:16 AM | March 24, 2021, 5:16 PM | 8 |  |  | PP-499 |  | Sprint 3 | Added during sprint
1.11.2 | Statistics for 2nd part of the testcases |  |  |  |  | 8 | 8 | Piotr | March 24, 2021, 8:16 AM | March 24, 2021, 5:16 PM | 8 |  |  | PP-500 |  | Sprint 3 | Added during sprint
1.12 | Add categories types to missing testcases after initial cleanup |  |  |  |  | 8 | 8 | Paulina | March 24, 2021, 10:04 AM | March 24, 2021, 3:08 PM | 5 |  |  | PP-501 |  | Sprint 3 | Added during sprint
2 | Integration tests of p2backend | [12 empty] | PP-697
2.1 | Testing caseSummaryCollection query | [12 empty] | PP-266
2.1.1 | Test caseSummaryCollection - market share graph | - Check response with multiple normal/LDS datasets - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: 1.1 | 24 | 24 | 16 | 24 | [6 empty] | PP-267 |  | Sprint 4 | Moved from Sprint 3 | 214
2.1.2 | Test caseSummaryCollection - benchmark graph | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: | 24 | 24 | 16 | 24 | [6 empty] | PP-268
2.1.3 | Test caseSummaryCollection - 2D graph | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings and combinations - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: | 24 | 24 | 16 | 24 | [6 empty] | PP-269
2.2 | Test caseLobCounts query | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests)" | BE: 1.3 | 6 | 8 | 8 | 8 | Swatantra | April 5, 2021, 2:03 PM |  |  |  |  | PP-546 |  | Sprint 4 | Moved from Sprint 3 | 10
2.3 | Test getAvailableYears query | see design - Check results for multiple normal/LDS datasets - Check pagination | BE: 1.4 | 4 | 4 | 4 | 4 | Swatantra | April 1, 2021, 4:32 PM | April 5, 2021, 2:01 PM |  |  |  | PP-547 |  | Sprint 4 | Moved from Sprint 3 | 10
2.4 | Test getDateTimeStatsForListOfYears query | see design - Check results for multiple normal/LDS datasets - Check pagination | BE: 1.5 | 6 | 8 | 8 | 8 | [6 empty] | PP-548 |  | Sprint 4 | Moved from Sprint 3 | 6
2.5 | Test filteredCareUnitTypes query | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests) | BE: 1.6 | 8 | 8 | 8 | 8 | Paulina | April 6, 2021, 1:00 PM |  |  |  |  | PP-549 |  | Sprint 4 | Moved from Sprint 3 | 12
2.6 | Test getDatasetsInitialFilters query | see design - Check normal/LDS datasets in combinations - Check boolean input fields | BE: 1.7 | 10 | 12 | 16 | 16 | [6 empty] | PP-550 |  | Sprint 4 | Moved from Sprint 3 | 10
2.7 | Report view | [12 empty] | PP-551 |  |  |  | 68
2.7.1 | Test ReportView query | design - Check if returne fields are correct and the if the response structure is as expected | BE: 3 | 12 | 12 | 16 | 16 | Paulina | April 1, 2021, 8:18 AM | April 6, 2021, 1:02 PM |  |  |  | PP-552 |  | Sprint 4 | Moved from Sprint 3
2.7.2 | Test ReportViews query | design - Check if the number of views returned is correct - Check if different user's id can be provided | BE: 3 | 10 | 12 | 16 | 16 | [6 empty] | PP-553 |  |  | Moved from Sprint 3
2.7.3 | Test SearchReportViews query | design - Search Report Views based on their names - Search Report Views based on the datasets used by the views | BE: 3 | 10 | 12 | 16 | 16 | [6 empty] | PP-554 |  |  | Moved from Sprint 3
2.7.4 | Test CreateReportView query | design - Check all possible input parameters with the special focus on: reportViewType, datasets and filters - Check if a view can be created for another user | BE: 3 | 16 | 16 | 16 | 16 | Paulina | March 30, 2021, 8:36 AM | April 1, 2021, 8:17 AM | 16 |  |  | PP-555 |  | Sprint 4 | Moved from Sprint 3
2.7.5 | Test UpdateReportView query | design - Check all possible input parameters with the special focus on: reportViewType, datasets and filters - Cases when an updated view doesn't exist or is deleted - Check if another user's view can e updated | BE: 3 | 16 | 16 | 16 | 16 | [6 empty] | PP-556 |  |  | Moved from Sprint 3
2.7.6 | Test DeleteReportView mutation | design - Delete existing ReportView and check if it was truly deleted (no appearing in ReportView and ReportViews queries) - Try deleting a ReportView that doesn't exist and/or the one that was already deleted | BE: 3 | 4 | 4 | 8 | 8 | [6 empty] | PP-557 |  |  | Moved from Sprint 3
2.8 | Getting datasets list | [12 empty] | PP-558
2.8.1 | allDatasets endpoint | see design - Check if datasets are returned correctly (the amount and names) - Check the correctness of upload status (upload can be finished, failed or in progress) - if possible now - Check if upload start and finish time are correct - if possible for now | BE: 1.17 | 14 |  | 12 | 14 | [6 empty] | PP-559 |  | Sprint 4 | Moved from Sprint 3 | 33
2.8.2 | getLDSDatasetsIDs endpoint | see design Check the query when there're multiple LDS and normal datasets uploaded | BE: 1.16 | 4 |  | 4 | 4 | [6 empty] | PP-560 |  | Sprint 4 | Moved from Sprint 3 | 4
2.9 | caseLocationDetails endpoint | see design - Check results for different dataset type - Check results for CBSA, FIPS, state, no option chosen |  | 10 |  | 8 | 10 | [6 empty] | PP-561 |  |  |  | 56
2.10 | searchCareUnitAndDetail endpoint | see design - Check data for different types of datasets - Check data for every type of entity |  | 14 |  | 16 | 16 | [6 empty] | PP-562 |  |  |  | 119
2.11 | filteredCareUnits endpoint | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests) |  | 10 |  | 10 | 10 | [6 empty] | PP-626 |  |  |  | 14
2.12 | caseSummaryCollectionMapView endpoint | see design | [11 empty] | PP-627 |  |  |  | 60
2.12.1 | caseSummaryCollectionMapView - marketshare map | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings |  | 16 |  | 20 | 20 | [6 empty] | PP-628
2.12.2 | caseSummaryCollectionMapView - benchmark map | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings - Check all filter types combinations |  | 16 |  | 20 | 20 | [6 empty] | PP-629
2.13 | Node Expand and Collapse | see design |  |  |  |  | 32 | [6 empty] | PP-630 |  |  |  | 52
2.13.1 | Node Expand and Collapse - marketshare graph | see design Check expanding/collapsing all AC/PAC types on all layers |  | 12 |  | 16 | 16 | [6 empty] | PP-631
2.13.2 | Node Expand and Collapse - benchmark graph | see design Check expanding/collapsing all AC/PAC types and all Service Lines on all layers |  | 12 |  | 16 | 16 | [6 empty] | PP-632
2.14 | Integration tests of p2backend report generator | [12 empty] | PP-563
2.14.1 | Research - pytest tools to generate tests report | Research about available tools to generate report for p2 integration tests. The following libraries were tested: pytest-csv pytest-excel pytest-html |  | 8 |  | 8 | 8 | [6 empty] | PP-564 |  |  | Moved from Sprint 3
2.14.2 | Implementation of tests report generator - structure of worksheets |  |  | 8 |  | 8 | 8 | [6 empty] | PP-565 |  |  | Moved from Sprint 3
2.14.3 | Implementation of tests report generator - summarize tabs |  |  | 8 |  | 8 | 8 | [6 empty] | PP-566 |  |  | Moved from Sprint 3
2.15 | ServiceLine API | [12 empty] | PP-633
2.15.1 | test searchServiceLine endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 4 |  |  | 4 | [6 empty] | PP-634
2.15.2 | test searchAllDiagnose endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | [6 empty] | PP-635
2.15.3 | test filteredServiceLines endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 4 |  |  | 4 | [6 empty] | PP-636
2.15.4 | test filteredClinicalEpisodes endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | [6 empty] | PP-637
2.15.5 | test filteredDRGs endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | [6 empty] | PP-638
2.16 | Location API | [12 empty] | PP-639
2.16.1 | test allUSStates endpoint | - check correctness of the response |  | 4 |  |  | 4 | [6 empty] | PP-640 |  | Sprint 4
2.16.2 | test usState endpoint | - check correctness of the response |  | 4 |  |  | 4 | [6 empty] | PP-641 |  | Sprint 4
2.16.3 | test searchUsLocation endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 6 |  |  | 6 | [6 empty] | PP-642 |  | Sprint 4
2.16.4 | test usStateGeoAll endpoint | - check correctness of the response |  | 4 |  |  | 4 | [6 empty] | PP-643 |  | Sprint 4
2.16.5 | test usCountyGeoForState endpoint | - check correctness of the response |  | 4 |  |  | 4 | [6 empty] | PP-644 |  | Sprint 4
2.16.6 | test usStateGeoSearch | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | [6 empty] | PP-645 |  | Sprint 4
2.16.7 | test usCountyGeoAll endpoint | - check correctness of the response |  | 5 |  |  | 5 | [6 empty] | PP-646 |  | Sprint 4
2.16.8 | test locationByRadialLocation endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 12 |  |  | 12 | [6 empty] | PP-647 |  | Sprint 4
3 | Front End tests | [12 empty] | PP-648
3.1 | Changes in regression library | [12 empty] | PP-649
3.1.1 | Authentication & Authorization | make a cleanup in the tab following the rules from the design |  | 16 |  |  | 16 | [6 empty] | PP-650
3.1.2 | Dataset Upload & Management | make a cleanup in the tab following the rules from the design |  | 20 | [9 empty] | PP-698
3.1.3 | View Dashboard | make a cleanup in the tab following the rules from the design |  | 16 |  |  | 16 | [6 empty] | PP-651
3.1.4 | Location Filter | make a cleanup in the tab following the rules from the design |  | 32 |  |  | 32 | [6 empty] | PP-652
3.1.5 | Entity Filter | make a cleanup in the tab following the rules from the design |  | 32 |  |  | 32 | [6 empty] | PP-653
3.1.6 | Service Line filter | make a cleanup in the tab following the rules from the design |  | 28 |  |  | 28 | [6 empty] | PP-654
3.1.7 | LOB Filter | make a cleanup in the tab following the rules from the design |  | 16 |  |  | 16 | [6 empty] | PP-655
3.1.8 | Graph View | make a cleanup in the tab following the rules from the design |  | 40 |  |  | 40 | [6 empty] | PP-656
3.1.9 | Map View | make a cleanup in the tab following the rules from the design |  | 32 |  |  | 32 | [6 empty] | PP-657
3.1.10 | 2D Graph View | make a cleanup in the tab following the rules from the design |  | 40 |  |  | 40 | [6 empty] | PP-658
3.1.11 | Benchmark Settings and calculations on Graph | make a cleanup in the tab following the rules from the design |  | 40 |  |  | 40 | [6 empty] | PP-659
3.1.12 | Benchmark Settings and calculations on Map | make a cleanup in the tab following the rules from the design |  | 40 |  |  | 40 | [6 empty] | PP-660
3.1.13 | Benchmark Settings and calculations on 2D | make a cleanup in the tab following the rules from the design |  | 40 |  |  | 40 | [6 empty] | PP-661
3.1.14 | Label settings | make a cleanup in the tab following the rules from the design |  | 24 |  |  | 24 | [6 empty] | PP-662
3.1.15 | LDS suppression rule-11 (after implementation add LDS test cases to check CC11 ) | make a cleanup in the tab following the rules from the design |  | 40 |  |  | 40 | [6 empty] | PP-663
3.1.16 | Save or export Visualization | make a cleanup in the tab following the rules from the design |  | 24 |  |  | 24 | [6 empty] | PP-664
3.1.17 | System | make a cleanup in the tab following the rules from the design |  | 8 |  |  | 8 | [6 empty] | PP-665
3.2. | Automating regression library test cases | [12 empty] | PP-666
3.2.1 | Authentication & Authorization | automate tests from the tab |  | 16 |  |  | 16 | [6 empty] | PP-667
3.2.2 | Dataset Upload & Management | automate tests from the tab |  | 20 | [9 empty] | PP-699
3.2.3 | View Dashboard | automate tests from the tab |  | 16 |  |  | 16 | [6 empty] | PP-668
3.2.4 | Location Filter | automate tests from the tab |  | 32 |  |  | 32 | [6 empty] | PP-669
3.2.5 | Entity Filter | automate tests from the tab |  | 28 |  |  | 28 | [6 empty] | PP-670
3.2.6 | Service Line filter | automate tests from the tab |  | 24 |  |  | 24 | [6 empty] | PP-671
3.2.7 | LOB Filter | automate tests from the tab |  | 16 |  |  | 16 | [6 empty] | PP-672
3.2.8 | Graph View | automate tests from the tab |  | 40 |  |  | 40 | [6 empty] | PP-673
3.2.9 | Map View | automate tests from the tab |  | 40 |  |  | 40 | [6 empty] | PP-674
3.2.10 | 2D Graph View | automate tests from the tab |  | 48 |  |  | 48 | [6 empty] | PP-675
3.2.11 | Benchmark Settings and calculations on Graph | automate tests from the tab |  | 32 |  |  | 32 | [6 empty] | PP-676
3.2.12 | Benchmark Settings and calculations on Map | automate tests from the tab |  | 40 |  |  | 40 | [6 empty] | PP-677
3.2.13 | Benchmark Settings and calculations on 2D | automate tests from the tab |  | 40 |  |  | 40 | [6 empty] | PP-678
3.2.14 | Label settings | automate tests from the tab |  | 24 |  |  | 24 | [6 empty] | PP-679
3.2.15 | LDS suppression rule-11 (after implementation add LDS test cases to check CC11 ) | automate tests from the tab |  | 48 |  |  | 48 | [6 empty] | PP-680
3.2.16 | Save or export Visualization | automate tests from the tab |  | 30 |  |  | 30 | [6 empty] | PP-681
3.2.17 | System | automate tests from the tab |  | 10 |  |  | 10 | [6 empty] | PP-682
4 | Unit tests analysis and implementation | [12 empty] | PP-683
4.1 | group_nodes method |  | BE: 1.1.12 |  |  | 40 | 40 | Monika | [5 empty] | PP-574 |  | Sprint 4 | Started in Sprint 3
4.2 | calculate_benchmark method |  | BE: 1.11.7 |  |  | 40 | 40 | Monika | [5 empty] | PP-684 |  | Sprint 5
4.3 | single packed node on each side in calculate_benchmark method |  | BE: 1.14.11 |  |  | 40 | 40 | Monika | [5 empty] | PP-685 |  | Sprint 6
5 | Performance tests | [12 empty] | PP-688
5.1 | Backend |  |  |  |  | 160 | 160 | [6 empty] | PP-689
5.2 | Front End |  |  |  |  | 200 | 200 | [6 empty] | PP-690
6 | Automation of generating tests result | [12 empty] | PP-691
6.1. | Set up repository | Set up new project on gitlab |  | 4 | 4 |  | 4 | [6 empty] | PP-692
6.2. | Implementing of merger dataset | Implementing class to merge datasets used in p2 |  | 8 | 8 |  | 8 | [6 empty] | PP-693
6.3. | Implementing of auxiliary functions | Implementing of auxiliary functions for calculation |  | 8 | 8 |  | 8 | [6 empty] | PP-694
6.4. | Implementing of methods to generate json | Implementing of methods to generate json |  | 8 | 8 |  | 8 | [6 empty] | PP-695
6.5. | Implementing fixture to read expected results from json | Implementing fixture to read expected results from json in the FE tests |  | 8 |  |  | 8 | [6 empty] | PP-700
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions