## Description
Design document: | Dataset Manager Technical Design
Jira project: | P2 next gen (PP)
Jira label: | Authorization
Number of tasks: | 23
Number of reported bugs: | 0
Estimated development time [h] (designer): | 65.5
Estimated development time [h] (reviewer): | 72
Estimated development time [h] (pm): | 102
Estimated testing time [h] (tester): | 0
Estimated testing time [h] (pm): | 0
Total time spent [h]: | 3.5

## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  | Assigned developer | Estimated testing time [h] |  | Assigned tester | Actual development time |  |  | Commit statistics |  | Estimated code documentation time [h] | Jira ID | Commit ID | Sprint | Comment
|  |  |  | Designer | Reviewer | PM |  | Tester | PM |  | Start time | Finish time | Duration [h] | Insertions | Deletions
0 | Project configuration | Create a project from a template and add library requirements |  | 1.5 | 1 | 1 |  |  |  |  | March 17, 2021, 11:15 AM | March 17, 2021, 12:46 PM | 1.5 | 911 | 0 |  | PP-458 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/commit/ac08f1f7e84a69a59f3c81703ec52026c9ed2afb | Sprint 2
1 | Describing abstract classes | Describe abstract classes and helper classes (like classes in model.py) | 0 | 1 |  | 1 |  |  |  |  | March 23, 2021, 10:11 AM | March 22, 2021, 2:56 PM |  | 196 | 87 |  | PP-485 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/2 | Sprint 3 | postponed from Sprint 2; Problem with actual time estimation, because of not updated jira
2 | DatasetStorage mock implementation | Implement mock implementation of DatasetStorage for use in tests (documentation). | 0, 1 | 2 | 2 | 4 |  |  |  |  | March 17, 2021, 2:00 PM | March 17, 2021, 4:00 PM | 2 | 211 | 2 |  | PP-311 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/1 | Sprint 3 | postponed from Sprint 2
3 | Access mock implementation | Implement mock implementation of Access for use in tests (documentation). | 0, 1 | 4 | 4 | 4 |  |  |  |  | March 17, 2021, 4:00 PM | March 22, 2021, 9:17 AM |  |  |  |  | PP-312 |  | Sprint 3 | postponed from Sprint 2
4 | DatasetManager implementation | implement the final version of the class according to the documentation (only class with methods without graphql) | 2, 3 | [7 empty] | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM |  |  |  |  | PP-313
4.1 | Implement get() | implement method according to the documentation |  | 5 | 6 | 8 |  |  |  |  | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM |  |  |  |  | PP-314 |  | Sprint 3
4.2 | Implement share() | implement method according to the documentation |  | 1.5 | 1.5 | 2 |  |  |  |  | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM |  |  |  |  | PP-315 |  | Sprint 3
4.3 | Implement unshare() | implement method according to the documentation |  | 1.5 | 1.5 | 2 |  |  |  |  | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM |  |  |  |  | PP-316 |  | Sprint 3
4.4 | Implement register() | implement method according to the documentation |  | 1.5 | 1.5 | 2 |  |  |  |  | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM |  |  |  |  | PP-317 |  | Sprint 3
4.5 | Implement remove() | implement method according to the documentation |  | 1.5 | 1.5 | 2 |  |  |  |  | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM |  |  |  |  | PP-318 |  | Sprint 3
4.6 | Implement add_user() | implement method according to the documentation |  | 1.5 | 1.5 | 2 |  |  |  |  | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM |  |  |  |  | PP-486 |  | Sprint 3
4.7 | Implement add_parameter() | implement method according to the documentation |  | 1.5 | 1.5 | 2 |  |  |  |  | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM |  |  |  |  | PP-487 |  | Sprint 3
5 | GraphQL server implementation |  | 4 | [13 empty] | PP-319
5.1 | Create model | You have to create a model the chosen technology (graphene) and pass all the requiered objects to it. |  | 4 | 6 | 8 | [10 empty] | PP-320 |  | Sprint 3
5.2 | Implement get() endpoint | create a graphql endpoint according to the documentation with filters | 5.1 | 5 | 6 | 8 | [10 empty] | PP-321 |  | Sprint 3
5.3 | Implement share() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | [10 empty] | PP-322 |  | Sprint 3
5.4 | Implement unshare() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | [10 empty] | PP-323 |  | Sprint 3
5.5 | Implement register() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | [10 empty] | PP-324 |  | Sprint 3
5.6 | Implement remove() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | [10 empty] | PP-325 |  | Sprint 3
5.7 | Implement add_user() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | [10 empty] | PP-488 |  | Sprint 3
5.8 | Implement add_parameter() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | [10 empty] | PP-489 |  | Sprint 3
6 | Access on SQLAlchemy implementation | create models in sqlalchemy and implement abstract methods from access class.Create a model according to sql queries | 3 | 8 | 8 | 12 | [10 empty] | PP-326 |  | Sprint 3
7 | Admin panel implementation | Implement the admin panel using the Flask-Admin library | 5 | 6 | 8 | 16 | [10 empty] | PP-490
8 | Flask integration | Integrate the flask server with sqlalchemy and graphene | 5, 6 | 4 | 6 | 8 | [10 empty] | PP-491
9 | DatasetStorage implementation | Implement implementation of DatasetStoage with selected warehouse (snowflake) | 2 | 4 | 4 | 8 | [10 empty] | PP-492

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions