## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  | Developer | Estimated testing time [h] |  | Tester | Actual development time |  |  | Commit statistics |  | Estimated code documentation time [h] | Jira ID | Commit ID | Sprint | Comment
|  |  |  | Designer | Reviewer | PM (Artur) |  | Tester () | PM (Artur) |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | AWS Lambda | see design | [14 empty] | PP-328
1.1 | Set up the empty o2-grouper-lambda project | prepare the dev / qa / release branches, use p2-backend-v3 as template |  | 6 | 0.5 | 1 | Adrian Z. |  |  |  | March 5, 2021, 10:52 AM | March 5, 2021, 11:24 AM | 0.5 | 721 | 1 |  | PP-329 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/commit/6e6f779574b800e2cd18cf806f01585869a33c88 | Sprint 2
1.2 | Create AWS lambda o2-grouper function | dev / qa / release versions |  | 3 | 3 | 4 | Adrian Z. |  |  |  | March 5, 2021, 11:30 AM | March 5, 2021, 4:14 PM | 5 | 9 | 0 |  | PP-330 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/1 | Sprint 2
1.3 | Create the API o2-grouper endpoints | dev / qa / release versions | 1.2 | 4 | 4 | 4 | Adrian Z. |  |  |  | March 8, 2021, 12:16 PM | March 8, 2021, 1:16 PM | 1 |  |  |  | PP-331 |  | Sprint 2 | No any commits - setup of AWS.
1.4 | Set up the CI/CD pipeline | deploy to AWS lambda | 1.1 - 1.2 | 6 | 8 | 8 | Adrian Z. |  |  |  | March 5, 2021, 4:47 PM | March 9, 2021, 2:34 PM | 15 | 35 | 8 |  | PP-332 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/5 | Sprint 2
1.5 | Implement configuration validation |  | 1.4 | 4 | 4 | 6 | Adrian Z. |  |  |  | March 16, 2021, 11:19 AM | March 16, 2021, 4:53 PM | 5.5 | 360 | 1 |  | PP-333 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/10 | Sprint 2
1.6 | Implement creation of pipeline description object | create from validated configuration | 1.5, 1.9 | 3 | 4 | 4 | Adrian Z. |  |  |  | March 18, 2021, 10:22 AM | March 18, 2021, 12:34 PM | 2 | 109 | 1 |  | PP-334 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/12 | Sprint 2
1.7 | Register new pipeline in the database (or find existing) |  | 1.6, 2.1, 3 | 3 | 3 | 2 | [10 empty] | PP-335
1.8 | Initiatie the pyspark job (databricks) |  | 1.7, 3.2 | 8 | 8 | 12 | Adrian Z. |  |  |  | March 15, 2021, 9:47 AM | March 16, 2021, 10:20 AM | 9 | 77 | 5 |  | PP-336 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/9 | Sprint 2
1.9 | Auth token validation | extract user_id from token | 1.4 | 6 | 4 | 2 | Adrian Z. |  |  |  | March 16, 2021, 3:59 PM | March 17, 2021, 10:11 PM | 4 | 138 | 1 |  | PP-337 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/11 | Sprint 2
2 | Pipeline Database | [15 empty] | PP-338
2.1 | Set up dev / qa / release databases (postgres/aurora) | can use existing instances, create public schema for pipelines |  | 4 | 4 | 4 | Adrian Z. | [9 empty] | PP-339
3 | O2 Grouper Job | [15 empty] | PP-340
3.1 | Set up the empty o2-grouper-job project in python |  |  | 4 | 0.5 | 1 | Adrian Z. |  |  |  | March 5, 2021, 10:51 AM | March 5, 2021, 11:23 AM | 0.5 | 721 | 1 |  | PP-341 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/commit/6e6f779574b800e2cd18cf806f01585869a33c88 | Sprint 2
3.2 | Prepare the CI/CD pipelines for the o2-grouper-job project | Must be deployed to databricks | 3.1 | 16 | 16 | 20 | Adrian Z. |  |  |  | March 9, 2021, 3:22 PM | March 11, 2021, 9:15 AM | 14 | 30 | 1 |  | PP-342 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/commit/6e6f779574b800e2cd18cf806f01585869a33c88 | Sprint 2
3.3 | Repository | see design | [14 empty] | PP-343
3.3.1 | Define AbstractRepository and implement MockRepository (in-memory) | only implement the methods: add_pipeline, add_artifact, find_artifact in the MockRepository |  | 10 | 12 | 16 | Adrian Z. |  |  |  | March 19, 2021, 10:07 AM | March 22, 2021, 11:15 AM |  |  |  |  | PP-344 |  | Sprint 3 | Sprint 2 and Sprint 3
3.3.5 | Read o2-grouper.config file | see design |  | 2 | 1 | 1 | Adrian Z. |  |  |  | March 22, 2021, 11:14 AM | March 22, 2021, 12:00 PM |  |  |  |  | PP-412 |  | Sprint 3
3.3.2 | Implent PipelineRepository | use postgres database connector, use SQLAlchemy for implementation of queries, only implement the methods: add_pipeline, add_artifact, find_artifact |  | 12 | 12 | 16 | Adrian Z. |  |  |  | March 22, 2021, 12:00 PM | March 24, 2021, 10:19 AM |  |  |  |  | PP-413 |  | Sprint 3
3.3.3 | Define AbstractFileSystem and implement MockFileSystem (for tests) | see design |  | 6 | 8 | 8 | Adrian Z. |  |  |  | March 24, 2021, 9:23 AM | March 24, 2021, 12:45 PM |  |  |  |  | PP-414 |  | Sprint 3
3.3.4 | Implement DBFS class implementing AbstractFileSystem interface | see design |  | 8 | 16 | 16 | Adrian Z. | [9 empty] | PP-415 |  | Sprint 3
3.4 | Dataset schema recognition | see design | [14 empty] | PP-345
3.4.1 | Implement detect_schema method |  | 3.2, 3.3 | 3 | 3 | 4 | [10 empty] | PP-346 |  | Sprint 3
3.4.2 | Implement resolve_dataset_id method |  | 3.2, 3.3 | 4 | 4 | 4 | [10 empty] | PP-347 |  | Sprint 3
3.4.3 | Implement get_dataset_schema method |  | 3.4.1, 3.4.2 | 5 | 4 | 8 | [10 empty] | PP-348 |  | Sprint 3
3.5 | LDS dataset validation | see design | [14 empty] | PP-349
3.5.1 | Implement get_claim_file_type method |  |  | 3 | 3 | 2 | [10 empty] | PP-350 |  | Sprint 3
3.5.2 | Implement find_fts_file method |  |  | 3.5 | 2 | 2 | [10 empty] | PP-351 |  | Sprint 3
3.5.3 | Implement read_fts method |  |  | 5.5 | 8 | 8 | [10 empty] | PP-352 |  | Sprint 3
3.5.4 | Implement read_claims_file method |  |  | 3.5 | 4 | 4 | [10 empty] | PP-353 |  | Sprint 3
3.5.5 | Implement LDSDataset class |  | 3.5.1 - 3.5.4 | 6.5 | 8 | 10 | [10 empty] | PP-354 |  | Sprint 3
3.6 | P2 dataset validation | see design | [14 empty] | PP-355
3.6.1 | Adapt validation code from the existing project | use pandas for validation, drop invalid lines, store validation statistics | 3.3.1 | 24 | 32 | 32 | [10 empty] | PP-416 |  | Sprint 3
3.6.2 | Implement P2UploadDataset | implement all methods |  | 18 | 20 | 24 | [10 empty] | PP-417
3.6.3 | Implement import_as_parquet method | see design |  | 16 | 16 | 16 | [10 empty] | PP-418
3.6.4 | Implement pipeline steps: schema recognition, validation, import and integrate with the pipeline | Integrate already implemented functions and classes | 3.4, 3.5, 3.6.1 | 24 | 32 | 40 | [10 empty] | PP-419
3.6.5 | Collect and report validation statistics | see also pipeline statistics | 3.6.4, 4.6 | 8 | 8 | 16 | [10 empty] | PP-420
3.7 | Stay Maker 1 (CMS) | see design | [14 empty] | PP-421 |  |  | Low priority
3.7.1 | Implement make_lds_stays | use the existing scala implementation | 3.2, 3.3.2 | 40 | 40 | 40 | [10 empty] | PP-422
3.7.2 | Integrate stay maker 1 with the pipeline |  | 3.7.1 | 4 | 8 | 8 | [10 empty] | PP-423
3.8 | Stay Maker 2 (P2 Upload) | see design | [14 empty] | PP-424
3.8.1 | Implement make_p2_stays method |  |  | 32 | 40 | 40 | [10 empty] | PP-425
3.8.2 | Integrate stay maker 2 with the pipeline |  |  | 4 | 8 | 8 | [10 empty] | PP-426
3.8.3 | Collect and report stay maker's statistics | see design | 3.8.2, 4.6 | 8 | 8 | 8 | [10 empty] | PP-427
3.9 | Episode Maker | [15 empty] | PP-428
3.9.1 | Implement get_anchor_drgs in PipelineRepository |  | 3.3.2 | 6 | 4 | 4 | [10 empty] | PP-429
3.9.2 | Implement get_excluded_drgs in PipelineRepository |  | 3.3.2 | 3 | 4 | 4 | [10 empty] | PP-430
3.9.3 | Implement get_excluded_icds in PipelineRepository |  | 3.3.2 | 3 | 4 | 4 | [10 empty] | PP-431
3.9.4 | Implement make_episodes method | use the existing scala implementation | 3.9.1 - 3.9.3, 3.2, 3.3.2 | 32 | 40 | 40 | [10 empty] | PP-432
3.9.5 | Integrate episode maker with the pipeline |  | 3.9.4 | 4 | 8 | 8 | [10 empty] | PP-433
3.9.6 | Collect and report the episode maker's statistics |  | 3.9.5, 4.6 | 8 | 8 | 8 | [10 empty] | PP-434
3.10 | Relation Maker | see design | [14 empty] | PP-435
3.10.1 | Implement get_valid_entities method in PipelineRepository | fetch data generated by the "Entities PIpeline", return only the NPI number column | 3.3.2 | 10 | 4 | 2 | [10 empty] | PP-436
3.10.2 | Implement make_relations method | translate and refactor the scala code | 3.9.1 - 3.9.3, 3.2, 3.3.2 | 32 | 40 | 40 | [10 empty] | PP-437
3.10.3 | Integrate relation maker with the pipeline |  | 3.10.2 | 4 | 8 | 8 | [10 empty] | PP-438
3.10.4 | Collect and report the relation maker's statistics |  | 3.10.2, 4.6 | 6 | 8 | 8 | [10 empty] | PP-439
4 | Pipeline Logs & Status Reporting | see design | [14 empty] | PP-440
4.1 | Implement add_log method in PipelineRepository |  | 3.3.2 | 2 | 2 | 4 | [10 empty] | PP-441
4.2 | Add global error handler, log errorr |  | 3.2 | 2 | 2 | 4 | [10 empty] | PP-442
4.3 | Implemet set_status method in PipelineRepository |  | 3.3.2 | 1.5 | 2 | 4 | [10 empty] | PP-443
4.4 | Implement set_stage method in PIpelineRepository |  | 3.3.2 | 1.5 | 2 | 4 | [10 empty] | PP-444
4.5 | Set status and stage during pipeline execution |  | 3.6 - 3.9 | 2 | 2 | 4 | [10 empty] | PP-445
4.6 | Implement the update_statistics method in PipelineRepository |  | 3.3.2 | 16 | 16 | 12 | [10 empty] | PP-446
5 | Dataset publishing and pipelne control | [15 empty] | PP-447
5.1 | Implement publish_relations_dataset method |  | DM, 3.3 | 24 | 28 | 32 | [10 empty] | PP-448
5.2 | Handle the pipeline_id control parameter |  | 1 - 3 | 3 | 3 | 3 | [10 empty] | PP-449
5.3 | Handle the template_pipeline_id parameter |  | 1 - 3 | 6.5 | 8 | 8 | [10 empty] | PP-450
5.4 | Handle start_from / stop_at parameters |  | 1 - 3 | 8 | 8 | 8 | [10 empty] | PP-451
5.5 | Implement published variables validation | integrate with the configuration validation (see design) | 1 | 3 | [12 empty] | PP-535
5.6 | Fill in published variable values | process publish_to JSON object | 5.5 | 3.5 | [12 empty] | PP-536