## Description
Design document: | Preferred Partners Backend v3
Jira project: | P2 next gen (PP)
Jira label: | P2_v3
Number of tasks:
Number of reported bugs:
Estimated development time [h] (designer):
Estimated development time [h] (reviewer):
Estimated development time [h] (pm):
Estimated testing time [h] (tester):
Estimated testing time [h] (pm):
Total time spent [h]:

## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  |  | Assigned developer | Actual development time |  |  | Commit statistics |  | Estimated code documentation time [h] | Jira ID | Commit ID | Sprint | Comment
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Analytical API | [13 empty] | PP-226
1.1 | caseSummaryCollection endpoint | This is the basic functionality with filtering but without: benchmarks, pagination or sorting, some response elements are not present in the outputs | [12 empty] | PP-247
1.1.1 | Implement Filter and derived classes - ColumnFilter, DistanceFilter |  |  | 3 | 4 | 4 |  | Michał | February 22, 2021, 5:13 PM | February 23, 2021, 12:08 PM | 8 | 570 | 0 |  | PP-227 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/2 | Sprint 1 | More time due to code analysis tool rejections.
1.1.2 | Implement extract_filters for the CaseSummaryFilterInputType input |  | 1.1.1 | 16 | 20 | 24 |  | Maciej | February 23, 2021, 2:11 PM | March 1, 2021, 6:13 PM | 32 | 391 | 1 |  | PP-228 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/8 | Sprint 1
1.1.3 | Implement extract_filters for the CaseSummaryActionsInputType input |  | 1.1.1 | 4 | 4 | 6 |  | Aleksandra | March 4, 2021, 1:38 PM | March 11, 2021, 11:56 AM | 15 | 301 | 181 |  | PP-229 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/19 | Sprint 2
1.1.4 | Implement extract_filters for the RangeInputType input |  | 1.1.1 | 2 | 2 | 4 |  | Maciej | March 1, 2021, 12:13 PM | March 1, 2021, 6:13 PM | 4 | 391 | 1 |  | PP-230 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/8 | Sprint 1
1.1.5 | Implement filter_by method for pandas.DataFrame with the ColumnFilter |  | 1.1.1 | 4 | 4 | 6 |  | Michał | February 25, 2021, 5:46 PM | February 26, 2021, 4:25 PM | 7 | 86 | 18 |  | PP-231 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/6 | Sprint 1 | More time due to code review rejection.
1.1.6 | Implement filter_by method for pandas.DataFrame with the DistanceFilter |  | 1.1.1 | 12 | 16 | 16 |  | Michał | February 26, 2021, 3:08 PM | March 1, 2021, 5:48 PM | 10 | 69 | 23 |  | PP-232 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/7 | Sprint 1
1.1.19 | Implement filter_by method for pandas.DataFrame with the RangeFilter |  | 1.1.1 | 2 |  | 4 |  | Maciej | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 2.5 | 77 | 13 |  | PP-307 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/11 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks.
1.1.7 | Implement Node, NodeTypeEnum and NodeSubTypeEnum classes, implement get_node_type_from_subtype method |  |  | 3 | 4 | 6 |  | Maciej | February 23, 2021, 1:06 PM | February 23, 2021, 1:42 PM | 3 | 98 | 0 |  | PP-233 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/3 | Sprint 1 | Forgot to change jira status at the beginning of the work on task.
1.1.8 | Implement PandasProvider class (extending the AnalyticsProvider) | We should be able to pull data from files (available in the project) and join with entities_ac / entities_pac automatically / carelines |  | 8 | 12 | 16 |  | Michał | February 23, 2021, 12:12 PM | February 25, 2021, 3:43 PM | 19 | 130 | 0 |  | PP-234 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/4 | Sprint 1 | More time spend due to fixes after code review + code fixes after more rigorous code analysis tool was implemented.
1.1.20 | Add computed column fiscal_date to PandasAnalyticalService | fiscal_date = fiscal_year * 10 + fiscal_quarter |  | 2 |  | 4 |  | Maciej | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 2.5 | 77 | 13 |  | PP-308 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/11 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks.
1.1.9 | Implement the PandasAnalyticalService find_nodes method | leave other methods unimplemented, all types of nodes should be supported | 1.1.8, 1.1.5, 1.1.6 | 16 | 20 | 24 |  | Michał | March 2, 2021, 10:32 AM | March 3, 2021, 05:45 PM | 16 | 120 | 6 |  | PP-235 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/13 | Sprint 1
1.1.10 | Implement AbstractGraphQuery class and make_abstract_graph_query method | for now only implement the methods get_nodes and get_filters, leave the others unimplemented | 1.1.1 - 1.1.9 | 3 | 4 | 4 |  | Aleksandra | March 9, 2021, 10:32 AM | March 11, 2021, 11:56 AM | 15 | 301 | 181 |  | PP-236 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/19 | Sprint 2 | postponed from Sprint 1
1.1.11 | Implement AbstractGraphModel class and the make_abstract_graph_model method | for now do not handle the sorting or pagination info | 1.1.10 | 3 | 4 | 4 |  | Aleksandra | March 9, 2021, 10:32 AM | March 11, 2021, 11:56 AM | 15 | 301 | 181 |  | PP-237 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/19 | Sprint 2 | postponed from Sprint 1
1.1.12 | Implement PandasAnalyticalService group_nodes method | All types of nodes should be supported | 1.1.8 | 32 | 40 | 48 |  | Maciej | March 4, 2021, 4:01 PM | March 16, 2021, 11:26PM | 64 | 707 | 345 |  | PP-238 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/29 | Sprint 2 | postponed from Sprint 1; finish delayed due to bug #1
1.1.13 | Implement SummaryStatistics class and extract_node_statistics method | All types of nodes should be supported | 1.1.12 | 18 | 24 | 24 |  | Maciej | March 16, 2021, 12:04 PM | March 18, 2021, 1:43 PM | 18 | 347 | 7 |  | PP-239 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/49 | Sprint 2 | postponed from Sprint 1
1.1.14 | Implement extract_relation_statistics method | For now do not extract benchmark_value | 1.1.13 | 5 | 8 | 8 |  | Maciej | March 19, 2021, 11:34 AM | March 19, 2021, 4:26 PM | 5 | 195 | 46 |  | PP-240 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/57 | Sprint 2
1.1.15 | Implement PandasAnalyticalService get_entity_details method | Just pull matching data from entities data frames | 1.1.9 | 4 | 4 | 4 |  | Michał | March 8, 2021, 2:48 PM | March 9, 2021, 1:42 PM | 8 | 63 | 11 |  | PP-241 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/16 | Sprint 2
1.1.16 | Implement copy_summary_statistics method |  | 1.1.13 | 4 | 4 | 4 |  | Aleksandra | March 18, 2021, 5:55 PM | March 19, 2021, 12:55 PM | 4 | 530 | 0 |  | PP-242 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/54 | Sprint 2
1.1.24 | Implement copy_node_details method |  |  | 4 |  | 4 |  | Maciej | March 24, 2021, 9:21 AM | March 25, 2021, 3:55 PM | 10 | 152 | 22 |  | PP-502 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/75 | Sprint 3 | Added to sprint in Sprint 3
1.1.17 | Implement CaseSummaryQueryRunner class | For now ignore the groupingInfo, benchmarkValues, count and legendData responses, ignore benchmark Future argument | 1.1.1 - 1.1.16, 1.1.24, 1.1.25 | 28 | 32 | 32 |  | Maciej | March 22, 2021, 9:50 AM | [5 empty] | PP-243 |  | Sprint 3 | postponed from Sprint 2
1.1.25 | Implement format_case_summary_element method |  |  | 4 |  | 4 |  | Maciej | [6 empty] | PP-575 |  | Sprint 3 | Added to sprint in Sprint 3
1.1.18 | implement caseSummaryCollection endpoint |  | 1.1.17 | 4 | 4 | 4 |  | Maciej | [6 empty] | PP-244 |  | Sprint 3 | Sprint 3 due to dependencies
1.1.21 | Implement get_sql_filter for Node | should return python object | 1.1.7 | 5 |  | 8 |  | Maciej | March 3, 2021, 4:58 PM | March 4, 2021, 1:39 PM | 4 | 72 | 6 |  | PP-309 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/14 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks.
1.1.22 | Implement get_sql_group_column for Node | should return python object | 1.1.7 | 4 |  | 6 |  | Maciej | March 3, 2021, 4:58 PM | March 4, 2021, 1:39 PM | 4 | 73 | 7 |  | PP-310 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/14 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks.
1.1.23 | Implement get_sql_chilld_id column for Node |  | 1.1.7 | 4 |  | 4 |  | Maciej | March 9, 2021, 12:41 PM | March 9, 2021, 12:58 PM | 1 | 51 | 1 |  | PP-368 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/15 | Sprint 2
1.2 | caseLocationDetails endpoint | For now we ignore the "state" output which is likely not used | [12 empty] | PP-248
1.2.1 | implement extract_filters method | The method takes CaseLocationOptionInputType as input, use already existing extract_filters method implementation for the nested types | 1.1.2 - 1.1.4 | 6 | 8 | 8 |  | Michał | March 17, 2021, 1:56 PM | March 17, 2021, 6:32 PM | 7 | 171 | 21 |  | PP-249 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/46 | Sprint 2
1.2.2 | implement get_entity_counts method in PandasAnalyticalService | use data frames provided in the examples, calculate statistics both for PACs and hospitals | 1.1.8, 1.2.1 | 20 | 24 | 24 |  | Michał | March 9, 2021, 4:58 PM | March 12, 2021, 4:14PM | 24 | 188 | 4 |  | PP-250 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/22 | Sprint 2
1.2.3 | implement copy_location_details method |  |  | 8 | 12 | 16 |  | Michał | March 15, 2021, 1:07 PM | March 17, 2021, 3:59 PM | 18 | 137 | 6 |  | PP-251 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/35 | Sprint 2
1.2.4 | implement caseLocationDetails endpoint |  | 1.2.1 - 1.2.3 | 4 | 8 | 8 |  | Michał | March 17, 2021, 6:32 PM | March 19, 2021, 5:41 PM | 16 | 819 | 373 |  | PP-252 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/60 | Sprint 3 | postponed from Sprint 2
1.3 | caseLobCounts endpoint | see design | [12 empty] | PP-253
1.3.1 | implement get_lob_statistics in PandasAnalyticalService |  | 1.1.8 | 4 | 4 | 4 |  | Aleksandra | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 1 | 60 | 4 |  | PP-254 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/21 | Sprint 2
1.3.2 | implement copy_lob_statistics method |  |  | 3.5 | 4 | 2 |  | Aleksandra | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 1 | 60 | 4 |  | PP-255 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/21 | Sprint 2
1.3.3 | Implement caseLobCounts endpoint | see design | 1.3.1, 1.3.2 | 1 | 2 | 4 |  | Aleksandra | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 1 | 60 | 4 |  | PP-256 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/21 | Sprint 2
1.4 | getAvailableYears endpoint | see design | [12 empty] | PP-257
1.4.1 | Implement get_all_years method in PandasAnalitycalService |  | 1.1.8 | 2 | 2 | 2 |  | Aleksandra | March 12, 2021, 1:52 PM | March 15, 2021, 11:25 AM | 2 | 50 | 13 |  | PP-258 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/25 | Sprint 2
1.4.2 | Implement get_row_range helper method for pandas DF |  |  | 1 | 2 | 4 |  | Aleksandra | March 12, 2021, 1:52 PM | March 15, 2021, 11:28 AM | 2 | 30 | 1 |  | PP-259 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/26 | Sprint 2
1.4.3 | Implement getAvailableYears endpoint | see design | 1.4.1, 1.4.2 | 1 | 2 | 4 |  | Aleksandra | March 12, 2021, 1:52 PM | March 15, 2021, 11:29 AM | 2 | 47 | 0 |  | PP-260 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/27 | Sprint 2
1.5 | getDateTimeStatsForListOfYears endpoint | see design | [12 empty] | PP-261
1.5.1 | implement get_quarterly_statistics method in PandasAnalyticalService |  | 1.1.8 | 3 | 4 | 4 |  | Tomek We | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 5 | 67 | 7 |  | PP-262 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/23 | Sprint 2
1.5.2 | implement copy_quarterly_statistics method |  |  | 2 | 2 | 2 |  | Tomek We | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 5 | 67 | 7 |  | PP-263 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/23 | Sprint 2
1.5.3 | implement getDateTimeStatsForListOfYears endpoint | see design | 1.5.1, 1.5.2 | 2 | 2 | 4 |  | Tomek We | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 5 | 67 | 7 |  | PP-264 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/23 | Sprint 2
1.6 | implement filteredCareUnitTypes endpoint | see design | [12 empty] | PP-265
1.6.1 | Implement get_careunit_statistics method in PandasAnalyticalService |  | 1.1.8 | 3 | 4 | 4 |  | Tomek We | March 5, 2021, 3:33 PM | March 10, 2021, 6:12 PM | 9 | 72 | 3 |  | PP-285 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/18 | Sprint 2
1.6.2 | Implement extract_careunit_statistics method |  |  | 2 | 2 | 4 |  | Tomek We | March 5, 2021, 3:33 PM | March 10, 2021, 6:12 PM | 9 | 72 | 3 |  | PP-286 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/18 | Sprint 2
1.6.3 | Implement filteredCareUnitTypes endpoint | see design | 1.6.1, 1.6.2 | 1 | 2 | 4 |  | Tomek We | March 9, 2021, 11:43 AM | March 10, 2021, 6:12 PM | 9 | 74 | 4 |  | PP-265 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/18 | Sprint 2
1.7 | implement getDatasetsInitialFilters | see design | [12 empty] | PP-288
1.7.1 | Implement get_diagnose_statistics method in PandasAnalyticalService |  | 1.1.8 | 3.5 | 4 | 4 |  | Aleksandra | February 25, 2021, 2:55 PM | March 4, 2021, 01:19 AM | 16 | 247 | 4 |  | PP-289 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/12 | Sprint 1 | Added during sprint, due to earlier finish of research tasks. | Did 10 hour estimate from PM really turn into 48 hours of implementation? Why? What have we learnt that allows us to make better estimates?
1.7.2 | implement copy_diagnose_statistics method |  |  | 2 | 2 | 2 |  | Aleksandra | March 1, 2021, 5:02 PM | March 4, 2021, 01:19 AM | 16 | 247 | 4 |  | PP-290 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/12 | Sprint 1 | Added during sprint, due to earlier finish of research tasks.
1.7.3 | implement getDatasetsInitialFilters endpoint | use existing queries / methods to populate data in the requested fields | 1.3, 1.4, 1.5, 1.6 | 6 | 6 | 4 |  | Aleksandra | March 1, 2021, 5:03 PM | March 4, 2021, 01:19 AM | 16 | 247 | 4 |  | PP-291 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/12 | Sprint 1 | Added during sprint, due to earlier finish of research tasks. Task to be finished - dependencies have to be implemented later.
1.8 | filteredCareUnits endpoint | see design | [12 empty] | PP-371
1.8.3 | Implement format_careunits method |  |  | 3.5 | 4 | 4 | [8 empty] | PP-375 |  | Sprint 4
1.8.4 | Implement findCareUnits endpoint |  | 1.6, 1.8.3, 1.13 | 8 | 4 | 10 | [8 empty] | PP-376 |  | Sprint 4
1.9 | searchCareUnitAndDetail endpoint | see design | [12 empty] | PP-377
1.9.1 | Implement make_hospital_node |  |  | 1 | 1 | 2 |  | Aleksandra | March 16, 2021, 5:07 PM | March 17, 2021, 2:11 PM | 3 | 21 | 0 |  | PP-378 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/44 | Sprint 2 | Added to sprint in Sprint 2
1.9.2 | Implement make_entity_node |  |  | 2.5 | 2 | 2 |  | Aleksandra | March 16, 2021, 5:07 PM | March 17, 2021, 2:11 PM | 3 | 21 | 0 |  | PP-379 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/44 | Sprint 2 | Added to sprint in Sprint 2
1.9.3 | Handle result_set argument in the group_nodes method (inside PandasAnalyticalService) | handle only SHORT and FULL GroupNodesResultSet values | 1.1.12 | 5 | 12 | 16 |  | Aleksandra | March 17, 2021, 5:44 PM | March 17, 2021, 8:03 PM | 2.5 | 107 | 26 |  | PP-380 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/47 | Sprint 2 | Added to sprint in Sprint 2 | Why are we so far off on this estimate?
1.9.4 | Modify extract_node_statistics to extract full result | extract 60-day readmission statistics when available | 1.1.13 | 2.5 | 4 | 4 |  | Manoj | March 22, 2021, 5:34 PM | March 22, 2021, 4:16 PM | 4 | 65 | 6 |  | PP-381 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/61 | Sprint 3 | Problem with actual time estimation, because of not updated jira
1.9.5 | Implement get_careunit_details method |  | 1.1.15, 1.9.4 | 4 | 4 | 6 |  | Manoj | March 22, 2021, 5:35 PM | March 22, 2021, 7:43 AM | 6 | 133 | 8 |  | PP-382 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/62 | Sprint 3
1.9.6 | Implement get_entity_address in PandasAnalyticalService | provide required datasets | 1.1.9 | 8 | 6 | 8 |  | Manoj | March 18, 2021, 8:14 AM | March 19, 2021, 4:28 PM | 16 | 41 | 1 |  | PP-383 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/58 | Sprint 3 | Problem with actual time estimation, because of not updated jira
1.9.7 | Implement make_address method |  |  | 1 | 1 | 2 |  | Manoj | March 19, 2021, 4:55 PM | March 19, 2021, 4:43PM | 2 | 24 | 1 |  | PP-384 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/59 | Sprint 3 | Problem with actual time estimation, because of not updated jira
1.9.8 | Implement get_entity_quality in PandasAnalyticalService |  | 1.9.6 | 26 | 32 | 36 |  | Bartek | [6 empty] | PP-385 |  | Sprint 4 | Postponed from sprint 3 (lower priority)
1.9.9 | Implement make_quality method |  |  | 1 | 1 | 1 |  | Manoj | March 24, 2021, 2:00 PM | March 24, 2021, 10:24 AM | 1.66 | 11 | 1 |  | PP-386 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/70 | Sprint 3 | Problem with actual time estimation, because of not updated jira
1.9.10 | Implement get_facility_details in PandasAnalyticalService |  | 1.9.6 | 18 | 16 | 24 |  | Bartek | [6 empty] | PP-387 |  | Sprint 4 | Postponed from sprint 3 (lower priority)
1.9.11 | Implement make_facility method |  |  | 1 | 1 | 2 |  | Manoj | March 24, 2021, 2:02 PM | March 24, 2021, 10:24 AM | 1.66 | 11 | 1 |  | PP-388 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/70 | Sprint 3 | Problem with actual time estimation, because of not updated jira
1.9.12 | Implement get_entity_staffing in PandasAnalyticalService |  | 1.9.6 | 4 | 4 | 4 |  | Manoj | March 23, 2021, 5:03 PM | March 24, 2021, 10:31 AM | 4 | 33 | 0 |  | PP-389 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/71 | Sprint 3
1.9.13 | Implement make_staffing method |  |  | 1 | 1 | 2 |  | Manoj | March 23, 2021, 5:03 PM | March 24, 2021, 10:24 AM | 1.66 | 11 | 1 |  | PP-390 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/70 | Sprint 3
1.9.14 | Implement searchCareUnitAndDetail endpoint |  | 1.9.1 - 1.9.13 | 8 | 8 | 10 |  | Bartek | [6 empty] | PP-391 |  | Sprint 4 | Postponed from sprint 3 (lower priority)
1.10 | getDateTimesForYear endpoint | see design | [12 empty] | PP-392
1.10.1 | Implement find_fiscal_quarters method in PandasAnalyticalService |  | 1.1.9 | 3 | 2 | 8 |  | Bartek | March 16, 2021, 11:54 AM | March 17, 2021, 1:29 PM | 5 | 59 | 6 |  | PP-393 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/33 | Sprint 2 | Added to sprint in Sprint 2
1.10.2 | Implement getDateTimesForYear endpoint |  | 1.10.1 | 3 | 2 | 4 |  | Bartek | March 16, 2021, 11:54 AM | March 17, 2021, 1:29 PM | 5 | 59 | 6 |  | PP-394 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/33 | Sprint 2 | Added to sprint in Sprint 2
1.11 | Benchmark Calculation | see design | [12 empty] | PP-395
1.11.1 | Implement get_dataset_properties in the DatasetService | see DatasetService design | DM | 4 | 3 | 8 | [8 empty] | PP-396
1.11.2 | Implement set_dataset_properties in DatasetService |  | DM | 6 | 3 | 8 | [8 empty] | PP-397
1.11.3 | Implement find_datasets in DatasetService |  | DM | 4 | 4 | 4 | [8 empty] | PP-398
1.11.4 | Implement get_time_range in PandasAnalyticalService |  | 1.1.8 | 3 | 2 | 4 |  | Bartek | March 18, 2021, 12:36 PM | March 19, 2021, 12:25 PM | 8 | 33 | 3 |  | PP-399 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/50 | Sprint 2 | Added to sprint in Sprint 2
1.11.5 | Implement find_dataset_time_range | use mock DatasetService for tests |  | 4 | 3 | 4 |  | Bartek | March 19, 2021, 11:36 AM | March 22, 2021, 9:56 AM | 6 | 123 | 12 |  | PP-400 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/55 | Sprint 3
1.11.6 | Implement find_benchmark_datasets method | use mock DatasetService for tests | 1.11.4, 1.11.5 | 6 | 6 | 8 |  | Bartek | March 22, 2021, 10:24 AM | March 24, 2021, 4:18 PM | 20 | 153 | 44 |  | PP-401 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/63 | Sprint 3 | Require reimplementation due to misunderstanding of requirements: https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/63
1.11.7 | Implement calculate_benchmark method in PandasAnalyticalService | for now do not implement any special handling of AC_Entity / PAC_Entity nodes, do not handle packed nodes | 1.1.8 | 40 | 40 | 48 |  | Aleksandra | March 19, 2021, 6:26 PM | [5 empty] | PP-402 |  | Sprint 3 | Delayed significantly due to COVID
1.11.8 | Implement get_service_line in PandasAnalyticalService |  | 1.1.8 | 3 | 3 | 4 |  | Bartek | March 23, 2021, 9:49 AM | March 24, 2021, 4:39 PM | 6 | 31 | 1 |  | PP-403 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/67 | Sprint 3
1.11.9 | Implement get_clinical_episode in PandasAnalyticalService |  | 1.1.8 | 3 | 3 | 4 |  | Bartek | March 23, 2021, 3:19 PM | March 24, 2021, 4:23PM | 4 | 25 | 2 |  | PP-404 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/68 | Sprint 3
1.11.10 | Implement get_parent_node method |  | 1.11.8, 1.11.9 | 3 | 2 | 4 |  | Bartek | March 24, 2021, 2:54 PM | March 25, 2021, 11:27 PM | 4 | 95 | 9 |  | PP-405 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/74 | Sprint 3
1.11.11 | Handle parent nodes in calculate_benchmark method | see design | 1.11.7 | 12 | 8 | 16 |  | Aleksandra | [6 empty] | PP-406 |  | Sprint 3
1.11.12 | Implement extract_time_range method | see design |  | 3.5 | 3 | 4 |  | Michał | March 24, 2021, 10:47 AM | March 24, 2021, 4:00 PM | 4 | 39 | 2 |  | PP-407 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/72 | Sprint 3
1.11.13 | Implement make_filter (from time range) method | see design | 1.11.12 | 1.5 | 3 | 4 |  | Michał | [6 empty] | PP-408 |  | Sprint 4 | Postponed from sprint 3 (lower priority)
1.11.14 | Extract benchmark_value in extract_relation_statistics method | see design | 1.1.14 | 6 | 8 | 16 |  | Michał | March 25, 2021, 9:55 AM | March 25, 2021, 3:55 PM | 6 | 40 | 0 |  | PP-409 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/78 | Sprint 3
1.11.15 | Handle benchmark future argument in CaseSummaryQueryRunner |  | 1.1.17 | 16 | 16 | 16 | [8 empty] | PP-410 |  | Sprint 4
1.11.16 | Integrate benchmark calculations with the caseSummaryCollection query | see design | 1.11.4 - 1.11.15 | 24 | 24 | 32 | [8 empty] | PP-411 |  | Sprint 4
1.11.17 | Implement handling of packed nodes in calculate_benchmark (use decompose_packed_nodes decorator) | see design, implement a unit test for this use case | 1.14.7, 1.14.11 | 6 |  | 8 | [8 empty] | PP-503 |  | Sprint 4
1.12 | Node Expand and Collapse | see design | [12 empty] | PP-460
1.12.1 | Implement extract_action method | see design |  | 4 | 4 | 8 | [8 empty] | PP-461 |  | Sprint 5
1.12.2 | Implement make_filter_from_node method | see design | 1.1.7, 1.1.21 - 1.1.23 | 4 | 4 | 8 | [8 empty] | PP-462 |  | Sprint 5
1.12.3 | Implement extract_filters method | extracting filters from list of actions | 1.12.1, 1.12.2 | 2 | 2 | 4 | [8 empty] | PP-463 |  | Sprint 5
1.12.4 | Integrate expand / collapse functionality with the caseSummaryCollection query | see design | 1.1, 1.12.1 - 1.12.3 | 22 | 24 | 32 | [8 empty] | PP-464 |  | Sprint 5
1.13 | find_child_nodes | see design | [12 empty] | PP-465
1.13.1 | Implement get_child_node_columns method |  |  | 3.5 | 4 | 4 |  | Tomek We | March 17, 2021, 6:53 PM | March 18, 2021, 12:32 PM | 4 | 128 | 28 |  | PP-454 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/48 | Sprint 2 | Added to sprint in Sprint 2
1.13.2 | Implement find_child_nodes method in PandasAnalyticalService, for now without sorting | implement first version without sorting or handing other options (dry_run, pagination, match_prefix) | 1.13.1, 1.9.1 | 32 | 24 | 32 |  | Tomek We | March 18, 2021, 1:52 PM | March 18, 2021, 8:25 PM | 6.5 | 151 | 5 |  | PP-455 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/52 | Sprint 2 | Added to sprint in Sprint 2
1.13.3 | Handle sorting by case_count in find_child_nodes, add case_count property in Node class | see design, also set case_count property in returned nodes, for now we can allow only sorting by 1 sort criteria | 1.13.2 | 8 | 4 | 12 |  | Tomek We | March 18, 2021, 7:36 PM | March 19, 2021, 12:10 PM | 5 | 95 | 3 |  | PP-456 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/53 | Sprint 2 | Added to sprint in Sprint 2
1.13.4 | Handle sorting by options 2 - 7 in find_child_nodes | also handle sorting by multiple columns | 1.13.3 | 32 | 20 | 32 |  | Tomek We | March 22, 2021, 10:20 AM | March 23, 2021, 11:17 AM | 8 | 191 | 21 |  | PP-466 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/64 | Sprint 3
1.13.5 | Handle sorting by rating in find_child_nodes |  | 1.13.4 | 6 | 8 | 10 |  | Tomek We | [6 empty] | PP-467 |  | Sprint 3
1.13.6 | Handle sorting by name in find_child_nodes |  | 1.13.4 | 24 | 24 | 32 |  | Tomek We | March 23, 2021, 11:20 AM | March 23, 2021, 12:22AM | 7 | 74 | 27 |  | PP-468 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/65, https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/69 | Sprint 3 | Planned in Sprint 4
1.13.7 | Handle pagination argument | Limit results to a specific page only | 1.13.2 | 3.5 | 4 | 4 |  | Tomek We | [6 empty] | PP-469 |  | Sprint 3
1.13.8 | Handle match_prefix argument |  | 1.13.6 | 8 | 4 | 8 |  | Tomek We | [6 empty] | PP-470 |  | Sprint 3 | Planned in Sprint 4
1.13.9 | Handle dry_run option | return int when dry_run = True | 1.13.2 | 8 | 4 | 8 |  | Tomek We | [6 empty] | PP-471 |  | Sprint 3
1.14 | Sorting and Pagination of Nodes | see design | [12 empty] | PP-472
1.14.1 | Implement extract_sort_criteria method |  | 1.13.2 | 3 | 4 | 4 |  | Michał | March 25, 2021, 4:42 PM | March 26, 2021, 1:00 PM | 5 | 67 | 2 |  | PP-473 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/82 | Sprint 3 | Added to sprint in Sprint 3
1.14.2 | Implement pack_nodes method, add is_packed() and unpack() methods to Node class | see design, make sure to check performance for ~40k nodes | 1.1.7 | 20 | 24 | 24 |  | Bartek | March 25, 2021, 12:45 PM | March 26, 2021, 9:20 AM | 8 | 90 | 12 |  | PP-474 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/79 | Sprint 3 | Added to sprint in Sprint 3
1.14.3 | Implement extract_pagination method |  |  | 2 | 4 | 4 |  | Michał | March 26, 2021, 1:07 PM | March 26, 2021, 3:16 PM | 2 | 29 | 3 |  | PP-475 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/83 | Sprint 3 | Added to sprint in Sprint 3
1.14.4 | Implement get_graph_orientation method |  |  | 3.5 | 4 | 4 |  | Michał | [6 empty] | PP-476 |  | Sprint 3 | Added to sprint in Sprint 3
1.14.5 | Implement extract_graph_pagination method |  | 1.14.3, 1.14.4 | 2 | 4 | 4 |  | Michał | March 29, 2021, 10:14 AM | [5 empty] | PP-477 |  | Sprint 3 | Added to sprint in Sprint 3
1.14.6 | Update group_nodes method in PandasAnalyticalService to allow a single packed node on either side (and up to 2 pack nodes in total) | see design | 1.14.2 | 24 | 32 | 32 |  | Maciej | March 26, 2021, 9:22 AM | [5 empty] | PP-478 |  | Sprint 4
1.14.11 | Handle single packed node on each side in calculate_benchmark method | see also 1.14.6 | 1.11.7, 1.14.6 | 12 | 20 | 26 |  | Bartek | [6 empty] | PP-504 |  | Sprint 4
1.14.7 | Implement decompose_packed_nodes decorator | Apply decorator to all group_nodes implementations (see design), make sure to run queries in parallel |  | 8 | 8 | 8 |  | Bartek | [6 empty] | PP-479 |  | Sprint 3 | Added to sprint in Sprint 3
1.14.8 | Refactor make_abstract_graph_query to use find_child_nodes method | pass sorting criteria, see updated design, make sure to run lhs/rhs queries in parallel | 1.1.10, 1.13.3, 1.14.1 | 20 | 24 | 24 |  | Michał | [6 empty] | PP-480 |  | Sprint 4
1.14.9 | Refactor AbstractGraphModel class and make_abstract_graph_model method to reflect design | make sure to pack nodes according to rules, see design | 1.14.1 - 1.14.5 | 12 | 16 | 16 |  | Michał | March 29, 2021, 2:21 PM | [5 empty] | PP-481 |  | Sprint 3 | Added to sprint in Sprint 3
1.14.10 | Update caseSummaryCollection endpoint to handle sorting and pagination | make sure sorting and pagination rules are processed, add unit tests for this functionality | 1.14.1 - 1.14.9 | 8 | 8 | 8 | [8 empty] | PP-482 |  | Sprint 4
1.15 | allDatasets endpoint | see design | [12 empty] | PP-483
1.15.1 | define the DatasetDetails class |  |  | 2 | 1 | 4 |  | Tomek We | March 24, 2021, 5:51 PM | March 24, 2021, 6:08 PM | 1 |  |  |  | PP-505 |  | Sprint 3 | Added to sprint in Sprint 3
1.15.2 | Implement get_all_datasets method in the DatasetService class |  | DM | 12 | 12 | 16 | [8 empty] | PP-484 |  | Sprint 5
1.15.3 | Implement format_all_datasets_response method |  | 1.15.1 | 1.5 | 1 | 1 |  | Tomek We | [6 empty] | PP-506 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/80 | Sprint 3 | Added to sprint in Sprint 3
1.15.4 | Implement DummyDatasetService | This is to run P2 application without the actual DM implementation yet, do not implement any unit tests for this class |  | 3.5 | 8 | 8 |  | Tomek We | March 25, 2021, 11:22 AM | March 25, 2021, 3:22 PM | 4 | 141 | 5 |  | PP-518 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/76 | Sprint 3 | Added to sprint in Sprint 3
1.15.5 | Implement allDatasets endpoint | use DummyDatasetService for now | 1.15.3, 1.15.4 | 3 | 4 | 4 |  | Tomek We | March 26, 2021, 11:43 AM | March 26, 2021, 4:41 PM | 4 |  |  |  | PP-507 |  | Sprint 3 | Added to sprint in Sprint 3
1.16 | getLDSDatasetsIDs endpoint | see design | [12 empty] | PP-508
1.16.1 | Implement getLDSDatasetsIDs endpoint | use mock DatasetService for now |  | 3 | 4 | 4 |  | Tomek We | [6 empty] | PP-509 |  | Sprint 3 | Added to sprint in Sprint 3
1.17 | dataset endpoint | see design | [12 empty] | PP-510
1.17.1 | Implement get_datasets method in DatasetService | 1.15.2 | DM | 3.5 | 4 | 4 | [8 empty] | PP-511 |  | Sprint 5
1.17.2 | Implement get_pipeline_statistics method in DatasetService | connect to the pipeline database | O2Grouper | 24 | 24 | 24 | [8 empty] | PP-512
1.17.3 | Implement dataset endpoint |  | 1.17.1, 1.17.2 | 4 | 8 | 8 | [8 empty] | PP-513
1.18 | caseStatistics endpoint | see design | [12 empty] | PP-514
1.18.1 | Implement get_case_statistics in PandasAnalyticalService | Handle sorting and limitation of results | 1.18 | 24 |  | 32 | [8 empty] | PP-519 |  | Sprint 4
1.18.2 | Implement get_serviceline_benchmarks in PandasAnalyticalService | similar to 1.19.2 | 1.18 | 12 |  | 16 | [8 empty] | PP-520 |  | Sprint 4
1.18.3 | Implement join_serviceline_benchmarks | similar to 1.19.3 |  | 3 |  | 4 | [8 empty] | PP-521 |  | Sprint 4
1.18.4 | Implement format_case_statistics | Prepare synthetic data frames for unit tests (without and with benchmark values) |  | 5 |  | 8 | [8 empty] | PP-522 |  | Sprint 4
1.18.5 | Implement caseStatistics endpoint | see design, make sure to run queries in parallel | 1.18.1 - 1.18.4, 1.21 | 17 |  | 20 | [8 empty] | PP-523 |  | Sprint 4
1.19 | caseSummaryCollectionMapView endpoint | see design | [12 empty] | PP-515
1.19.1 | Implement get_map_view_entity_statistics in PandasAnalyticalService |  | 1.1.8 | 16 |  | 20 | [8 empty] | PP-524 |  | Sprint 4
1.19.2 | Implement get_careunit_benchmarks in PandasAnalyticalService |  | 1.1.8 | 14 |  | 20 | [8 empty] | PP-525 |  | Sprint 4
1.19.3 | Implement join_careunit_benchmarks | Prepare sythetic data frames for the unit test |  | 3 |  | 4 | [8 empty] | PP-526 |  | Sprint 4
1.19.4 | Implement format_entity_statistics | Prepare synthetic data frames for unit tests (without and with benchmark values) |  | 4 |  | 4 | [8 empty] | PP-527 |  | Sprint 4
1.19.5 | Implement caseSummaryCollectionMapView endpoint | see design, make sure to run queries in parallel | 1.19.1 - 1.19.4 | 16 |  | 12 | [8 empty] | PP-528 |  | Sprint 4
1.20 | Error Handling | see design | [12 empty] | PP-529
1.20.1 | Define ApplicationError base class and app_error_class decorator | just copy from the design and add unit tests |  | 3 |  | 2 | [8 empty] | PP-530 |  | Sprint 5
1.20.2 | Review applicatoin's code, find all raise statements and throw proper errors | Declare proper exception classes, define error variables, use DatasetNotFound as a model example, place all errors in the errors.py module | 1.1 - 1.19 | 28 |  | 36 | [8 empty] | PP-531 |  | Sprint 5
1.20.3 | Add list of error codes and descriptions to technical design | This task is development driven |  | 6 |  | 4 | [8 empty] | PP-532 |  | Sprint 5
1.21 | Backend Configuration | see design | [12 empty] | PP-533
1.21.1 | Implement AppConfig | Define ConfigVariables and defaults, validate configuration on first access to AppConfig |  | 4 | [10 empty] | PP-534
1.22 | Data Suppression (LDS-11 rule) | [13 empty] | PP-537
1.23 | User Dataset Upload | [13 empty] | PP-538
1.24 | Snowflake Integration | [13 empty] | PP-539
1.25 | ServiceLine API | Move code and data from existing P2v2 implementation to P2v3 | [12 empty] | PP-540
1.25.1 | Implement searchServiceLine endpoint | [13 empty] | PP-541
1.25.2 | Implement searchAllDiagnose endpoint | [13 empty] | PP-580
1.25.3 | Implement filteredServiceLines endpoint | [13 empty] | PP-581
1.25.4 | Implement filteredClinicalEpisodes endpoint | [13 empty] | PP-582
1.25.5 | Implement filteredDRGs endpoint | [13 empty] | PP-583
1.26 | Location API | Move code and data from existing P2v2 implementation to P2v3 | [12 empty] | PP-542
1.26.1 | Move allUSStates endpoint | Copy data to postgres, move django model from P2v2 |  | 2.5 |  | 4 |  | Manoj | [6 empty] | PP-543 |  | Sprint 4
1.26.2 | Move usState endpoint | Copy data to postgres, move django model from P2v2 |  | 2.5 |  | 4 |  | Manoj | [6 empty] | PP-584 |  | Sprint 4
1.26.3 | Move searchUsLocation endpoint | Copy data to postgres, move django model from P2v2 |  | 6 |  | 4 |  | Manoj | [6 empty] | PP-585 |  | Sprint 4
1.26.4 | Move usStateGeoAll endpoint | Copy .json file, make the path configurable | 1.21.1 | 4 |  | 4 |  | Manoj | [6 empty] | PP-586 |  | Sprint 4
1.26.5 | Move usCountyGeoForState endpoint | Copy .json file, make the path configurable | 1.21.1 | 4 |  | 4 |  | Manoj | [6 empty] | PP-587 |  | Sprint 4
1.26.6 | Move usStateGeoSearch | Copy data to postgres, move django model from P2v2 |  | 3.5 |  | 4 |  | Manoj | [6 empty] | PP-588 |  | Sprint 4
1.26.7 | Move usCountyGeoAll endpoint | Copy data to postgres, move django model from P2v2 |  | 2 |  | 4 |  | Manoj | [6 empty] | PP-589 |  | Sprint 4
1.26.8 | Move locationByRadialLocation endpoint | Copy .json file, make the path configurable | 1.21.1 | 8 |  | 4 |  | Manoj | [6 empty] | PP-590 |  | Sprint 4
2 | Testing caseSummaryCollection query | [13 empty] | PP-266
2.1 | Test caseSummaryCollection - market share graph | Test filters and responsed for caseSummaryCollection with benchmark option set to false | [12 empty] | PP-267 |  |  | Moved to QA team tasks list summary: link
2.2 | Test caseSummaryCollection - benchmark graph | Test filters and responses for caseSummaryCollection with benchmark set to true | [12 empty] | PP-268
2.3 | Test caseSummaryCollection - 2D graph | Test filters and responses for caseSummaryCollection with 2D graph benchmark settings | [12 empty] | PP-269
3 | Report View Management | [13 empty] | PP-356 |  |  | Design not detailed enough to estimate by reviewer/PM
3.0 | Environment Setup | Setu development environment including DJangoand PGSql | [5 empty] | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 20 | 147 | 0 |  | PP-357 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.1 | Define schema.py | Class that defines graphQL queries, endpoints and object structure. Python file will have definition of following ojects. Developer can refer existing P2BE code at p2backend\ReportView\schema.py file. | [5 empty] | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 |  | PP-358 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.2 | Define reportview_api.py | Class that has actual implementation for all end points. Developer can refer p2backend\BigSense\Reportview\reportview_api.py file from existing P2BE code | [5 empty] | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 |  | PP-359 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.3 | Define model.py | Class that defines the Entity Relation of report view as per OLTP database(Postgres) | [5 empty] | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 |  | PP-360 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.4 | Implementing Endpoints | This implementation will have a resolve method in schema.py and corresponding method in reportview_api.py file | [5 empty] | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 |  | PP-361 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.4.1 | ReportView | [6 empty] | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 |  | PP-362 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.4.2 | ReportViews | [6 empty] | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 |  | PP-363 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.4.3 | SearchReportViews | [6 empty] | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 |  | PP-364 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.4.4 | CreateReportView | [6 empty] | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 |  | PP-365 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.4.5 | UpdateReportView | [6 empty] | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 |  | PP-366 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.4.6 | DeleteReportView | [6 empty] | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 |  | PP-367 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2
3.5 | [BE] Extract user details from Auth0 token |  |  | 8 |  |  |  | Manoj | [6 empty] | PP-516 |  | Sprint 3 | Added to sprint in Sprint 3
3.6 | [BE] Modify Report view endpoints to use user details from Auth0 token |  |  | 12 |  |  |  | Manoj | [6 empty] | PP-517 |  | Sprint 3 | Added to sprint in Sprint 3
4 | Integrate analytical endpoints with django | Integrate endpoints with django. To be seen under https://p2v3.ownedoutcomes.com/backend/graphql/ url. List:caseLocationDetails endpoint caseLobCounts endpoint getAvailableYears endpoint getDateTimeStatsForListOfYears endpoint filteredCareUnitTypes endpoint getDatasetsInitialFilters getDateTimesForYear endpoint allDatasets endpoint getLDSDatasetsIDs endpoint |  | 8 |  | 8 |  | Tomek We | [6 empty] | PP-567 |  | Sprint 3 | Added to sprint in Sprint 3

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Problem with missing DRGs | Problem found during writing unit test. The issue was with type of join of DRG table in already finished implementation. | Maciej, Michał, Ola | March 12, 2021, 8:00 AM | March 15, 2021, 2:10 PM | 20 | 28 | 30 |  | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/28 | Issue delayed finish of group nodes task (1.1.12)