## Description
Design document: | Dataset Manager Technical Design
Jira project: | P2 next gen (PP)
Jira label:
Number of tasks:
Number of reported bugs:
Estimated development time [h] (designer):
Estimated development time [h] (reviewer):
Estimated development time [h] (pm):
Total time spent [h]:

## Tasks
WBS | Name | Description | Depends on | Estimated work time [h] |  |  | Assignee | Actual work time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment
|  |  |  | Designer | Reviewer | PM |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Make a cleanup in tests library | [11 empty] | PP-246
1.1 | ‘2D graph’ - finish and update the unfinished tests. |  |  | 20 | 20 | 16 | Swatantra | March 24, 2021, 1:00 PM |  |  |  |  | PP-301 |  | Sprint 3
1.2 | Changes in columns |  |  | 1 | 2 | 4 | [6 empty] | PP-303 |  | Sprint 3
1.3 | Update graph combination filter tests to use all existing types of filters | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 | Monika | March 19, 2021, 8:18 AM |  |  |  |  | PP-304 |  | Sprint 3
1.4 | Update map view filter combination tests to use all existing filter types | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 | Monika | March 26, 2021, 8:26 AM |  |  |  |  | PP-305 |  | Sprint 3
1.5 | Update 2D graph view filter combination tests to use all existing filter types | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 | Paulina | March 23, 2021, 8:51 AM |  |  |  |  | PP-306 |  | Sprint 3
1.6 | Review and prune tests from Benchmark Average on Graph tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | Piotr | [5 empty] | PP-493 |  | Sprint 3
1.7 | Review and prune tests from Benchmark Perecentile on Graph tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | [6 empty] | PP-494 |  | Sprint 3
1.8 | Review and prune tests from Benchmark Average&Percentile_Map tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | [6 empty] | PP-495 |  | Sprint 3
1.9 | Review and prune tests from Dataset Management tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | Paulina | March 18, 2021, 3:56 PM | March 26, 2021, 8:26 AM |  |  |  | PP-457 |  | Sprint 3
1.10 | Review and prune tests from Labels tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 16 | 16 | 20 | Kamil | March 18, 2021, 4:16 PM |  |  |  |  | PP-459 |  | Sprint 3
1.11 | Prepare statistics of automated testcases for old suite | [11 empty] | PP-498 |  | Sprint 3 | Added during sprint
1.11.1 | Statistics for 1st part of the testcases |  |  |  |  | 8 | Kamil | [5 empty] | PP-499 |  | Sprint 3 | Added during sprint
1.11.2 | Statistics for 2nd part of the testcases |  |  |  |  | 8 | Piotr | [5 empty] | PP-500 |  | Sprint 3 | Added during sprint
1.12 | Add categories types to missing testcases after initial cleanup |  |  |  |  | 16 | Paulina | [5 empty] | PP-501 |  | Sprint 3 | Added during sprint
2 | Integration tests of p2backend | [11 empty] | PP-545
2.1 | Testing caseSummaryCollection query | [11 empty] | PP-266
2.1.1 | Test caseSummaryCollection - market share graph | - Check response with multiple normal/LDS datasets - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: 1.1 | 24 | 24 | 16 | [6 empty] | PP-267 |  | Sprint 3
2.1.2 | Test caseSummaryCollection - benchmark graph | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: 1.1 | 24 | 24 | 16 | [6 empty] | PP-268
2.1.3 | Test caseSummaryCollection - 2D graph | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings and combinations - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: 1.1 | 24 | 24 | 16 | [6 empty] | PP-269
2.2 | Test caseLobCounts query | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests)" | BE: 1.3 | 6 | 8 | 8 | [6 empty] | PP-546 |  | Sprint 3
2.3 | Test getAvailableYears query | see design - Check results for multiple normal/LDS datasets - Check pagination | BE: 1.4 | 4 | 4 | 4 | [6 empty] | PP-547 |  | Sprint 3
2.4 | Test getDateTimeStatsForListOfYears query | see design - Check results for multiple normal/LDS datasets - Check pagination | BE: 1.5 | 6 | 8 | 8 | [6 empty] | PP-548 |  | Sprint 3
2.5 | Test filteredCareUnitTypes query | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests) | BE: 1.6 | 8 | 8 | 8 | [6 empty] | PP-549 |  | Sprint 3
2.6 | Test getDatasetsInitialFilters query | see design - Check normal/LDS datasets in combinations - Check boolean input fields | BE: 1.7 | 10 | 12 | 16 | [6 empty] | PP-550 |  | Sprint 3
2.7 | Report view | [11 empty] | PP-551
2.7.1 | Test ReportView query | design - Check if returne fields are correct and the if the response structure is as expected | BE: 3 | 12 | 12 | 16 | [6 empty] | PP-552 |  | Sprint 3
2.7.2 | Test ReportViews query | design - Check if the number of views returned is correct - Check if different user's id can be provided | BE: 3 | 10 | 12 | 16 | [6 empty] | PP-553 |  | Sprint 3
2.7.3 | Test SearchReportViews query | design - Search Report Views based on their names - Search Report Views based on the datasets used by the views | BE: 3 | 10 | 12 | 16 | [6 empty] | PP-554 |  | Sprint 3
2.7.4 | Test CreateReportView query | design - Check all possible input parameters with the special focus on: reportViewType, datasets and filters - Check if a view can be created for another user | BE: 3 | 16 | 16 | 16 | [6 empty] | PP-555 |  | Sprint 3
2.7.5 | Test UpdateReportView query | design - Check all possible input parameters with the special focus on: reportViewType, datasets and filters - Cases when an updated view doesn't exist or is deleted - Check if another user's view can e updated | BE: 3 | 16 | 16 | 16 | [6 empty] | PP-556 |  | Sprint 3
2.7.6 | Test DeleteReportView mutation | design - Delete existing ReportView and check if it was truly deleted (no appearing in ReportView and ReportViews queries) - Try deleting a ReportView that doesn't exist and/or the one that was already deleted | BE: 3 | 4 | 4 | 8 | [6 empty] | PP-557 |  | Sprint 3
2.8 | Getting datasets list | [11 empty] | PP-558
2.8.1 | allDatasets endpoint | see design - Check if datasets are returned correctly (the amount and names) - Check the correctness of upload status (upload can be finished, failed or in progress) - if possible now - Check if upload start and finish time are correct - if possible for now | BE: 1.17 | 14 | [8 empty] | PP-559
2.8.2 | getLDSDatasetsIDs endpoint | see design Check the query when there're multiple LDS and normal datasets uploaded | BE: 1.16 | 4 | [8 empty] | PP-560
2.9 | caseLocationDetails endpoint | - | [10 empty] | PP-561
2.10 | searchCareUnitAndDetail endpoint | see design - Check data for different types of datasets - Check data for every type of entity |  | 14 | [8 empty] | PP-562
2.11 | Research and implementation of raport generator | [11 empty] | PP-563
2.11.1 | Research |  |  | 8 | [8 empty] | PP-564 |  | Sprint 3
2.11.2 | implementation of raport generator part 1 |  |  | 8 | [8 empty] | PP-565 |  | Sprint 3
2.11.3 | implementation of raport generator part 2 |  |  | 8 | [8 empty] | PP-566 |  | Sprint 3

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions