## Summary
Design document: | Dataset Manager Technical Design
Jira project: | P2 next gen (PP)
Jira label: | Tests
Number of tasks: | 349
Number of reported bugs: | 0
Total planned development worktime [h]: | 2081
Planned development worktime of finished tasks [h]: | 297
Current worktime spent [h]: | 256.17
Planned time to finish project [h]: | 1784
Planned availability [h]: | 2527.5
Project completeness based on planned worktime [%]: | 14.272
Current worktime vs planned worktime [%]: | 86.2525 | > 100% - delay; < 100% - ahead

## Tasks
WBS | Name | Description | Depends on | Estimated work time [h] |  |  |  | Assignee | Actual work time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment | Category
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Make a cleanup in tests library | [7 empty] | 2021-03-18 15:56 | 2021-04-01 14:59 |  |  |  | PP-246 |  |  |  | Dataset upload and management | 0
1.1 | ‘2D graph’ - finish and update the unfinished tests. |  |  | 20 | 20 | 16 |  | Swatantra | March 24, 2021, 1:00 PM | April 1, 2021, 2:59 PM |  |  |  | PP-301 |  | Sprint 3 | Abandoned | Visualization Generation | 0
1.2 | Changes in columns |  |  | 1 | 2 | 4 | [7 empty] | PP-303 |  | Sprint 3 | Abandoned |  | 0
1.3 | Update graph combination filter tests to use all existing types of filters | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 |  | Monika | March 19, 2021, 8:18 AM |  |  |  |  | PP-304 |  | Sprint 3 | Abandoned | Visualization Generation | 0
1.4 | Update map view filter combination tests to use all existing filter types | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 |  | Monika | March 26, 2021, 8:26 AM |  |  |  |  | PP-305 |  | Sprint 3 | Abandoned | Visualization Generation | 0
1.5 | Update 2D graph view filter combination tests to use all existing filter types | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 |  | Paulina | March 23, 2021, 8:51 AM | March 26, 2021, 8:51 AM |  |  |  | PP-306 |  | Sprint 3 | Abandoned | Visualization Generation | 0
1.6 | Review and prune tests from Benchmark Average on Graph tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 |  | Piotr | [5 empty] | PP-493 |  | Sprint 3 | Abandoned | Benchmark settings customization & Benchmark Calculation | 0
1.7 | Review and prune tests from Benchmark Perecentile on Graph tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | [7 empty] | PP-494 |  | Sprint 3 | Abandoned | Benchmark settings customization & Benchmark Calculation | 0
1.8 | Review and prune tests from Benchmark Average&Percentile_Map tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | [7 empty] | PP-495 |  | Sprint 3 | Abandoned | Benchmark settings customization & Benchmark Calculation | 0
1.9 | Review and prune tests from Dataset Management tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 |  | Paulina | March 18, 2021, 3:56 PM | March 26, 2021, 8:26 AM |  |  |  | PP-457 |  | Sprint 3 | Abandoned | Dataset upload and management | 0
1.10 | Review and prune tests from Labels tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 16 | 16 | 20 |  | Kamil | March 18, 2021, 4:16 PM |  |  |  |  | PP-459 |  | Sprint 3 | Abandoned | Label settings | 0
1.11 | Prepare statistics of automated testcases for old suite | [7 empty] | 2021-03-24 08:16 | 2021-03-24 17:16 |  |  |  | PP-498 |  | Sprint 3 | Added during sprint |  | 0
1.11.1 | Statistics for 1st part of the testcases |  |  |  |  | 8 |  | Kamil | March 24, 2021, 8:16 AM | March 24, 2021, 5:16 PM |  |  |  | PP-499 |  | Sprint 3 | Added during sprint |  | 0
1.11.2 | Statistics for 2nd part of the testcases |  |  |  |  | 8 |  | Piotr | March 24, 2021, 8:16 AM | March 24, 2021, 5:16 PM |  |  |  | PP-500 |  | Sprint 3 | Added during sprint |  | 0
1.12 | Add categories types to missing testcases after initial cleanup |  |  |  |  | 8 |  | Paulina | March 24, 2021, 10:04 AM | March 24, 2021, 3:08 PM |  |  |  | PP-501 |  | Sprint 3 | Added during sprint |  | 0
2 | Integration tests of p2backend | [7 empty] | 2021-03-29 14:29 | 2021-05-21 |  |  |  | PP-1048 |  |  |  |  | 0
2.1 | Testing caseSummaryCollection query | [7 empty] | 2021-04-09 13:14 | 2021-05-21 |  |  |  | PP-266 |  |  |  | Visualization Generation | 0
2.1.1 | Test caseSummaryCollection - market share graph | - Check response with multiple normal/LDS datasets - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: 1.1 | 24 | 24 | 16 | 24 | Paulina | April 9, 2021, 1:14 PM |  |  |  |  | PP-267 |  | Sprint 4 | Moved from Sprint 3, postponed due to reported bugs | Visualization Generation | 0
2.1.2 | Test caseSummaryCollection - benchmark graph | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: | 24 | 24 | 16 | 24 |  | 2021-05-04 | 2021-05-07 |  |  |  | PP-268 |  | Sprint 6 |  | Visualization Generation | 0
2.1.3 | Test caseSummaryCollection - 2D graph | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings and combinations - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: | 24 | 24 | 16 | 24 |  | 2021-05-18 | 2021-05-21 |  |  |  | PP-269 |  | Sprint 7 |  | Visualization Generation | 0
2.2 | Test caseLobCounts query | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests)" | BE: 1.3 | 6 | 8 | 8 | 8 | Swatantra | April 5, 2021, 2:03 PM | April 7, 2021, 8:49 AM | 15 | 51 | 2 | PP-546 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/5 | Sprint 4 | Moved from Sprint 3 | Filters - LOB filters | 8
2.3 | Test getAvailableYears query | see design - Check results for multiple normal/LDS datasets - Check pagination | BE: 1.4 | 4 | 4 | 4 | 4 | Swatantra | April 1, 2021, 4:32 PM | April 5, 2021, 2:01 PM | 19 | 37 | 0 | PP-547 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/4 | Sprint 4 | Moved from Sprint 3 | Visualization Generation | 4
2.4 | Test getDateTimeStatsForListOfYears query | see design - Check results for multiple normal/LDS datasets - Check pagination | BE: 1.5 | 6 | 8 | 8 | 8 | Swatantra | April 12, 2021, 8:43 AM | April 13, 2021, 1:19 AM | 15 | 47 | 0 | PP-548 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/9 | Sprint 4 | Moved from Sprint 3 | Visualization Generation | 8
2.5 | Test filteredCareUnitTypes query | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests) | BE: 1.6 | 8 | 8 | 8 | 8 | Paulina | April 6, 2021, 1:00 PM | April 8, 2021, 12:43 PM | 8 | 325 | 0 | PP-549 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/6 | Sprint 4 | Moved from Sprint 3 | Visualization Generation | 8
2.6 | Test getDatasetsInitialFilters query | see design - Check normal/LDS datasets in combinations - Check boolean input fields | BE: 1.7 | 10 | 12 | 16 | 16 | Paulina | April 7, 2021, 2:29 PM | April 8, 2021, 1:03 PM | 5 | 102 | 2 | PP-550 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/7 | Sprint 4 | Moved from Sprint 3 | Visualization Generation | 16
2.7 | Report view | [7 empty] | 2021-03-30 08:36 | 2021-04-15 16:06 |  |  |  | PP-551 |  |  |  | View Dashboard | 0
2.7.1 | Test ReportView query | design - Check if returne fields are correct and the if the response structure is as expected | BE: 3 | 12 | 12 | 16 | 16 | Paulina | April 1, 2021, 8:18 AM | April 6, 2021, 1:02 PM | 11 | 527 | 1 | PP-552 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/2 | Sprint 4 | Moved from Sprint 3 | View Dashboard | 16
2.7.2 | Test ReportViews query | design - Check if the number of views returned is correct - Check if different user's id can be provided | BE: 3 | 10 | 12 | 16 | 16 |  | April 15, 2021, 11:24 AM | April 15, 2021, 4:06 PM | 9.5 | 527 | 1 | PP-553 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/2 | Sprint 4 | Moved from Sprint 3 | View Dashboard | 16
2.7.3 | Test SearchReportViews query | design - Search Report Views based on their names - Search Report Views based on the datasets used by the views | BE: 3 | 10 | 12 | 16 | 16 | Paulina | April 13, 2021, 2:29 PM | April 14, 2021, 12:40 PM |  | 58 | 2 | PP-554 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/15 | Sprint 4 | Moved from Sprint 3 | View Dashboard | 0
2.7.4 | Test CreateReportView query | design - Check all possible input parameters with the special focus on: reportViewType, datasets and filters - Check if a view can be created for another user | BE: 3 | 16 | 16 | 16 | 16 | Paulina | March 30, 2021, 8:36 AM | April 1, 2021, 8:17 AM | 18 | 527 | 1 | PP-555 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/2 | Sprint 4 | Moved from Sprint 3 | View Dashboard | 16
2.7.5 | Test UpdateReportView query | design - Check all possible input parameters with the special focus on: reportViewType, datasets and filters - Cases when an updated view doesn't exist or is deleted - Check if another user's view can e updated | BE: 3 | 16 | 16 | 16 | 16 | Paulina | April 2, 2021, 3:36 PM | April 7, 2021, 1:39 PM | 9.5 | 527 | 1 | PP-556 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/2 | Sprint 4 | Moved from Sprint 3 | View Dashboard | 16
2.7.6 | Test DeleteReportView mutation | design - Delete existing ReportView and check if it was truly deleted (no appearing in ReportView and ReportViews queries) - Try deleting a ReportView that doesn't exist and/or the one that was already deleted | BE: 3 | 4 | 4 | 8 | 8 |  | April 15, 2021, 3:41 PM | April 15, 2021, 3:43 PM | 2.5 | 57 | 0 | PP-557 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/26 | Sprint 4 | Moved from Sprint 3 | View Dashboard | 8
2.8 | Getting datasets list | [7 empty] | 2021-04-13 14:12 | 2021-05-05 06:00 |  |  |  | PP-558 |  |  |  |  | 0
2.8.1 | allDatasets endpoint | see design - Check if datasets are returned correctly (the amount and names) | BE: 1.17 | 14 |  | 12 | 4 | Piotr | April 13, 2021, 2:22 PM | April 13, 2021, 3:31 PM | 2 | 67 | 0 | PP-559 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/12 | Sprint 4 | Moved from Sprint 3, task splitted into two due to availability of endpoint from BE (2.8.3) | Dataset upload and management | 4
2.8.2 | getLDSDatasetsIDs endpoint | see design Check the query when there're multiple LDS and normal datasets uploaded | BE: 1.16 | 4 |  | 4 | 4 | Swatantra | April 13, 2021, 2:12 PM | April 16, 2021, 8:45 AM | 4.5 |  |  | PP-560 |  | Sprint 4 | Moved from Sprint 3 | Dataset upload and management | 4
2.8.3 | allDatasets endpoint - upload status | - Check the correctness of upload status (upload can be finished, failed or in progress) - if possible now - Check if upload start and finish time are correct - if possible for now | BE: 1.17 |  |  |  | 10 |  | 2021-05-04 | 2021-05-05 06:00 |  |  |  | PP-1006 |  | Sprint 6 |  | Dataset upload and management
2.9 | caseLocationDetails endpoint | see design - Check results for different dataset type - Check results for CBSA, FIPS, state, no option chosen |  | 10 |  | 8 | 10 | Paulina | April 8, 2021, 3:02 PM | April 9, 2021, 12:19 PM | 7.5 | 228 | 7 | PP-561 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/8 | Sprint 4 | Added to sprint in Sprint 4 | Filters - Geography (Location) filters | 10
2.10 | searchCareUnitAndDetail endpoint | see design - Check data for different types of datasets - Check data for every type of entity |  | 14 |  | 16 | 16 |  | 2021-05-04 | 2021-05-06 |  |  |  | PP-562 |  | Sprint 6 |  | Visualization Generation | 0
2.11 | filteredCareUnits endpoint | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests) |  | 10 |  | 10 | 10 | Swatantra | 2021-04-20 | 2021-04-21 06:00 |  |  |  | PP-626 |  | Sprint 5 |  | Visualization Generation | 0
2.12 | caseSummaryCollectionMapView endpoint | see design | [6 empty] | 2021-05-18 | 2021-05-20 12:00 |  |  |  | PP-627 |  | Sprint 7 |  | Visualization Generation | 0
2.12.1 | caseSummaryCollectionMapView - marketshare map | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings |  | 16 |  | 20 | 20 |  | 2021-05-18 | 2021-05-20 12:00 |  |  |  | PP-628 |  | Sprint 7 |  | Visualization Generation | 0
2.12.2 | caseSummaryCollectionMapView - benchmark map | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings - Check all filter types combinations |  | 16 |  | 20 | 20 |  | 2021-05-18 | 2021-05-20 12:00 |  |  |  | PP-629 |  | Sprint 7 |  | Visualization Generation | 0
2.13 | Node Expand and Collapse | see design |  |  |  |  | 32 |  | 2021-05-04 | 2021-05-06 |  |  |  | PP-630 |  | Sprint 6 |  | Visualization Navigation | 0
2.13.1 | Node Expand and Collapse - marketshare graph | see design Check expanding/collapsing all AC/PAC types on all layers |  | 12 |  | 16 | 16 |  | 2021-05-04 | 2021-05-06 |  |  |  | PP-631 |  | Sprint 6 |  | Visualization Navigation | 0
2.13.2 | Node Expand and Collapse - benchmark graph | see design Check expanding/collapsing all AC/PAC types and all Service Lines on all layers |  | 12 |  | 16 | 16 |  | 2021-05-04 | 2021-05-06 |  |  |  | PP-632 |  | Sprint 6 |  | Visualization Navigation | 0
2.14 | Integration tests of p2backend report generator | [7 empty] | 2021-03-29 14:29 | 2021-03-31 12:24 |  |  |  | PP-563 |  |  |  |  | 0
2.14.1 | Research - pytest tools to generate tests report | Research about available tools to generate report for p2 integration tests. The following libraries were tested: pytest-csv pytest-excel pytest-html |  | 8 |  | 8 | 8 | Piotr | March 29, 2021, 2:29 PM | March 29, 2021, 4:30 PM | 6 |  |  | PP-564 | - | Sprint 3 |  |  | 8
2.14.2 | Implementation of tests report generator - structure of worksheets |  |  | 8 |  | 8 | 8 | Piotr | March 29, 2021, 4:31 PM | March 30, 2021, 11:40 AM | 8.5 |  |  | PP-565 | - | Sprint 3 |  |  | 8
2.14.3 | Implementation of tests report generator - summarize tabs |  |  | 8 |  | 8 | 8 | Piotr | March 30, 2021, 11:41 AM | March 31, 2021, 12:24 PM | 8.5 |  |  | PP-566 | - | Sprint 3 |  |  | 8
2.15 | ServiceLine API | [7 empty] | 2021-04-15 11:23 | 2021-05-05 |  |  |  | PP-633 |  |  |  | Filters - Service Line filters | 0
2.15.1 | test searchServiceLine endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-634 |  | Sprint 6 |  | Filters - Service Line filters | 0
2.15.2 | test searchAllDiagnose endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 |  | 2021-05-04 | 2021-05-05 |  |  |  | PP-635 |  | Sprint 6 |  | Filters - Service Line filters | 0
2.15.3 | test filteredServiceLines endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 4 |  |  | 4 | Paulina | April 15, 2021, 11:23 AM | April 15, 2021, 2:40 PM | 4 | 39 | 0 | PP-636 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/24 | Sprint 4 | Added to sprint in Sprint 4 | Filters - Service Line filters | 4
2.15.4 | test filteredClinicalEpisodes endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | Monika | [5 empty] | PP-637 |  | Sprint 4 | Added to sprint in Sprint 4 | Filters - Service Line filters | 0
2.15.5 | test filteredDRGs endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | Paulina | April 15, 2021, 3:23 PM | April 16, 2021, 9:36 AM | 2.5 |  |  | PP-638 |  |  |  | Filters - Service Line filters | 8
2.16 | Location API | [7 empty] | 2021-04-13 13:06 | 2021-04-15 14:07 |  |  |  | PP-639 |  |  |  |  | 0
2.16.1 | test allUSStates endpoint | - check correctness of the response |  | 4 |  |  | 4 | Paulina | April 13, 2021, 1:06 PM | April 13, 2021, 2:28 PM | 1.5 | 34 | 0 | PP-640 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/11 | Sprint 4 |  | Filters - Geography (Location) filters | 4
2.16.2 | test usState endpoint | - check correctness of the response |  | 4 |  |  | 4 | Paulina | April 14, 2021, 12:59 PM | April 15, 2021, 9:39 AM | 3 | 59 | 0 | PP-641 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/22 | Sprint 4 |  | Filters - Geography (Location) filters | 4
2.16.3 | test searchUsLocation endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 6 |  |  | 6 | Paulina | April 14, 2021, 3:17 PM | April 15, 2021, 9:13 AM | 2.5 | 106 | 0 | PP-642 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/21 | Sprint 4 |  | Filters - Geography (Location) filters | 6
2.16.4 | test usStateGeoAll endpoint | - check correctness of the response |  | 4 |  |  | 4 | Monika | April 14, 2021, 12:58 PM | April 15, 2021, 9:50 AM | 3.5 | 44 | 0 | PP-643 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/20 | Sprint 4 |  | Filters - Geography (Location) filters | 4
2.16.5 | test usCountyGeoForState endpoint | - check correctness of the response |  | 4 |  |  | 4 | Monika | April 15, 2021, 8:32 AM | April 15, 2021, 2:07 PM | 4.5 |  |  | PP-644 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/23 | Sprint 4 |  | Filters - Geography (Location) filters | 4
2.16.6 | test usStateGeoSearch | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | Piotr | April 14, 2021, 11:58 AM | April 15, 2021, 11:24 AM | 4 | 43 | 2 | PP-645 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/17 | Sprint 4 |  | Filters - Geography (Location) filters | 8
2.16.7 | test usCountyGeoAll endpoint | - check correctness of the response |  | 5 |  |  | 5 | Piotr | April 14, 2021, 9:28 AM | April 14, 2021, 11:38 AM | 2 | 42 | 0 | PP-646 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/14 | Sprint 4 |  | Filters - Geography (Location) filters | 5
2.16.8 | test locationByRadialLocation endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 12 |  |  | 12 | Piotr | April 13, 2021, 4:10 PM | April 14, 2021, 9:21 AM | 2 | 49 | 0 | PP-647 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/13 | Sprint 4 |  | Filters - Geography (Location) filters | 12
3 | Front End tests | [7 empty] | 2021-04-20 | 2021-06-20 12:00 |  |  |  | PP-648 |  |  |  |  | 0
3.1 | Changes in regression library | [7 empty] | 2021-04-20 | 2021-06-19 18:00 |  |  |  | PP-649 |  |  |  |  | 0
3.1.1 | Authentication & Authorization | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-650 |  |  |  | Authentication & Authorization | 0
3.1.1.1 | Authentication Module |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1049 |  | Sprint 6 |  | Authentication & Authorization | 0
3.1.1.2 | Multi-tenancy |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1050 |  | Sprint 6 |  | Authentication & Authorization | 0
3.1.1.3 | Password requirements |  |  | 2 |  |  | 2 |  | 2021-05-04 | 2021-05-04 06:00 |  |  |  | PP-1051 |  | Sprint 6 |  | Authentication & Authorization | 0
3.1.1.4 | Change password |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1052 |  | Sprint 6 |  | Authentication & Authorization | 0
3.1.1.5 | Email Notifications & New email templates |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1053 |  | Sprint 6 |  | Authentication & Authorization | 0
3.1.2 | Dataset Upload & Management | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-698 |  |  |  |  | 0
3.1.2.1 | Dataset upload |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1054 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.1.2.2 | Dataset permissions |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1055 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.1.2.3 | View datasets details |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1056 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.1.2.4 | Delete Dataset |  |  | 2 |  |  | 2 |  | 2021-05-04 | 2021-05-04 06:00 |  |  |  | PP-1057 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.1.2.5 | Export datasets statistics details as Excel file |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1058 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.1.2.6 | Statistics preview of a dataset by entity type |  |  | 2 |  |  | 2 |  | 2021-05-04 | 2021-05-04 06:00 |  |  |  | PP-1059 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.1.3 | View Dashboard | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-04-20 | 2021-04-21 |  |  |  | PP-651 |  |  |  |  | 0
3.1.3.1 | View Creation |  |  | 6 |  |  | 6 |  | 2021-04-20 | 2021-04-20 18:00 |  |  |  | PP-1060 |  | Sprint 5 |  | View Dashboard | 0
3.1.3.2 | View Management (delete, search, etc) + search by dataset + save view/new view |  |  | 8 |  |  | 8 |  | 2021-04-20 | 2021-04-21 |  |  |  | PP-1061 |  | Sprint 5 |  | View Dashboard | 0
3.1.3.3 | View duplication |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1062 |  | Sprint 5 |  | View Dashboard | 0
3.1.3.4 | View name editing |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1063 |  | Sprint 5 |  | View Dashboard | 0
3.1.4 | Location Filter | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-04-20 | 2021-04-21 06:00 |  |  |  | PP-652 |  |  |  |  | 0
3.1.4.1 | Location filter by states & FIPS & CBSA [2nd and 3rd panel] |  |  | 10 |  |  | 10 |  | 2021-04-20 | 2021-04-21 06:00 |  |  |  | PP-1064 |  | Sprint 5 |  | Location filter by FIPS | 0
3.1.4.2 | Location filter by Radius map [2nd and 3rd panel] |  |  | 10 |  |  | 10 |  | 2021-04-20 | 2021-04-21 06:00 |  |  |  | PP-1065 |  | Sprint 5 |  | Location filter by FIPS | 0
3.1.4.3 | Location filter switch between grayscale and terrain |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1066 |  | Sprint 5 |  | Location filter by FIPS | 0
3.1.4.4 | Location filter applies to |  |  | 8 |  |  | 8 |  | 2021-04-20 | 2021-04-21 |  |  |  | PP-1067 |  | Sprint 5 |  | Location filter by FIPS | 0
3.1.4.5 | Tooltips for location filters |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1068 |  | Sprint 5 |  | Location filter by FIPS | 0
3.1.4.6 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features e.g. scrolling/zooming map] |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1069 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.4.7 | Pagination of the Entity, Service Lines,..Filters |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1070 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.4.8 | Filter search |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1071 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.4.9 | Clear filters feature |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1072 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.4.10 | Filters breadcrumb (tree structures) |  |  | 6 |  |  | 6 |  | 2021-04-20 | 2021-04-20 18:00 |  |  |  | PP-1073 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.1.4.11 | Filters breadcrumb navigation to the selected layer |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1074 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.1.5 | Entity Filter | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-04-20 | 2021-04-21 |  |  |  | PP-653 |  |  |  |  | 0
3.1.5.1 | Entity-post acute type filter & Entity-Hospital filter [2nd and 3rd panel] |  |  | 8 |  |  | 8 |  | 2021-04-20 | 2021-04-21 |  |  |  | PP-1075 |  | Sprint 5 |  | Filters - Entity filters | 0
3.1.5.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1076 |  | Sprint 5 |  | Filters - Entity filters | 0
3.1.5.3 | Pagination of the Entity, Service Lines,..Filters |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1077 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.5.4 | Filter search |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1078 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.5.5 | Tooltips when hovering over filters |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1079 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.5.6 | Clear filters feature |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1080 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.5.7 | Filters breadcrumb (tree structures) for Service Line and Entity filters |  |  | 6 |  |  | 6 |  | 2021-04-20 | 2021-04-20 18:00 |  |  |  | PP-1081 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.1.5.8 | Filters breadcrumb navigation to the selected layer |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1082 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.1.6 | Service Line filter | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-04-20 | 2021-04-21 06:00 |  |  |  | PP-654 |  |  |  |  | 0
3.1.6.1 | Service line filter [SL, Episode, DRG levels - 2nd and 3rd panel] |  |  | 10 |  |  | 10 |  | 2021-04-20 | 2021-04-21 06:00 |  |  |  | PP-1083 |  | Sprint 5 |  | Filters - Service Line filters | 0
3.1.6.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1084 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.6.3 | Pagination of the Entity, Service Lines,..Filters |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1085 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.6.4 | Filter search |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1086 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.6.5 | Tooltips when hovering over filters |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1087 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.6.6 | Clear filters feature |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1088 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.6.7 | Filters breadcrumb (tree structures) for Service Line and Entity filters |  |  | 6 |  |  | 6 |  | 2021-04-20 | 2021-04-20 18:00 |  |  |  | PP-1089 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.1.6.8 | Filters breadcrumb navigation to the selected layer |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1090 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.1.7 | LOB Filter | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-655 |  |  |  |  | 0
3.1.7.1 | LOB filter [2nd and 3rd panel] |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1091 |  | Sprint 5 |  | Filters - LOB filters | 0
3.1.7.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1092 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.7.3 | Filter search |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1093 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.7.4 | Tooltips when hovering over filters |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1094 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.7.5 | Clear filters feature |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1095 |  | Sprint 5 |  | Filters - Convenience features | 0
3.1.8 | Graph View | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-05-04 | 2021-05-06 12:00 |  |  |  | PP-656 |  |  |  |  | 0
3.1.8.1 | Loading the default view/report |  |  | 1 |  |  | 1 |  | 2021-05-04 | 2021-05-04 03:00 |  |  |  | PP-1096 |  | Sprint 6 |  | Visualization Generation | 0
3.1.8.2 | Market share Graph + filters [check calculations results here] |  |  | 20 |  |  | 20 |  | 2021-05-04 | 2021-05-06 12:00 |  |  |  | PP-1097 |  | Sprint 6 |  | Visualization Generation | 0
3.1.8.3 | Benchmark Graph + filters [general cases, calculations checked in benchmark tab] |  |  | 16 |  |  | 16 |  | 2021-05-04 | 2021-05-06 |  |  |  | PP-1098 |  | Sprint 6 |  | Visualization Generation | 0
3.1.8.4 | Multi-layer Graph view (all navigation types checked in here) |  |  | 10 |  |  | 10 |  | 2021-05-04 | 2021-05-05 06:00 |  |  |  | PP-1099 |  | Sprint 6 |  | Graph visualization convenience features | 0
3.1.8.5 | Graph view maximum number of nodes display |  |  | 6 |  |  | 6 |  | 2021-05-04 | 2021-05-04 18:00 |  |  |  | PP-1100 |  | Sprint 6 |  | Graph visualization convenience features | 0
3.1.8.6 | Highlight a node for re-calculation |  |  | 6 |  |  | 6 |  | 2021-05-04 | 2021-05-04 18:00 |  |  |  | PP-1101 |  | Sprint 6 |  | Graph visualization convenience features | 0
3.1.8.7 | Orders settings |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1102 |  | Sprint 6 |  | Graph visualization convenience features | 0
3.1.8.8 | Legend for Graph [general tests only, check calculations along with graph + filters category, dynamic legend with navigation/multi-layer graph] |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1103 |  | Sprint 6 |  | Visualization Legend | 0
3.1.8.9 | Custom error messages related to filter choice |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1104 |  | Sprint 6 |  | System | 0
3.1.8.10 | Exit the view and warning popups |  |  | 1 |  |  | 1 |  | 2021-05-04 | 2021-05-04 03:00 |  |  |  | PP-1105 |  | Sprint 6 |  | System | 0
3.1.8.11 | Navigation menu (switching between view types, market share and benchmark modes) |  |  | 2 |  |  | 2 |  | 2021-05-04 | 2021-05-04 06:00 |  |  |  | PP-1106 |  | Sprint 6 |  | Visualization Navigation | 0
3.1.9 | Map View | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-05-18 | 2021-05-20 12:00 |  |  |  | PP-657 |  |  |  |  | 0
3.1.9.1 | Market share Map + filters [check calculations results here] |  |  | 20 |  |  | 20 |  | 2021-05-18 | 2021-05-20 12:00 |  |  |  | PP-1107 |  | Sprint 7 |  | Visualization Generation | 0
3.1.9.2 | Benchmark view Map + filters [general cases, calculations checked in benchmark tab] |  |  | 16 |  |  | 16 |  | 2021-05-18 | 2021-05-20 |  |  |  | PP-1108 |  | Sprint 7 |  | Visualization Generation | 0
3.1.9.3 | Map view navigation |  |  | 6 |  |  | 6 |  | 2021-05-18 | 2021-05-18 18:00 |  |  |  | PP-1109 |  | Sprint 7 |  | Visualization Navigation | 0
3.1.9.4 | Opacity slider for map |  |  | 2 |  |  | 2 |  | 2021-05-18 | 2021-05-18 06:00 |  |  |  | PP-1110 |  | Sprint 7 |  | Graph visualization convenience features | 0
3.1.9.5 | Legend for Map [general tests only, check calculations along with graph + filters category] + dynamic legend |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1111 |  | Sprint 7 |  | Visualization Legend | 0
3.1.9.6 | Custom error messages related to filter choice |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1112 |  | Sprint 7 |  | System | 0
3.1.9.7 | Exit the view and warning popups |  |  | 1 |  |  | 1 |  | 2021-05-18 | 2021-05-18 03:00 |  |  |  | PP-1113 |  | Sprint 7 |  | System | 0
3.1.10 | 2D Graph View | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-05-18 | 2021-05-20 |  |  |  | PP-658 |  |  |  |  | 0
3.1.10.1 | 2D graph view + filters [general cases, calculations checked in benchmark tab] |  |  | 16 |  |  | 16 |  | 2021-05-18 | 2021-05-20 |  |  |  | PP-1114 |  | Sprint 7 |  | Visualization Generation | 0
3.1.10.2 | 2D Navigation |  |  | 8 |  |  | 8 |  | 2021-05-18 | 2021-05-19 |  |  |  | PP-1115 |  | Sprint 7 |  | Visualization Navigation | 0
3.1.10.3 | Legend for 2D [general tests only, check calculations along with graph + filters category] + dynamic legend |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1116 |  | Sprint 7 |  | Visualization Legend | 0
3.1.10.4 | Custom error messages related to filter choice |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1117 |  | Sprint 7 |  | System | 0
3.1.10.5 | Exit the view and warning popups |  |  | 1 |  |  | 1 |  | 2021-05-18 | 2021-05-18 03:00 |  |  |  | PP-1118 |  | Sprint 7 |  | System | 0
3.1.11 | Benchmark Settings and calculations on Graph | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-05-18 | 2021-06-15 |  |  |  | PP-659 |  |  |  |  | 0
3.1.11.1 | Benchmarking default settings for Graph and benchmark calculation |  |  | 1 |  |  | 1 |  | 2021-05-18 | 2021-05-18 03:00 |  |  |  | PP-1119 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.11.2 | Benchmarking Measures |  |  | 6 |  |  | 6 |  | 2021-05-18 | 2021-05-18 18:00 |  |  |  | PP-1120 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.11.3 | Benchmark standard level of aggregations |  |  | 6 |  |  | 6 |  | 2021-05-18 | 2021-05-18 18:00 |  |  |  | PP-1121 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.11.4 | Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1122 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.11.5 | Benchmark metrics by percentile & average |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1123 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.11.6 | Benchmark time range |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1124 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.11.7 | Benchmark to LOB settings |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1125 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.11.8 | Search function on benchmark settings |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1126 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.11.9 | Benchmark calculations (all filters + various benchmark settings) |  |  | 24 |  |  | 24 |  | 2021-06-12 | 2021-06-15 |  |  |  | PP-1127 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.12 | Benchmark Settings and calculations on Map | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-06-12 | 2021-06-15 |  |  |  | PP-660 |  |  |  |  | 0
3.1.12.1 | Benchmarking default settings for Map and benchmark calculation |  |  | 1 |  |  | 1 |  | 2021-06-12 | 2021-06-12 03:00 |  |  |  | PP-1128 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.12.2 | Benchmarking Measures |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1129 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.12.3 | Benchmark standard level of aggregations |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1130 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.12.4 | Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1131 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.12.5 | Benchmark metrics by percentile & average |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1132 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.12.6 | Benchmark time range |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1133 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.12.7 | Benchmark to LOB settings |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1134 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.12.8 | Search function on benchmark settings |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1135 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.12.9 | Benchmark calculations (all filters + various benchmark settings) |  |  | 24 |  |  | 24 |  | 2021-06-12 | 2021-06-15 |  |  |  | PP-1136 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.13 | Benchmark Settings and calculations on 2D | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-06-12 | 2021-06-15 |  |  |  | PP-661 |  |  |  |  | 0
3.1.13.1 | Benchmarking default settings for 2D and benchmark calculation |  |  | 1 |  |  | 1 |  | 2021-06-12 | 2021-06-12 03:00 |  |  |  | PP-1137 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.13.2 | Benchmarking Measures |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1138 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.13.3 | Benchmark standard level of aggregations |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1139 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.13.4 | Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1140 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.13.5 | Benchmark metrics by percentile & average |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1141 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.13.6 | Benchmark time range |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1142 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.13.7 | Benchmark to LOB settings |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1143 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.13.8 | Search function on benchmark settings |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1144 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.13.9 | Benchmark calculations (all filters + various benchmark settings) |  |  | 24 |  |  | 24 |  | 2021-06-12 | 2021-06-15 |  |  |  | PP-1145 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.1.14 | Label settings | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-06-15 | 2021-06-16 12:00 |  |  |  | PP-662 |  |  |  |  | 0
3.1.14.1 | Labels on Graph |  |  | 12 |  |  | 12 |  | 2021-06-15 | 2021-06-16 12:00 |  |  |  | PP-1146 |  | Sprint 9 |  | Label settings | 0
3.1.14.2 | Labels on Map |  |  | 6 |  |  | 6 |  | 2021-06-15 | 2021-06-15 18:00 |  |  |  | PP-1147 |  | Sprint 9 |  | Label settings | 0
3.1.14.3 | Labels on 2D Graph |  |  | 6 |  |  | 6 |  | 2021-06-15 | 2021-06-15 18:00 |  |  |  | PP-1148 |  | Sprint 9 |  | Label settings | 0
3.1.15 | LDS suppression rule-11 (after implementation add LDS test cases to check CC11 ) | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-06-15 | 2021-06-19 18:00 |  |  |  | PP-663 |  |  |  |  | 0
3.1.15.1 | LDS suppression rule-11 |  |  | 38 |  |  | 38 |  | 2021-06-15 | 2021-06-19 18:00 |  |  |  | PP-1149 |  | Sprint 9 |  | LDS suppression rule-11 | 0
3.1.15.2 | LDS rule-11 in screen floating message |  |  | 2 |  |  | 2 |  | 2021-06-15 | 2021-06-15 06:00 |  |  |  | PP-1150 |  | Sprint 9 |  | LDS suppression rule-11 | 0
3.1.16 | Save or export Visualization | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-04-20 | 2021-06-16 |  |  |  | PP-664 |  |  |  |  | 0
3.1.16.1 | Export as PNG |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1151 |  | Sprint 5 |  | Save or export Visualization | 0
3.1.16.2 | Export the View as Excel |  |  | 8 |  |  | 8 |  | 2021-06-15 | 2021-06-16 |  |  |  | PP-1152 |  | Sprint 9 |  | Save or export Visualization | 0
3.1.17 | System | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-06-15 | 2021-06-15 06:00 |  |  |  | PP-665 |  |  |  |  | 0
3.1.17.1 | Inactivity countdown timer |  |  | 2 |  |  | 2 |  | 2021-06-15 | 2021-06-15 06:00 |  |  |  | PP-1153 |  | Sprint 9 |  | System | 0
3.1.17.2 | View user manual |  |  | 1 |  |  | 1 |  | 2021-06-15 | 2021-06-15 03:00 |  |  |  | PP-1154 |  | Sprint 9 |  | System | 0
3.1.17.3 | Customer support contact information icons |  |  | 1 |  |  | 1 |  | 2021-06-15 | 2021-06-15 03:00 |  |  |  | PP-1155 |  | Sprint 9 |  | System | 0
3.1.17.4 | Versioning and copyright maintenance |  |  | 1 |  |  | 1 |  | 2021-06-15 | 2021-06-15 03:00 |  |  |  | PP-1156 |  | Sprint 9 |  | System | 0
3.1.18 | Show Details | make a cleanup in the tab following the rules from the design | [6 empty] | 2021-06-15 | 2021-06-16 |  |  |  | PP-1157 |  |  |  |  | 0
3.1.18.1 | Contex menu - Graph View |  |  | 2 |  |  | 2 |  | 2021-06-15 | 2021-06-15 06:00 |  |  |  | PP-1158 |  | Sprint 9 |  | Visualization Generation | 0
3.1.18.2 | Context menu - 2D Graph View |  |  | 1 |  |  | 1 |  | 2021-06-15 | 2021-06-15 03:00 |  |  |  | PP-1159 |  | Sprint 9 |  | Visualization Generation | 0
3.1.18.3 | Context menu - Map view |  |  | 1 |  |  | 1 |  | 2021-06-15 | 2021-06-15 03:00 |  |  |  | PP-1160 |  | Sprint 9 |  | Visualization Generation | 0
3.1.18.4 | Show details panel |  |  | 8 |  |  | 8 |  | 2021-06-15 | 2021-06-16 |  |  |  | PP-1161 |  | Sprint 9 |  | Visualization Generation | 0
3.2. | Automating regression library test cases | [12 empty] | PP-666 |  |  |  |  | 0
3.2.1 | Authentication & Authorization | automate tests from the tab | [6 empty] | 2021-05-04 | 2021-05-05 |  |  |  | PP-667 |  |  |  |  | 0
3.2.1.1 | Authentication Module |  |  | 6 |  |  | 6 |  | 2021-05-04 | 2021-05-04 18:00 |  |  |  | PP-1162 |  | Sprint 6 |  | Authentication & Authorization | 0
3.2.1.2 | Multi-tenancy |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1163 |  | Sprint 6 |  | Authentication & Authorization | 0
3.2.1.3 | Password requirements |  |  | 2 |  |  | 2 |  | 2021-05-04 | 2021-05-04 06:00 |  |  |  | PP-1164 |  | Sprint 6 |  | Authentication & Authorization | 0
3.2.1.4 | Change password |  |  | 8 |  |  | 8 |  | 2021-05-04 | 2021-05-05 |  |  |  | PP-1165 |  | Sprint 6 |  | Authentication & Authorization | 0
3.2.1.5 | Email Notifications & New email templates |  |  | 8 |  |  | 8 |  | 2021-05-04 | 2021-05-05 |  |  |  | PP-1166 |  | Sprint 6 |  | Authentication & Authorization | 0
3.2.2 | Dataset Upload & Management | automate tests from the tab | [6 empty] | 2021-05-04 | 2021-05-04 18:00 |  |  |  | PP-699 |  |  |  |  | 0
3.2.2.1 | Dataset upload |  |  | 6 |  |  | 6 |  | 2021-05-04 | 2021-05-04 18:00 |  |  |  | PP-1167 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.2.2.2 | Dataset permissions |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1168 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.2.2.3 | View datasets details |  |  | 5 |  |  | 5 |  | 2021-05-04 | 2021-05-04 15:00 |  |  |  | PP-1169 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.2.2.4 | Delete Dataset |  |  | 3 |  |  | 3 |  | 2021-05-04 | 2021-05-04 09:00 |  |  |  | PP-1170 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.2.2.5 | Export datasets statistics details as Excel file |  |  | 6 |  |  | 6 |  | 2021-05-04 | 2021-05-04 18:00 |  |  |  | PP-1171 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.2.2.6 | Statistics preview of a dataset by entity type |  |  | 3 |  |  | 3 |  | 2021-05-04 | 2021-05-04 09:00 |  |  |  | PP-1172 |  | Sprint 6 |  | Dataset Upload & Management | 0
3.2.3 | View Dashboard | automate tests from the tab | [6 empty] | 2021-04-20 | 2021-04-21 06:00 |  |  |  | PP-668 |  |  |  |  | 0
3.2.3.1 | View Creation |  |  | 6 |  |  | 6 |  | 2021-04-20 | 2021-04-20 18:00 |  |  |  | PP-1173 |  | Sprint 5 |  | View Dashboard | 0
3.2.3.2 | View Management (delete, search, etc) + search by dataset + save view/new view |  |  | 10 |  |  | 10 |  | 2021-04-20 | 2021-04-21 06:00 |  |  |  | PP-1174 |  | Sprint 5 |  | View Dashboard | 0
3.2.3.3 | View duplication |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1175 |  | Sprint 5 |  | View Dashboard | 0
3.2.3.4 | View name editing |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1176 |  | Sprint 5 |  | View Dashboard | 0
3.2.4 | Location Filter | automate tests from the tab | [6 empty] | 2021-04-20 | 2021-04-22 |  |  |  | PP-669 |  |  |  |  | 0
3.2.4.1 | Location filter by states & FIPS & CBSA [2nd and 3rd panel] |  |  | 16 |  |  | 16 |  | 2021-04-20 | 2021-04-22 |  |  |  | PP-1177 |  | Sprint 5 |  | Location filter by FIPS | 0
3.2.4.2 | Location filter by Radius map [2nd and 3rd panel] |  |  | 16 |  |  | 16 |  | 2021-04-20 | 2021-04-22 |  |  |  | PP-1178 |  | Sprint 5 |  | Location filter by FIPS | 0
3.2.4.3 | Location filter switch between grayscale and terrain |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1179 |  | Sprint 5 |  | Location filter by FIPS | 0
3.2.4.4 | Location filter applies to |  |  | 8 |  |  | 8 |  | 2021-04-20 | 2021-04-21 |  |  |  | PP-1180 |  | Sprint 5 |  | Location filter by FIPS | 0
3.2.4.5 | Tooltips for location filters |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1181 |  | Sprint 5 |  | Location filter by FIPS | 0
3.2.4.6 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features e.g. scrolling/zooming map] |  |  | 8 |  |  | 8 |  | 2021-04-20 | 2021-04-21 |  |  |  | PP-1182 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.4.7 | Pagination of the Entity, Service Lines,..Filters |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1183 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.4.8 | Filter search |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1184 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.4.9 | Clear filters feature |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1185 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.4.10 | Filters breadcrumb (tree structures) |  |  | 8 |  |  | 8 |  | 2021-04-20 | 2021-04-21 |  |  |  | PP-1186 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.2.4.11 | Filters breadcrumb navigation to the selected layer |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1187 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.2.5 | Entity Filter | automate tests from the tab | [6 empty] | 2021-04-20 | 2021-04-22 |  |  |  | PP-670 |  |  |  |  | 0
3.2.5.1 | Entity-post acute type filter & Entity-Hospital filter [2nd and 3rd panel] |  |  | 16 |  |  | 16 |  | 2021-04-20 | 2021-04-22 |  |  |  | PP-1188 |  | Sprint 5 |  | Filters - Entity filters | 0
3.2.5.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  |  | 8 |  |  | 8 |  | 2021-04-20 | 2021-04-21 |  |  |  | PP-1189 |  | Sprint 5 |  | Filters - Entity filters | 0
3.2.5.3 | Pagination of the Entity, Service Lines,..Filters |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1190 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.5.4 | Filter search |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1191 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.5.5 | Tooltips when hovering over filters |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1192 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.5.6 | Clear filters feature |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1193 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.5.7 | Filters breadcrumb (tree structures) for Service Line and Entity filters |  |  | 6 |  |  | 6 |  | 2021-04-20 | 2021-04-20 18:00 |  |  |  | PP-1194 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.2.5.8 | Filters breadcrumb navigation to the selected layer |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1195 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.2.6 | Service Line filter | automate tests from the tab | [6 empty] | 2021-04-20 | 2021-04-22 |  |  |  | PP-671 |  |  |  |  | 0
3.2.6.1 | Service line filter [SL, Episode, DRG levels - 2nd and 3rd panel] |  |  | 16 |  |  | 16 |  | 2021-04-20 | 2021-04-22 |  |  |  | PP-1196 |  | Sprint 5 |  | Filters - Service Line filters | 0
3.2.6.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  |  | 8 |  |  | 8 |  | 2021-04-20 | 2021-04-21 |  |  |  | PP-1197 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.6.3 | Pagination of the Entity, Service Lines,..Filters |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1198 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.6.4 | Filter search |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1199 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.6.5 | Tooltips when hovering over filters |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1200 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.6.6 | Clear filters feature |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1201 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.6.7 | Filters breadcrumb (tree structures) for Service Line and Entity filters |  |  | 6 |  |  | 6 |  | 2021-04-20 | 2021-04-20 18:00 |  |  |  | PP-1202 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.2.6.8 | Filters breadcrumb navigation to the selected layer |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1203 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | 0
3.2.7 | LOB Filter | automate tests from the tab | [6 empty] | 2021-04-20 | 2021-04-21 |  |  |  | PP-672 |  |  |  |  | 0
3.2.7.1 | LOB filter [2nd and 3rd panel] |  |  | 8 |  |  | 8 |  | 2021-04-20 | 2021-04-21 |  |  |  | PP-1204 |  | Sprint 5 |  | Filters - LOB filters | 0
3.2.7.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  |  | 4 |  |  | 4 |  | 2021-04-20 | 2021-04-20 12:00 |  |  |  | PP-1205 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.7.3 | Filter search |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1206 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.7.4 | Tooltips when hovering over filters |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1207 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.7.5 | Clear filters feature |  |  | 2 |  |  | 2 |  | 2021-04-20 | 2021-04-20 06:00 |  |  |  | PP-1208 |  | Sprint 5 |  | Filters - Convenience features | 0
3.2.8 | Graph View | automate tests from the tab | [6 empty] | 2021-05-04 | 2021-05-06 12:00 |  |  |  | PP-673 |  |  |  |  | 0
3.2.8.1 | Loading the default view/report |  |  | 2 |  |  | 2 |  | 2021-05-04 | 2021-05-04 06:00 |  |  |  | PP-1209 |  | Sprint 6 |  | Visualization Generation | 0
3.2.8.2 | Market share Graph + filters [check calculations results here] |  |  | 20 |  |  | 20 |  | 2021-05-04 | 2021-05-06 12:00 |  |  |  | PP-1210 |  | Sprint 6 |  | Visualization Generation | 0
3.2.8.3 | Benchmark Graph + filters [general cases, calculations checked in benchmark tab] |  |  | 16 |  |  | 16 |  | 2021-05-04 | 2021-05-06 |  |  |  | PP-1211 |  | Sprint 6 |  | Visualization Generation | 0
3.2.8.4 | Multi-layer Graph view (all navigation types checked in here) |  |  | 16 |  |  | 16 |  | 2021-05-04 | 2021-05-06 |  |  |  | PP-1212 |  | Sprint 6 |  | Graph visualization convenience features | 0
3.2.8.5 | Graph view maximum number of nodes display |  |  | 6 |  |  | 6 |  | 2021-05-04 | 2021-05-04 18:00 |  |  |  | PP-1213 |  | Sprint 6 |  | Graph visualization convenience features | 0
3.2.8.6 | Highlight a node for re-calculation |  |  | 6 |  |  | 6 |  | 2021-05-04 | 2021-05-04 18:00 |  |  |  | PP-1214 |  | Sprint 6 |  | Graph visualization convenience features | 0
3.2.8.7 | Orders settings |  |  | 8 |  |  | 8 |  | 2021-05-04 | 2021-05-05 |  |  |  | PP-1215 |  | Sprint 6 |  | Graph visualization convenience features | 0
3.2.8.8 | Legend for Graph [general tests only, check calculations along with graph + filters category, dynamic legend with navigation/multi-layer graph] |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1216 |  | Sprint 6 |  | Visualization Legend | 0
3.2.8.9 | Custom error messages related to filter choice |  |  | 4 |  |  | 4 |  | 2021-05-04 | 2021-05-04 12:00 |  |  |  | PP-1217 |  | Sprint 6 |  | System | 0
3.2.8.10 | Exit the view and warning popups |  |  | 2 |  |  | 2 |  | 2021-05-04 | 2021-05-04 06:00 |  |  |  | PP-1218 |  | Sprint 6 |  | System | 0
3.2.8.11 | Navigation menu (switching between view types, market share and benchmark modes) |  |  | 2 |  |  | 2 |  | 2021-05-04 | 2021-05-04 06:00 |  |  |  | PP-1219 |  | Sprint 6 |  | Visualization Navigation | 0
3.2.9 | Map View | automate tests from the tab | [6 empty] | 2021-05-18 | 2021-05-20 12:00 |  |  |  | PP-674 |  |  |  |  | 0
3.2.9.1 | Market share Map + filters [check calculations results here] |  |  | 20 |  |  | 20 |  | 2021-05-18 | 2021-05-20 12:00 |  |  |  | PP-1220 |  | Sprint 7 |  | Visualization Generation | 0
3.2.9.2 | Benchmark view Map + filters [general cases, calculations checked in benchmark tab] |  |  | 16 |  |  | 16 |  | 2021-05-18 | 2021-05-20 |  |  |  | PP-1221 |  | Sprint 7 |  | Visualization Generation | 0
3.2.9.3 | Map view navigation |  |  | 16 |  |  | 16 |  | 2021-05-18 | 2021-05-20 |  |  |  | PP-1222 |  | Sprint 7 |  | Visualization Navigation | 0
3.2.9.4 | Opacity slider for map |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1223 |  | Sprint 7 |  | Graph visualization convenience features | 0
3.2.9.5 | Legend for Map [general tests only, check calculations along with graph + filters category] + dynamic legend |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1224 |  | Sprint 7 |  | Visualization Legend | 0
3.2.9.6 | Custom error messages related to filter choice |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1225 |  | Sprint 7 |  | System | 0
3.2.9.7 | Exit the view and warning popups |  |  | 2 |  |  | 2 |  | 2021-05-18 | 2021-05-18 06:00 |  |  |  | PP-1226 |  | Sprint 7 |  | System | 0
3.2.10 | 2D Graph View | automate tests from the tab | [6 empty] | 2021-05-18 | 2021-05-20 12:00 |  |  |  | PP-675 |  |  |  |  | 0
3.2.10.1 | 2D graph view + filters [general cases, calculations checked in benchmark tab] |  |  | 20 |  |  | 20 |  | 2021-05-18 | 2021-05-20 12:00 |  |  |  | PP-1227 |  | Sprint 7 |  | Visualization Generation | 0
3.2.10.2 | 2D Navigation |  |  | 16 |  |  | 16 |  | 2021-05-18 | 2021-05-20 |  |  |  | PP-1228 |  | Sprint 7 |  | Visualization Navigation | 0
3.2.10.3 | Legend for 2D [general tests only, check calculations along with graph + filters category] + dynamic legend |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1229 |  | Sprint 7 |  | Visualization Legend | 0
3.2.10.4 | Custom error messages related to filter choice |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1230 |  | Sprint 7 |  | System | 0
3.2.10.5 | Exit the view and warning popups |  |  | 2 |  |  | 2 |  | 2021-05-18 | 2021-05-18 06:00 |  |  |  | PP-1231 |  | Sprint 7 |  | System | 0
3.2.11 | Benchmark Settings and calculations on Graph | automate tests from the tab | [6 empty] | 2021-05-18 | 2021-06-15 |  |  |  | PP-676 |  |  |  |  | 0
3.2.11.1 | Benchmarking default settings for Map and benchmark calculation |  |  | 2 |  |  | 2 |  | 2021-05-18 | 2021-05-18 06:00 |  |  |  | PP-1232 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.11.2 | Benchmarking Measures |  |  | 8 |  |  | 8 |  | 2021-05-18 | 2021-05-19 |  |  |  | PP-1233 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.11.3 | Benchmark standard level of aggregations |  |  | 8 |  |  | 8 |  | 2021-05-18 | 2021-05-19 |  |  |  | PP-1234 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.11.4 | Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) |  |  | 4 |  |  | 4 |  | 2021-05-18 | 2021-05-18 12:00 |  |  |  | PP-1235 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.11.5 | Benchmark metrics by percentile & average |  |  | 6 |  |  | 6 |  | 2021-05-18 | 2021-05-18 18:00 |  |  |  | PP-1236 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.11.6 | Benchmark time range |  |  | 8 |  |  | 8 |  | 2021-06-12 | 2021-06-13 |  |  |  | PP-1237 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.11.7 | Benchmark to LOB settings |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1238 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.11.8 | Search function on benchmark settings |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1239 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.11.9 | Benchmark calculations (all filters + various benchmark settings) |  |  | 24 |  |  | 24 |  | 2021-06-12 | 2021-06-15 |  |  |  | PP-1240 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.12 | Benchmark Settings and calculations on Map | automate tests from the tab | [6 empty] | 2021-06-12 | 2021-06-15 |  |  |  | PP-677 |  |  |  |  | 0
3.2.12.1 | Benchmarking default settings for Map and benchmark calculation |  |  | 2 |  |  | 2 |  | 2021-06-12 | 2021-06-12 06:00 |  |  |  | PP-1241 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.12.2 | Benchmarking Measures |  |  | 8 |  |  | 8 |  | 2021-06-12 | 2021-06-13 |  |  |  | PP-1242 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.12.3 | Benchmark standard level of aggregations |  |  | 8 |  |  | 8 |  | 2021-06-12 | 2021-06-13 |  |  |  | PP-1243 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.12.4 | Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1244 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.12.5 | Benchmark metrics by percentile & average |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1245 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.12.6 | Benchmark time range |  |  | 8 |  |  | 8 |  | 2021-06-12 | 2021-06-13 |  |  |  | PP-1246 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.12.7 | Benchmark to LOB settings |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1247 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.12.8 | Search function on benchmark settings |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1248 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.12.9 | Benchmark calculations (all filters + various benchmark settings) |  |  | 24 |  |  | 24 |  | 2021-06-12 | 2021-06-15 |  |  |  | PP-1249 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.13 | Benchmark Settings and calculations on 2D | automate tests from the tab | [6 empty] | 2021-06-12 | 2021-06-18 |  |  |  | PP-678 |  |  |  |  | 0
3.2.13.1 | Benchmarking default settings for 2D and benchmark calculation |  |  | 2 |  |  | 2 |  | 2021-06-12 | 2021-06-12 06:00 |  |  |  | PP-1250 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.13.2 | Benchmarking Measures |  |  | 8 |  |  | 8 |  | 2021-06-12 | 2021-06-13 |  |  |  | PP-1251 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.13.3 | Benchmark standard level of aggregations |  |  | 8 |  |  | 8 |  | 2021-06-12 | 2021-06-13 |  |  |  | PP-1252 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.13.4 | Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1253 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.13.5 | Benchmark metrics by percentile & average |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1254 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.13.6 | Benchmark time range |  |  | 8 |  |  | 8 |  | 2021-06-12 | 2021-06-13 |  |  |  | PP-1255 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.13.7 | Benchmark to LOB settings |  |  | 4 |  |  | 4 |  | 2021-06-12 | 2021-06-12 12:00 |  |  |  | PP-1256 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.13.8 | Search function on benchmark settings |  |  | 6 |  |  | 6 |  | 2021-06-12 | 2021-06-12 18:00 |  |  |  | PP-1257 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.13.9 | Benchmark calculations (all filters + various benchmark settings) |  |  | 24 |  |  | 24 |  | 2021-06-15 | 2021-06-18 |  |  |  | PP-1258 |  | Sprint 9 |  | Benchmark settings customization & Benchmark Calculation | 0
3.2.14 | Label settings | automate tests from the tab | [6 empty] | 2021-06-15 | 2021-06-17 |  |  |  | PP-679 |  |  |  |  | 0
3.2.14.1 | Labels on Graph |  |  | 16 |  |  | 16 |  | 2021-06-15 | 2021-06-17 |  |  |  | PP-1259 |  | Sprint 9 |  | Label settings | 0
3.2.14.2 | Labels on Map |  |  | 8 |  |  | 8 |  | 2021-06-15 | 2021-06-16 |  |  |  | PP-1260 |  | Sprint 9 |  | Label settings | 0
3.2.14.3 | Labels on 2D Graph |  |  | 8 |  |  | 8 |  | 2021-06-15 | 2021-06-16 |  |  |  | PP-1261 |  | Sprint 9 |  | Label settings | 0
3.2.15 | LDS suppression rule-11 (after implementation add LDS test cases to check CC11 ) | automate tests from the tab | [6 empty] | 2021-06-15 | 2021-06-20 12:00 |  |  |  | PP-680 |  |  |  |  | 0
3.2.15.1 | LDS suppression rule-11 |  |  | 44 |  |  | 44 |  | 2021-06-15 | 2021-06-20 12:00 |  |  |  | PP-1262 |  | Sprint 9 |  | LDS suppression rule-11 | 0
3.2.15.2 | LDS rule-11 in screen floating message |  |  | 4 |  |  | 4 |  | 2021-06-15 | 2021-06-15 12:00 |  |  |  | PP-1263 |  | Sprint 9 |  | LDS suppression rule-11 | 0
3.2.16 | Save or export Visualization | automate tests from the tab | [6 empty] | 2021-04-20 | 2021-06-17 |  |  |  | PP-681 |  |  |  |  | 0
3.2.16.1 | Export as PNG |  |  | 16 |  |  | 16 |  | 2021-04-20 | 2021-04-22 |  |  |  | PP-1264 |  | Sprint 5 |  | Save or export Visualization | 0
3.2.16.2 | Export the View as Excel |  |  | 16 |  |  | 16 |  | 2021-06-15 | 2021-06-17 |  |  |  | PP-1265 |  | Sprint 9 |  | Save or export Visualization | 0
3.2.17 | System | automate tests from the tab | [6 empty] | 2021-06-15 | 2021-06-15 03:00 |  |  |  | PP-682 |  |  |  |  | 0
3.2.17.1 | View user manual |  |  | 1 |  |  | 1 |  | 2021-06-15 | 2021-06-15 03:00 |  |  |  | PP-1266 |  | Sprint 9 |  | System | 0
3.2.17.2 | Customer support contact information icons |  |  | 1 |  |  | 1 |  | 2021-06-15 | 2021-06-15 03:00 |  |  |  | PP-1267 |  | Sprint 9 |  | System | 0
3.2.17.3 | Versioning and copyright maintenance |  |  | 1 |  |  | 1 |  | 2021-06-15 | 2021-06-15 03:00 |  |  |  | PP-1268 |  | Sprint 9 |  | System | 0
3.2.18 | Show Details | automate tests from the tab | [6 empty] | 2021-06-15 | 2021-06-16 |  |  |  | PP-1269 |  |  |  |  | 0
3.2.18.1 | Contex menu - Graph View |  |  | 4 |  |  | 4 |  | 2021-06-15 | 2021-06-15 12:00 |  |  |  | PP-1270 |  | Sprint 9 |  | Visualization Generation | 0
3.2.18.2 | Context menu - 2D Graph View |  |  | 2 |  |  | 2 |  | 2021-06-15 | 2021-06-15 06:00 |  |  |  | PP-1271 |  | Sprint 9 |  | Visualization Generation | 0
3.2.18.3 | Context menu - Map view |  |  | 2 |  |  | 2 |  | 2021-06-15 | 2021-06-15 06:00 |  |  |  | PP-1272 |  | Sprint 9 |  | Visualization Generation | 0
3.2.18.4 | Show details panel |  |  | 8 |  |  | 8 |  | 2021-06-15 | 2021-06-16 |  |  |  | PP-1273 |  | Sprint 9 |  | Visualization Generation | 0
4 | Unit tests analysis and implementation | [7 empty] | 2021-03-30 15:03 | 2021-06-17 12:00 |  |  |  | PP-683 |  |  |  |  | 0
4.1 | group_nodes method |  | BE: 1.1.12 |  |  | 40 | 40 | Monika | March 30, 2021, 3:03 PM | April 15, 2021, 8:29 AM | 24 | 874 | 28 | PP-574 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/140 | Sprint 4 | Started in Sprint 3 |  | 40
4.2 | calculate_benchmark method |  | BE: 1.11.7 |  |  | 40 | 20 | Monika | 2021-06-15 | 2021-06-17 12:00 |  |  |  | PP-684 |  | Sprint 9 |  |  | 0
4.3 | single packed node on each side in calculate_benchmark method |  | BE: 1.14.11 |  |  | 40 | 10 | Monika | 2021-06-15 | 2021-06-16 06:00 |  |  |  | PP-685 |  | Sprint 9 |  |  | 0
5 | Performance tests | [7 empty] | 2021-06-15 | 2021-07-02 |  |  |  | PP-688 |  |  |  |  | 0
5.1 | Backend | [7 empty] | 2021-06-15 | 2021-06-17 |  |  |  | PP-689 |  | Sprint 9 |  |  | 0
5.1.1 | Implement benchmark fixture | see design |  | 6 | 8 |  | 8 |  | 2021-06-15 | 2021-06-16 |  |  |  | PP-1274 |  | Sprint 9
5.1.2 | Implement measuring method | see design |  | 8 | 8 |  | 8 |  | 2021-06-15 | 2021-06-16 |  |  |  | PP-1275 |  | Sprint 9
5.1.3 | Change existing tests to use measuring method, mark those tests with pytest | see design |  | 16 | 16 |  | 16 |  | 2021-06-15 | 2021-06-17 |  |  |  | PP-1276 |  | Sprint 9
5.2 | Front End | [7 empty] | 2021-06-15 | 2021-07-02 |  |  |  | PP-690 |  | Sprint 9 |  |  | 0
5.2.1 | Implement measuring class | see design |  | 4 | 6 |  | 6 |  | 2021-06-15 | 2021-06-15 18:00 |  |  |  | PP-1277 |  | Sprint 9
5.2.2 | Implement benchmark fixture | see design |  | 6 | 6 |  | 6 |  | 2021-06-15 | 2021-06-15 18:00 |  |  |  | PP-1278 |  | Sprint 9
5.2.3 | Implement test measuring decorator | see design |  | 4 | 6 |  | 6 |  | 2021-06-15 | 2021-06-15 18:00 |  |  |  | PP-1279 |  | Sprint 9
5.2.4 | Implement utils methods | see design |  | 4 | 6 |  | 6 |  | 2021-06-15 | 2021-06-15 18:00 |  |  |  | PP-1280 |  | Sprint 9
5.2.5 | Implement performance test cases | see design | 3.2.4 - 3.2.10 | 16 | 24 |  | 24 |  | 2021-06-29 | 2021-07-02 |  |  |  | PP-1281 |  | Sprint 10
6 | Automation of generating tests result | [7 empty] | 2021-04-07 10:01 | 2021-06-30 |  |  |  | PP-691 |  |  |  |  | 0
6.1 | Set up repository | Set up new project on gitlab |  | 4 | 4 |  | 4 |  | April 7, 2021, 10:01 AM | April 7, 2021, 10:50 AM | 3.5 |  |  | PP-692 | https://gitlab-01.itx.pl/p2-project/tests/p2-automated-tests-calculations | Sprint 4 |  |  | 4
6.2 | Implementing of merger dataset | Implementing class to merge datasets used in p2 |  | 8 | 8 |  | 8 |  | April 7, 2021, 11:21 AM | April 8, 2021, 9:03 AM | 7.67 |  |  | PP-693 |  | Sprint 4 |  |  | 8
6.3 | Implementing of auxiliary functions | Implementing of auxiliary functions for calculation |  | 8 | 8 |  | 8 |  | April 8, 2021, 10:40 AM | April 9, 2021, 8:48 AM | 6 |  |  | PP-694 | https://gitlab-01.itx.pl/p2-project/tests/p2-automated-tests-calculations/-/merge_requests/3 | Sprint 4 |  |  | 8
6.4 | Implementing of methods to generate json | Implementing of methods to generate json |  | 8 | 8 |  | 8 |  | April 9, 2021, 10:05 AM | April 12, 2021, 10:19 AM | 7 |  |  | PP-695 | https://gitlab-01.itx.pl/p2-project/tests/p2-automated-tests-calculations/-/merge_requests/4 | Sprint 4 |  |  | 8
6.5 | Implementing fixture to read expected results from json | Implementing fixture to read expected results from json in the FE tests |  | 8 |  |  | 8 |  | 2021-06-29 | 2021-06-30 |  |  |  | PP-700 |  | Sprint 10 | Removed from sprint 4 - FE dependency |  | 0
6.6 | Implementing integration tests, which check calculation |  |  | 12 |  |  | 12 |  | April 12, 2021, 2:19 PM | April 13, 2021, 9:01 AM | 6 |  |  | PP-1001 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/10/ | Sprint 4 | Added to sprint in Sprint 4 |  | 12
7 | research on reporting of skipped tests in regression suits and keeping a track of them | [7 empty] | 2021-04-20 | 2021-04-21 | 23 |  |  | PP-934 |  | Sprint 5
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions

## Planned availability
Date | People | Hrs | Cummulative |  | People | Hrs | Cummulative |  | People | Hrs | Cummulative
2021-04-12 | 4 | 30 | 30 | Sprint 4 | 4 | 30 | 30 | Sprint 4 | 4 | 30 | 30
2021-04-13 | 4 | 30 | 60 |  | 4 | 30 | 60 |  | 4 | 30 | 60
2021-04-14 | 4 | 30 | 90 |  | 4 | 30 | 90 |  | 4 | 30 | 90
2021-04-15 | 4 | 30 | 120 |  | 4 | 30 | 120 |  | 4 | 30 | 120
2021-04-16 | 4 | 30 | 150 |  | 4 | 30 | 150 |  | 4 | 30 | 150
2021-04-17 | 0 | 0 | 150 |  | 0 | 0 | 150 |  | 0 | 0 | 150
2021-04-18 | 0 | 0 | 150 |  | 0 | 0 | 150 |  | 0 | 0 | 150
2021-04-19 | 5 | 37.5 | 187.5 | sprint 5 | 5 | 37.5 | 187.5 | sprint 5 | 5 | 37.5 | 187.5
2021-04-20 | 5 | 37.5 | 225 |  | 5 | 37.5 | 225 |  | 5 | 37.5 | 225
2021-04-21 | 5 | 37.5 | 262.5 |  | 5 | 37.5 | 262.5 |  | 5 | 37.5 | 262.5
2021-04-22 | 5 | 37.5 | 300 |  | 5 | 37.5 | 300 |  | 5 | 37.5 | 300
2021-04-23 | 5 | 37.5 | 337.5 |  | 5 | 37.5 | 337.5 |  | 5 | 37.5 | 337.5
2021-04-24 | 0 | 0 | 337.5 |  | 0 | 0 | 337.5 |  | 0 | 0 | 337.5
2021-04-25 | 0 | 0 | 337.5 |  | 0 | 0 | 337.5 |  | 0 | 0 | 337.5
2021-04-26 | 5 | 37.5 | 375 |  | 5 | 37.5 | 375 |  | 5 | 37.5 | 375
2021-04-27 | 5 | 37.5 | 412.5 |  | 5 | 37.5 | 412.5 |  | 5 | 37.5 | 412.5
2021-04-28 | 5 | 37.5 | 450 |  | 5 | 37.5 | 450 |  | 5 | 37.5 | 450
2021-04-29 | 5 | 37.5 | 487.5 |  | 5 | 37.5 | 487.5 |  | 5 | 37.5 | 487.5
2021-04-30 | 5 | 37.5 | 525 |  | 5 | 37.5 | 525 |  | 5 | 37.5 | 525
2021-05-01 | 0 | 0 | 525 |  | 0 | 0 | 525 |  | 0 | 0 | 525
2021-05-02 | 0 | 0 | 525 |  | 0 | 0 | 525 |  | 0 | 0 | 525
2021-05-03 | 0 | 0 | 525 | sprint 6 | 0 | 0 | 525 | sprint 6 | 0 | 0 | 525
2021-05-04 | 5 | 37.5 | 562.5 |  | 5 | 37.5 | 562.5 |  | 5 | 37.5 | 562.5
2021-05-05 | 5 | 37.5 | 600 |  | 5 | 37.5 | 600 |  | 5 | 37.5 | 600
2021-05-06 | 5 | 37.5 | 637.5 |  | 5 | 37.5 | 637.5 |  | 5 | 37.5 | 637.5
2021-05-07 | 5 | 37.5 | 675 |  | 5 | 37.5 | 675 |  | 5 | 37.5 | 675
2021-05-08 | 0 | 0 | 675 |  | 0 | 0 | 675 |  | 0 | 0 | 675
2021-05-09 | 0 | 0 | 675 |  | 0 | 0 | 675 |  | 0 | 0 | 675
2021-05-10 | 5 | 37.5 | 712.5 |  | 5 | 37.5 | 712.5 |  | 5 | 37.5 | 712.5
2021-05-11 | 5 | 37.5 | 750 |  | 5 | 37.5 | 750 |  | 5 | 37.5 | 750
2021-05-12 | 5 | 37.5 | 787.5 |  | 5 | 37.5 | 787.5 |  | 5 | 37.5 | 787.5
2021-05-13 | 5 | 37.5 | 825 |  | 5 | 37.5 | 825 |  | 5 | 37.5 | 825
2021-05-14 | 5 | 37.5 | 862.5 |  | 5 | 37.5 | 862.5 |  | 5 | 37.5 | 862.5
2021-05-15 | 0 | 0 | 862.5 |  | 0 | 0 | 862.5 |  | 0 | 0 | 862.5
2021-05-16 | 0 | 0 | 862.5 |  | 0 | 0 | 862.5 |  | 0 | 0 | 862.5
2021-05-17 | 3 | 22.5 | 885 | sprint 7 | 5 | 37.5 | 900 | sprint 7 | 4 | 30 | 892.5
2021-05-18 | 3 | 22.5 | 907.5 |  | 5 | 37.5 | 937.5 |  | 4 | 30 | 922.5
2021-05-19 | 3 | 22.5 | 930 |  | 5 | 37.5 | 975 |  | 4 | 30 | 952.5
2021-05-20 | 3 | 22.5 | 952.5 |  | 5 | 37.5 | 1012.5 |  | 4 | 30 | 982.5
2021-05-21 | 3 | 22.5 | 975 |  | 5 | 37.5 | 1050 |  | 4 | 30 | 1012.5
2021-05-22 | 0 | 0 | 975 |  | 0 | 0 | 1050 |  | 0 | 0 | 1012.5
2021-05-23 | 0 | 0 | 975 |  | 0 | 0 | 1050 |  | 0 | 0 | 1012.5
2021-05-24 | 3 | 22.5 | 997.5 |  | 5 | 37.5 | 1087.5 |  | 4 | 30 | 1042.5
2021-05-25 | 3 | 22.5 | 1020 |  | 5 | 37.5 | 1125 |  | 4 | 30 | 1072.5
2021-05-26 | 3 | 22.5 | 1042.5 |  | 5 | 37.5 | 1162.5 |  | 4 | 30 | 1102.5
2021-05-27 | 3 | 22.5 | 1065 |  | 5 | 37.5 | 1200 | Minimal plan finish date | 4 | 30 | 1132.5
2021-05-28 | 0 | 0 | 1065 |  | 5 | 37.5 | 1237.5 |  | 4 | 30 | 1162.5
2021-05-29 | 0 | 0 | 1065 |  | 0 | 0 | 1237.5 |  | 0 | 0 | 1162.5
2021-05-30 | 3 | 22.5 | 1087.5 |  | 5 | 37.5 | 1275 |  | 4 | 30 | 1192.5
2021-05-31 | 3 | 22.5 | 1110 |  | 5 | 37.5 | 1312.5 |  | 4 | 30 | 1222.5 | Minimal plan finish date
2021-06-01 | 3 | 22.5 | 1132.5 |  | 5 | 37.5 | 1350 |  | 4 | 30 | 1252.5
2021-06-02 | 3 | 22.5 | 1155 |  | 5 | 37.5 | 1387.5 | Faster plan finish date | 4 | 30 | 1282.5
2021-06-03 | 3 | 22.5 | 1177.5 |  | 5 | 37.5 | 1425 |  | 4 | 30 | 1312.5
2021-06-04 | 0 | 0 | 1177.5 |  | 0 | 0 | 1425 |  | 0 | 0 | 1312.5
2021-06-05 | 0 | 0 | 1177.5 |  | 0 | 0 | 1425 |  | 0 | 0 | 1312.5
2021-06-06 | 3 | 22.5 | 1200 | Minimal plan finish date | 5 | 37.5 | 1462.5 |  | 4 | 30 | 1342.5
2021-06-07 | 3 | 22.5 | 1222.5 |  | 5 | 37.5 | 1500 |  | 4 | 30 | 1372.5
2021-06-08 | 3 | 22.5 | 1245 |  | 5 | 37.5 | 1537.5 |  | 4 | 30 | 1402.5 | Faster plan finish date
2021-06-09 | 3 | 22.5 | 1267.5 |  | 5 | 37.5 | 1575 |  | 4 | 30 | 1432.5
2021-06-10 | 3 | 22.5 | 1290 |  | 5 | 37.5 | 1612.5 |  | 4 | 30 | 1462.5
2021-06-11 | 0 | 0 | 1290 |  | 0 | 0 | 1612.5 |  | 0 | 0 | 1462.5
2021-06-12 | 0 | 0 | 1290 |  | 0 | 0 | 1612.5 |  | 0 | 0 | 1462.5
2021-06-13 | 3 | 22.5 | 1312.5 |  | 5 | 37.5 | 1650 |  | 4 | 30 | 1492.5
2021-06-14 | 3 | 22.5 | 1335 |  | 5 | 37.5 | 1687.5 |  | 4 | 30 | 1522.5
2021-06-15 | 3 | 22.5 | 1357.5 | Faster plan finish date | 5 | 37.5 | 1725 |  | 4 | 30 | 1552.5
2021-06-16 | 3 | 22.5 | 1380 |  | 5 | 37.5 | 1762.5 |  | 4 | 30 | 1582.5
2021-06-17 | 3 | 22.5 | 1402.5 |  | 5 | 37.5 | 1800 |  | 4 | 30 | 1612.5
2021-06-18 | 0 | 0 | 1402.5 |  | 0 | 0 | 1800 |  | 0 | 0 | 1612.5
2021-06-19 | 0 | 0 | 1402.5 |  | 0 | 0 | 1800 |  | 0 | 0 | 1612.5
2021-06-20 | 3 | 22.5 | 1425 |  | 5 | 37.5 | 1837.5 | Current plan finish date | 0 | 0 | 1612.5
2021-06-21 | 3 | 22.5 | 1447.5 |  | 5 | 37.5 | 1875 |  | 0 | 0 | 1612.5
2021-06-22 | 3 | 22.5 | 1470 |  | 5 | 37.5 | 1912.5 |  | 4 | 30 | 1642.5
2021-06-23 | 3 | 22.5 | 1492.5 |  | 5 | 37.5 | 1950 |  | 4 | 30 | 1672.5
2021-06-24 | 3 | 22.5 | 1515 |  | 5 | 37.5 | 1987.5 |  | 4 | 30 | 1702.5
2021-06-25 | 0 | 0 | 1515 |  | 0 | 0 | 1987.5 |  | 4 | 30 | 1732.5
2021-06-26 | 0 | 0 | 1515 |  | 0 | 0 | 1987.5 |  | 4 | 30 | 1762.5
2021-06-27 | 3 | 22.5 | 1537.5 |  | 5 | 37.5 | 2025 |  | 0 | 0 | 1762.5
2021-06-28 | 3 | 22.5 | 1560 |  | 5 | 37.5 | 2062.5 |  | 0 | 0 | 1762.5
2021-06-29 | 3 | 22.5 | 1582.5 |  | 5 | 37.5 | 2100 |  | 0 | 0 | 1762.5
2021-06-30 | 3 | 22.5 | 1605 |  | 5 | 37.5 | 2137.5 |  | 0 | 0 | 1762.5
2021-07-01 | 3 | 22.5 | 1627.5 |  | 5 | 37.5 | 2175 |  | 4 | 30 | 1792.5
2021-07-02 | 0 | 0 | 1627.5 |  | 0 | 0 | 2175 |  | 4 | 30 | 1822.5
2021-07-03 | 0 | 0 | 1627.5 |  | 0 | 0 | 2175 |  | 4 | 30 | 1852.5
2021-07-04 | 3 | 22.5 | 1650 |  | 5 | 37.5 | 2212.5 |  | 4 | 30 | 1882.5 | Current plan finish date
2021-07-05 | 3 | 22.5 | 1672.5 |  | 5 | 37.5 | 2250 |  | 4 | 30 | 1912.5
2021-07-06 | 3 | 22.5 | 1695 |  | 5 | 37.5 | 2287.5 |  | 0 | 0 | 1912.5
2021-07-07 | 3 | 22.5 | 1717.5 |  | 5 | 37.5 | 2325 |  | 0 | 0 | 1912.5
2021-07-08 | 3 | 22.5 | 1740 |  | 5 | 37.5 | 2362.5 |  | 0 | 0 | 1912.5
2021-07-09 | 0 | 0 | 1740 |  | 0 | 0 | 2362.5 |  | 0 | 0 | 1912.5
2021-07-10 | 0 | 0 | 1740 |  | 0 | 0 | 2362.5 |  | 4 | 30 | 1942.5
2021-07-11 | 3 | 22.5 | 1762.5 |  | 5 | 37.5 | 2400 |  | 4 | 30 | 1972.5
2021-07-12 | 3 | 22.5 | 1785 |  | 5 | 37.5 | 2437.5 |  | 4 | 30 | 2002.5
2021-07-13 | 3 | 22.5 | 1807.5 |  | 5 | 37.5 | 2475 |  | 4 | 30 | 2032.5
2021-07-14 | 3 | 22.5 | 1830 | Current plan finish date | 5 | 37.5 | 2512.5 |  | 4 | 30 | 2062.5
2021-07-15 | 3 | 22.5 | 1852.5 |  | 5 | 37.5 | 2550 |  | 0 | 0 | 2062.5
2021-07-16 | 0 | 0 | 1852.5 |  | 0 | 0 | 2550 |  | 0 | 0 | 2062.5
2021-07-17 | 0 | 0 | 1852.5 |  | 0 | 0 | 2550 |  | 0 | 0 | 2062.5
2021-07-18 | 3 | 22.5 | 1875 |  | 5 | 37.5 | 2587.5 |  | 0 | 0 | 2062.5
2021-07-19 | 3 | 22.5 | 1897.5 |  | 5 | 37.5 | 2625 |  | 4 | 30 | 2092.5
2021-07-20 | 3 | 22.5 | 1920 |  | 5 | 37.5 | 2662.5 |  | 4 | 30 | 2122.5
2021-07-21 | 3 | 22.5 | 1942.5 |  | 5 | 37.5 | 2700 |  | 4 | 30 | 2152.5
2021-07-22 | 3 | 22.5 | 1965 |  | 5 | 37.5 | 2737.5 |  | 4 | 30 | 2182.5
2021-07-23 | 0 | 0 | 1965 |  | 0 | 0 | 2737.5 |  | 4 | 30 | 2212.5
2021-07-24 | 0 | 0 | 1965 |  | 0 | 0 | 2737.5 |  | 0 | 0 | 2212.5
2021-07-25 | 3 | 22.5 | 1987.5 |  | 5 | 37.5 | 2775 |  | 0 | 0 | 2212.5
2021-07-26 | 3 | 22.5 | 2010 |  | 5 | 37.5 | 2812.5 |  | 0 | 0 | 2212.5
2021-07-27 | 3 | 22.5 | 2032.5 |  | 5 | 37.5 | 2850 |  | 0 | 0 | 2212.5
2021-07-28 | 3 | 22.5 | 2055 |  | 5 | 37.5 | 2887.5 |  | 4 | 30 | 2242.5
2021-07-29 | 3 | 22.5 | 2077.5 |  | 5 | 37.5 | 2925 |  | 4 | 30 | 2272.5
2021-07-30 | 0 | 0 | 2077.5 |  | 0 | 0 | 2925 |  | 4 | 30 | 2302.5
2021-07-31 | 0 | 0 | 2077.5 |  | 0 | 0 | 2925 |  | 4 | 30 | 2332.5
2021-08-01 | 3 | 22.5 | 2100 |  | 5 | 37.5 | 2962.5 |  | 4 | 30 | 2362.5
2021-08-02 | 3 | 22.5 | 2122.5 |  | 5 | 37.5 | 3000 |  | 0 | 0 | 2362.5
2021-08-03 | 3 | 22.5 | 2145 |  | 5 | 37.5 | 3037.5 |  | 0 | 0 | 2362.5
2021-08-04 | 3 | 22.5 | 2167.5 |  | 5 | 37.5 | 3075 |  | 0 | 0 | 2362.5
2021-08-05 | 3 | 22.5 | 2190 |  | 5 | 37.5 | 3112.5 |  | 0 | 0 | 2362.5
2021-08-06 | 0 | 0 | 2190 |  | 0 | 0 | 3112.5 |  | 4 | 30 | 2392.5
2021-08-07 | 0 | 0 | 2190 |  | 0 | 0 | 3112.5 |  | 4 | 30 | 2422.5
2021-08-08 | 3 | 22.5 | 2212.5 |  | 5 | 37.5 | 3150 |  | 4 | 30 | 2452.5
2021-08-09 | 3 | 22.5 | 2235 |  | 5 | 37.5 | 3187.5 |  | 4 | 30 | 2482.5
2021-08-10 | 3 | 22.5 | 2257.5 |  | 5 | 37.5 | 3225 |  | 4 | 30 | 2512.5
2021-08-11 | 3 | 22.5 | 2280 |  | 5 | 37.5 | 3262.5 |  | 0 | 0 | 2512.5
2021-08-12 | 3 | 22.5 | 2302.5 |  | 5 | 37.5 | 3300 |  | 0 | 0 | 2512.5
2021-08-13 | 0 | 0 | 2302.5 |  | 0 | 0 | 3300 |  | 0 | 0 | 2512.5
2021-08-14 | 0 | 0 | 2302.5 |  | 0 | 0 | 3300 |  | 0 | 0 | 2512.5
2021-08-15 | 3 | 22.5 | 2325 |  | 5 | 37.5 | 3337.5 |  | 4 | 30 | 2542.5
2021-08-16 | 3 | 22.5 | 2347.5 |  | 5 | 37.5 | 3375 |  | 4 | 30 | 2572.5
2021-08-17 | 3 | 22.5 | 2370 |  | 5 | 37.5 | 3412.5 |  | 4 | 30 | 2602.5
2021-08-18 | 3 | 22.5 | 2392.5 |  | 5 | 37.5 | 3450 |  | 4 | 30 | 2632.5
2021-08-19 | 3 | 22.5 | 2415 |  | 5 | 37.5 | 3487.5 |  | 4 | 30 | 2662.5
2021-08-20 | 0 | 0 | 2415 |  | 0 | 0 | 3487.5 |  | 0 | 0 | 2662.5
2021-08-21 | 0 | 0 | 2415 |  | 0 | 0 | 3487.5 |  | 0 | 0 | 2662.5
2021-08-22 | 3 | 22.5 | 2437.5 |  | 5 | 37.5 | 3525 |  | 0 | 0 | 2662.5
2021-08-23 | 3 | 22.5 | 2460 |  | 5 | 37.5 | 3562.5 |  | 0 | 0 | 2662.5
2021-08-24 | 3 | 22.5 | 2482.5 |  | 5 | 37.5 | 3600 |  | 4 | 30 | 2692.5
2021-08-25 | 3 | 22.5 | 2505 |  | 5 | 37.5 | 3637.5 |  | 4 | 30 | 2722.5
2021-08-26 | 3 | 22.5 | 2527.5 |  | 5 | 37.5 | 3675 |  | 4 | 30 | 2752.5
2021-08-27 | 0 | 0 | 2527.5 |  | 0 | 0 | 3675 |  | 4 | 30 | 2782.5
2021-08-28 | 0 | 0 | 2527.5 |  | 0 | 0 | 3675 |  | 4 | 30 | 2812.5
|  | 0 |  |  |  | 0 | 3675 |  | 0 | 0 | 2812.5
|  | 0 |  |  |  | 0 | 3675 |  | 0 | 0 | 2812.5
|  | 0 | [8 empty] | 2812.5
|  | 0 | [8 empty] | 2812.5
|  | 0 | [8 empty] | 2812.5
|  | 0 | [8 empty] | 2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5
2812.5

## Sheet4
| current plan | faster plan | minimal plan
estimated hours | 1418 | 1000 | 804
description | That's the original approach: - First the regression library is reworked and imrpoved according to the propositions from this document - Then, the regression library is automated in our new selenium suite based on pytest | Original approach with trade-offs: - We still do some rework on the regression library (e.g. consitent naming convention, mapping functionalities to the feature pruning document) but don't spend much time analiyzing whether a given functionality is covered well enough and adding tests to it. - We'll proceed with test automation similar to the first approach | Minimal approach - Abandon current regression library document (stop updating it) - Automate already existing tests with only the necessary updates and modifications (e.g. changes in labels tests, consistent naming convention, mapping functionalities to the pruning document), create extensive documentation of the automated test to generate reports similar to the ones already existing for the integration tests library link
pros | - All test scenarios would be mapped to p2 feature pruninng functionalities - The library structure would be more clean and related to p2 feature pruning document - We'll make that all functionalities from the pruning document are covered well | - Less time consuming approach, we could get the automated test suite up-and-running sooner - Test scenarios from the regression library would be mapped to the feature pruning document and we'll keep more detailed stats about the entire suite | - Faster to finish since we won't spend time working on the regression library document - Easy to maintain mapping between the library and automated tests since everyting would be stored in one place
cons | Reworking the regression library according to the the document will take aroun 600 hours to finish | - Quality of the existing regression test scenarios would only be slightly improved | - Quality of the existing regression test scenarios would be only slightly improved - Reports generated from the selenium tests suite are somewhat less formatted than those created in the google sheets by hand - In order to make changes in test cases documentation one would need to change it from the selenium tests repository
| Tab/category | Regression library rework | Automation | Total
Authentication & Authorization
| Authentication Module | 4 | 6 | 10
| Multi-tenancy | 4 | 4 | 8
| Password requirements | 2 | 2 | 4
| Change password | 4 | 8 | 12
| Email Notifications & New email templates | 4 | 8 | 12
Dataset Upload & Management
| Dataset upload | 4 | 6 | 10
| Dataset permissions | 4 | 4 | 8
| View datasets details | 4 | 5 | 9
| Delete Dataset | 2 | 3 | 5
| Export datasets statistics details as Excel file | 4 | 6 | 10
| Statistics preview of a dataset by entity type | 2 | 3 | 5
View Dashboard
| View Creation | 6 | 6 | 12
| View Management (delete, search, etc) + search by dataset + save view/new view | 8 | 10 | 18
| View duplication | 2 | 2 | 4
| View name editing | 2 | 2 | 4
Location Filter
| Location filter by states & FIPS & CBSA [2nd and 3rd panel] | 10 | 16 | 26
| Location filter by Radius map [2nd and 3rd panel] | 10 | 16 | 26
| Location filter switch between grayscale and terrain | 2 | 2 | 4
| Location filter applies to | 8 | 8 | 16
| Tooltips for location filters | 2 | 4 | 6
| Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features e.g. scrolling/zooming map] | 4 | 8 | 12
| Pagination of the Entity, Service Lines,..Filters | 2 | 4 | 6
| Filter search | 4 | 4 | 8
| Clear filters feature | 2 | 2 | 4
| Filters breadcrumb (tree structures) | 6 | 8 | 14
| Filters breadcrumb navigation to the selected layer | 2 | 4 | 6
Entity Filter
| Entity-post acute type filter & Entity-Hospital filter [2nd and 3rd panel] | 8 | 16 | 24
| Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] | 4 | 8 | 12
| Pagination of the Entity, Service Lines,..Filters | 4 | 4 | 8
| Filter search | 4 | 4 | 8
| Tooltips when hovering over filters | 2 | 4 | 6
| Clear filters feature | 2 | 2 | 4
| Filters breadcrumb (tree structures) for Service Line and Entity filters | 6 | 6 | 12
| Filters breadcrumb navigation to the selected layer | 2 | 4 | 6
Service Line filter
| Service line filter [SL, Episode, DRG levels - 2nd and 3rd panel] | 10 | 16 | 26
| Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] | 2 | 8 | 10
| Pagination of the Entity, Service Lines,..Filters | 4 | 4 | 8
| Filter search | 4 | 4 | 8
| Tooltips when hovering over filters | 2 | 4 | 6
| Clear filters feature | 2 | 2 | 4
| Filters breadcrumb (tree structures) for Service Line and Entity filters | 6 | 6 | 12
| Filters breadcrumb navigation to the selected layer | 2 | 4 | 6
LOB Filter
| LOB filter [2nd and 3rd panel] | 4 | 8 | 12
| Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] | 2 | 4 | 6
| Filter search | 2 | 2 | 4
| Tooltips when hovering over filters | 2 | 2 | 4
| Clear filters feature | 2 | 2 | 4
Graph View
| Loading the default view/report | 1 | 2 | 3
| Market share Graph + filters [check calculations results here] | 20 | 20 | 40
| Benchmark Graph + filters [general cases, calculations checked in benchmark tab] | 16 | 16 | 32
| Multi-layer Graph view (all navigation types checked in here) | 10 | 16 | 26
| Graph view maximum number of nodes display | 6 | 6 | 12
| Highlight a node for re-calculation | 6 | 6 | 12
| Orders settings | 4 | 8 | 12
| Legend for Graph [general tests only, check calculations along with graph + filters category, dynamic legend with navigation/multi-layer graph] | 4 | 4 | 8
| Custom error messages related to filter choice | 4 | 4 | 8
| Exit the view and warning popups | 1 | 2 | 3
| Navigation menu (switching between view types, market share and benchmark modes) | 2 | 2 | 4
Map View
| Market share Map + filters [check calculations results here] | 20 | 20 | 40
| Benchmark view Map + filters [general cases, calculations checked in benchmark tab] | 16 | 16 | 32
| Map view navigation | 6 | 16 | 22
| Opacity slider for map | 2 | 4 | 6
| Legend for Map [general tests only, check calculations along with graph + filters category] + dynamic legend | 4 | 4 | 8
| Custom error messages related to filter choice | 4 | 4 | 8
| Exit the view and warning popups | 1 | 2 | 3
2D Graph View
| 2D graph view + filters [general cases, calculations checked in benchmark tab] | 16 | 20 | 36
| 2D Navigation | 8 | 16 | 24
| Legend for 2D [general tests only, check calculations along with graph + filters category] + dynamic legend | 4 | 4 | 8
| Custom error messages related to filter choice | 4 | 4 | 8
| Exit the view and warning popups | 1 | 2 | 3
Benchmark Settings and calculations on Graph
| Benchmarking default settings for Graph and benchmark calculation | 1 | 2 | 3
| Benchmarking Measures | 6 | 8 | 14
| Benchmark standard level of aggregations | 6 | 8 | 14
| Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) | 4 | 4 | 8
| Benchmark metrics by percentile & average | 4 | 6 | 10
| Benchmark time range | 6 | 8 | 14
| Benchmark to LOB settings | 4 | 4 | 8
| Search function on benchmark settings | 4 | 6 | 10
| Benchmark calculations (all filters + various benchmark settings) | 24 | 24 | 48
Benchmark Settings and calculations on Map
| Benchmarking default settings for Map and benchmark calculation | 1 | 2 | 3
| Benchmarking Measures | 6 | 8 | 14
| Benchmark standard level of aggregations | 6 | 8 | 14
| Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) | 4 | 4 | 8
| Benchmark metrics by percentile & average | 4 | 6 | 10
| Benchmark time range | 6 | 8 | 14
| Benchmark to LOB settings | 4 | 4 | 8
| Search function on benchmark settings | 4 | 6 | 10
| Benchmark calculations (all filters + various benchmark settings) | 24 | 24 | 48
Benchmark Settings and calculations on 2D
| Benchmarking default settings for 2D and benchmark calculation | 1 | 2 | 3
| Benchmarking Measures | 6 | 8 | 14
| Benchmark standard level of aggregations | 6 | 8 | 14
| Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) | 4 | 4 | 8
| Benchmark metrics by percentile & average | 4 | 6 | 10
| Benchmark time range | 6 | 8 | 14
| Benchmark to LOB settings | 4 | 4 | 8
| Search function on benchmark settings | 4 | 6 | 10
| Benchmark calculations (all filters + various benchmark settings) | 24 | 24 | 48
Label settings
| Labels on Graph | 12 | 16 | 28
| Labels on Map | 6 | 8 | 14
| Labels on 2D Graph | 6 | 8 | 14
LDS suppression rule-11 (after implementation add LDS test cases to check CC11 )
| LDS suppression rule-11 | 38 | 44 | 82
| LDS rule-11 in screen floating message | 2 | 4 | 6
Save or export Visualization
| Export as PNG | 4 | 16 | 20
| Export the View as Excel | 8 | 16 | 24
System
| Inactivity countdown timer | 2 | 1 | 3
| View user manual | 1 | 1 | 2
| Customer support contact information icons | 1 | 1 | 2
| Versioning and copyright maintenance | 1 | 0 | 1
Show Details
| Contex menu - Graph View | 2 | 4 | 6
| Context menu - 2D Graph View | 1 | 2 | 3
| Context menu - Map view | 1 | 2 | 3
| Show details panel | 8 | 8 | 16
| Summary | 614 | 804 | 1418