## Tasks
WBS | Name | Description | Depends on | Estimated work time [h] |  |  |  | Assignee | Actual work time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment | Category | Version
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Setup | [12 empty] | PP-1825
1.1 | Setup repository | - set up new project on gitlab - add necessary directories and files, like settings.py, config, requirements etc. |  | 5 | 8 |  | 5 | Paulina | [5 empty] | PP-1826
1.2 | Dockerization | - add dockerfile - add docker-compose |  | 8 | 8 |  | 8 | [6 empty] | PP-1827
1.3 | Add bash script to run tests | - add bash script to run tests on pipeline |  | 4 | 4 |  | 4 | [6 empty] | PP-1828
1.4 | Implement fixtures and methods | - login_as_admin (scope function) -> fixture that creates client with admin permissions - login_as_user_with_role... (scope function) -> fixture that creates client with specific role permissions - register_dataset (scope function) -> fixture that adds a public dataset to DM before test and removes it from DM after test (yield - datasetID) - create_token() -> method to generate access token for specific user - get_user_id_from_token() -> method to decode JWT access token and derive user id from it |  | 8 | 10 |  | 8 | [6 empty] | PP-1829
2 | Integration tests of Dataset Manager | [12 empty] | PP-1830
NOTE: - for every positive test check response['statusInfo']['status'] == "OK", ['errorMessage'] == "", ['errorClass'] == "" - for every negative test check response['statusInfo']['status'] == "ERROR", ['errorMessage'] == "<error message>", ['errorClass'] == "<type of error>"
2.1 | Test add_user() endpoint | - add users with all posible roles (read, write, properties, share, users, admin) -> check using other endpoints if the right role was added and the user has access to those endpoints - add user with list of multiple roles -> check using other endpoints if the right role was added and the user has access to those endpoints - add user with nonexistent role - add user with no roles (empty list) - add already existing user -> check for error message (UserException) - add user as user with no permission to add users (roles: read, write, properties, share) -> check for error message (AccessException) |  | 6 | 8 |  | 6 | [6 empty] | PP-1831
2.2 | Test register() endpoint | - register dataset as user with permission to register (roles: write, admin) -> check with get() if not automatically shared to this user, next: share with this user and check with get() if the dataset was registered, check returned fields (response['data']['dataset']) - register dataset with missing field (fields: storage_dataset_id, address, connector_type, storage_type, type) - register dataset without properties: name - register as user with no permission to register (roles: read, properties, share, users) -> check for error message (AccessException) |  | 5 | 6 |  | 5 | [6 empty] | PP-1832
2.3 | Test get() endpoint | - get() datasets using empty filter -> preconditions: at least one of the dataset must be shared with the user and at least one dataset must be not shared with the user, then: check if datasets are returned, check if datasets that were not shared with the user are not returned - check if #public datasets are returned -> preconditions: share dataset as public, then: check if dataset in get response - query using available operators (eq, ne, ls, le, gt, ge) + "and" and "or" -> preconditions: at least two datasets have to be shared with user or as public |  | 7 | 8 |  | 7 | [6 empty] | PP-1833
2.4 | Test share() endpoint | - share with single user, group of users, as public -> preconditions: make sure the dataset is not already shared with the user, then: login as the user with which the dataset was shared with and check with get() if dataset is returned for the user(s) - share using different permissions combinations (read, read + write, write) - share a nonexistent dataset (datasetID that doesnt exist in DM), deleted datatset -> check for error message (DatasetException) - share with nonexistent user/group id -> check if new user was added and has access to dataset with specified in share() permissions - share using invalid/not providing application_id - share a dataset with thes user that was already shared with - share providing null dataset id - share as user with no permission to share (roles: read, write, properties) -> check for error message (AccessException) |  | 7 | 8 |  | 7 | [6 empty] | PP-1834
2.5 | Test unshare() endpoint | - unshare from single user, group of users, from public -> preconditions: make sure the dataset is already shared with the user/as public, then: login as the user with which the dataset was unshared from and check with get() if dataset is no longer returned for the user(s) - unshare a nonexistent dataset (datsetID that doesnt exist in DM), deleted datatset -> check for error message (DatasetException) - unshare from nonexistent user/group id - unshare using invalid/not providing application_id - unshare from user/group id that the dataset that wasnt shared with - unshare providing null dataset id - unshare as user with no permission to unshare (roles: read, write, properties) -> check for error message (AccessException) |  | 7 | 8 |  | 7 | [6 empty] | PP-1835
2.6 | Test update_properties() endpoint | - update dataset name (to: valid, null) -> check with get() - update properties using invalid json -> check for error message (JsonException) - update_properties() of nonexistent dataset (datasetID that doesnt exist in DM), deleted datatset -> check for error message (DatasetException) - update_properties() providing null dataset id - update_properties() as user with no permission to update properties (roles: read, write, share, users) -> check for error message (AccessException) |  | 5 | 6 |  | 5 | [6 empty] | PP-1836
2.7 | Test remove() endpoint | - remove existing dataset -> register(), share() with user, remove(), check with get() using the same user - remove public dataset -> register(), share() as public, remove(), check with get() if removed - remove nonexistent dataset (nonexistent datasetID), already removed dataset -> check for error message (DatasetException) - remove as user with no permission to remove (roles: read, write, properties, share, users) -> check for error message (AccessException) |  | 5 | 6 |  | 5 | [6 empty] | PP-1837
2.8 | Test run_queries() endpoint | - execute multiple queries in the same query (ex. get, share) |  | 5 | 6 |  | 5 | [6 empty] | PP-1838
3 | Test suite features | [12 empty] | PP-1839
3.1 | Add README |  |  | 2 | 2 |  | 2 | [6 empty] | PP-1840
|  |  | SUMA: | 74 | 88 | 0 | 74