## Description
Design document: | Modivcare P1 design
Jira project: | MC
Jira label: | backend
Number of tasks: | 32
Number of reported bugs: | 0
Total planned development worktime [h]: | 428 | 0
Planned development worktime of finished tasks [h]: | 0 | 0
Current worktime spent [h]: | 0 | 0
Planned time to finish project [h]: | 428 | 0
Planned availability (until 28 May) [h]: |  | 0
Project completeness based on planned worktime [%]: | 0 | 0
Current worktime vs planned worktime [%]: | #DIV/0! | 0 | > 100% - delay; < 100% - ahead
Last update | Jun 10, 2021 16:36:13
Number of updated tasks (during last update) | 1

## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  |  | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment | Category | Version
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Administration scripts | [12 empty] | MC-183 |  |  |  |  | MVP
1.1 | Create user account |  |  | 4 | 4 |  | 4 | [6 empty] | MC-184 |  |  |  |  | MVP
1.2 | Set user password |  | 1.1 | 4 | 4 |  | 4 | [6 empty] | MC-185 |  |  |  |  | MVP
1.3 | Deactivate user account |  | 1.1 | 4 | 4 |  | 4 | [6 empty] | MC-186 |  |  |  |  | MVP
1.4 | Import states, counties, metro areas, regions dictionaries |  |  | 24 | 30 |  | 24 | [6 empty] | MC-187 |  |  |  |  | MVP
2 | Application Deployment |  |  | 40 | [9 empty] | MC-188 |  |  |  |  | MVP
2.1 | Build script | [12 empty] | MC-189 |  |  |  |  | MVP
2.2 | Local development | [12 empty] | MC-190 |  |  |  |  | MVP
2.3 | Setup target environments | [12 empty] | MC-191 |  |  |  |  | MVP
2.4 | Setup CI | [12 empty] | MC-192 |  |  |  |  | MVP
2.5 | Deploy module at target environment | [12 empty] | MC-193 |  |  |  |  | MVP
2.6 | Project setup on gitlab |  |  | 16 |  | 2 | 16 | [6 empty] | MC-194 |  |  |  |  | MVP
2.7 | User and technical Documentation |  |  | 40 |  | 40 | 40 | [6 empty] | MC-195 |  |  |  |  | MVP
2.8 | Tests (integration, regression, smoke) | Will be analyzed separately by QA team lead |  | 300 | [9 empty] | MC-196 |  |  |  |  | MVP
3 | Authorization Module | auth0 integration, session token validity check, getting user information and roles (regular, admin) local development mode without auth0 | 4 | 20 | 24 |  | 20 | [6 empty] | MC-197 |  |  |  |  | MVP
4 | Auth0 configuration | auth0 configuration files and scripts for initial application setup |  | 4 | 4 |  | 4 | [6 empty] | MC-198 |  |  |  |  | MVP
5 | Postgres setup |  |  | 2 | 2 |  | 2 | [6 empty] | MC-199 |  |  |  |  | MVP
6 | Backend Configuration | dynamic configuration class and variables stored at database static configuration in files | 5 | 2 | 2 |  | 2 | [6 empty] | MC-200 |  |  |  |  | MVP
7 | Backend module | [12 empty] | MC-201 |  |  |  |  | MVP
7.1 | Geo common module | Common GraphQL schema types and helper functions |  | 8 | 8 |  | 8 | [6 empty] | MC-202 |  |  |  |  | MVP
7.2 | Snowflake setup and integration | snowflake setup, snowflake/local SQL db connector |  | 4 | 8 |  | 4 | [6 empty] | MC-203 |  |  |  |  | MVP
7.3 | dataset manager setup | datasetmanager setup and integration |  | 8 | 8 |  | 8 | [6 empty] | MC-204 |  |  |  |  | MVP
7.4 | Illness burden module | getting area data endpoint: dataset selection and filtering, ilness burden categories mapping, geo area data aggregation, decile calculation, top 3 categories getting combined areas data endpoint: like previous one but couple of areas joined | 3, 7.1, 7.2, 7.3 | 60 | 60 |  | 60 | [6 empty] | MC-205 |  |  |  |  | MVP
7.5 | Social needs module | Reuse code from Illness Burden Module getting area data endpoint: dataset selection and filtering, geo area data aggregation, decile calculation, top N categories getting combined areas data endpoint: like previous one but couple of areas joined | 3, 7.1, 7.2, 7.3 | 20 | 30 |  | 20 | [6 empty] | MC-206 |  |  |  |  | MVP
7.6 | Services presence module | Reuse code from Illness Burden Module getting area data endpoint: dataset selection and filtering, geo area data aggregation, decile calculation, top N categories getting combined areas data endpoint: like previous one but couple of areas joined | 3, 7.1, 7.2, 7.3 | 20 | 30 |  | 20 | [6 empty] | MC-207 |  |  |  |  | MVP
7.7 | Help Seeker Measures module | Reuse code from Illness Burden Module getting area data endpoint: dataset selection and filtering, geo area data aggregation, decile calculation, top N categories getting combined areas data endpoint: like previous one but couple of areas joined | 3, 7.1, 7.2, 7.3 | 20 | 30 |  | 20 | [6 empty] | MC-208 |  |  |  |  | MVP
8 | Data preprocessing pipelines | [12 empty] | MC-209 |  |  |  |  | MVP
8.1 | Geo crosswalks pipeline | Fill geo crosswalks tables on csv files changes us_counties us_states us_regions |  | 8 | 12 |  | 8 | [6 empty] | MC-210 |  |  |  |  | MVP
8.2 | Illness Burden pipeline | new job in o2-grouper, for last year of claims data identify unique patients, select elixhauser and charslon component conditions using ICD10 diagnoses, aggregate at county level , publish output to snowflake |  | 60 | 60 |  | 60 | [6 empty] | MC-211 |  |  |  |  | MVP
8.3 | Social Needs pipeline | process separate census files at county level published once a year to get: food, transportation, financial, housing, composite index publish output to snowflake |  | 40 | 40 |  | 40 | [6 empty] | MC-212 |  |  |  |  | MVP
8.4 | Services Presence pipeline | new AWS Lambda triggered pipeline, process MOdivcare input files to get rides and social services scores, aggregate by county, publish to snowflake |  | 40 | 40 |  | 40 | [6 empty] | MC-213 |  |  |  |  | MVP
8.5 | Help Seeker pipeline | Once a month fetch google trends data for 4 categories phrases. Use last year averages, publish to snowflake |  | 20 | 20 |  | 20 | [6 empty] | MC-214 |  |  |  |  | MVP
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions

## Planned availability
Date | Devs | Hrs | Cummulative
|  | 0 | 0 | Sprint | 0 | 0