## Description
Design document: | https://docs.google.com/document/d/1wZsXl8XMl21V3WNjHIGPi_brwDXqoCBx7Pxdo1Abudo/edit#
Jira project: | P2 next gen (PP)
Jira label: | P2_pipelines_test
Number of tasks: | 24
Number of reported bugs: | 0
Total planned development worktime [h]: | 155
Planned development worktime of finished tasks [h]: | 0
Current worktime spent [h]: | 0
Planned time to finish project [h]: | 155
Project completeness based on planned worktime [%]: | 0
Current worktime vs planned worktime [%]: | #DIV/0! | > 100% - delay; < 100% - ahead
Last update | Jul 19, 2021 16:21:08
Number of updated tasks (during last update) | 0

## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  |  | Developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment | Category | Version
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Environment and pipeline | see design | [11 empty] | PP-1798 |  |  |  |  | 1 | 0
1.1 | create a script to get the access token needed to run the o2 grouper | get access token to run o2 grouper pipeline |  | 24 |  |  | 24 | [6 empty] | PP-1799 |  |  |  |  | 1 | 0
1.2 | create repository | create: file requirements, folder with config files, config, folder with tests, folder with methods |  | 6 |  |  | 6 | [6 empty] | PP-1800 |  |  |  |  | 1 | 0
1.3 | create necessary methods for data comparison | get header names, types, check duplicates, check full data |  | 8 |  |  | 8 | [6 empty] | PP-1801 |  |  |  |  | 1 | 0
1.4 | create necessary methods for pipeline status | get pipeline status, stage, validationStatistics, caseStatistics |  | 8 |  |  | 8 | [6 empty] | PP-1802 |  |  |  |  | 1 | 0
1.5 | create necessary methods (fixtures, get token to o2 grouper) | fixtures (run pipeline, download files from s3, authentication) |  | 8 |  |  | 8 | [6 empty] | PP-1803 |  |  |  |  | 1 | 0
1.6 | prepare containers (dockers) |  |  | 8 |  |  | 8 | [6 empty] | PP-1804 |  |  |  |  | 1 | 0
1.7 | create README |  |  | 5 |  |  | 5 | [6 empty] | PP-1805 |  |  |  |  | 1 | 0
2 | Prepare data | see design | [11 empty] | PP-1806 |  |  |  |  | 1 | 0
2.1 | input/output/correct/incorrect: stay maker (cms) (result: Stays and Patients) | Prepare data to verify edge case and proper result |  | 8 |  |  | 8 | [6 empty] | PP-1807 |  |  |  |  | 1 | 0
2.2 | input/output/correct/incorrect: stay maker (p2upload) - (result: Stays and Patients) | Prepare data to verify edge case and proper result |  | 8 |  |  | 8 | [6 empty] | PP-1808 |  |  |  |  | 1 | 0
2.3 | output relation maker file | Prepare data to verify edge case and proper result |  | 4 |  |  | 4 | [6 empty] | PP-1809 |  |  |  |  | 1 | 0
3 | Verify data | see design | [11 empty] | PP-1810 |  |  |  |  | 1 | 0
3.1 | stay maker (cms) | verify output data |  | 8 |  |  | 8 | [6 empty] | PP-1811 |  |  |  |  | 1 | 0
3.2 | stay maker (p2upload) | verify output data |  | 8 |  |  | 8 | [6 empty] | PP-1812 |  |  |  |  | 1 | 0
3.3 | relation maker (cms) | verify output data |  | 8 |  |  | 8 | [6 empty] | PP-1813 |  |  |  |  | 1 | 0
3.4 | relation maker (p2upload) | verify output data |  | 8 |  |  | 8 | [6 empty] | PP-1814 |  |  |  |  | 1 | 0
4 | Integration Tests | see design | [11 empty] | PP-1815 |  |  |  |  | 1 | 0
4.1 | correct files (publish False/True) | Verify happypath for input files: cms and p2upload and for publish set to True and False |  | 6 |  |  | 6 | [6 empty] | PP-1816 |  |  |  |  | 1 | 0
4.2 | incorrect files | Verify edge case for input files: cms and p2upload and for publish set to True and False |  | 6 |  |  | 6 | [6 empty] | PP-1817 |  |  |  |  | 1 | 0
4.3 | start with step 2 (Stay maker) (publish False/True) | Verify pipeline works correctly after run from a specific o2 grouper stage |  | 6 |  |  | 6 | [6 empty] | PP-1818 |  |  |  |  | 1 | 0
4.4 | start with step 3 (Episode maker) (publish False/True) | Verify pipeline works correctly after run from a specific o2 grouper stage |  | 6 |  |  | 6 | [6 empty] | PP-1819 |  |  |  |  | 1 | 0
4.5 | start with step 4 (Relation maker) (publish False/True) | Verify pipeline works correctly after run from a specific o2 grouper stage |  | 6 |  |  | 6 | [6 empty] | PP-1820 |  |  |  |  | 1 | 0
4.6 | pipeline server - endpoint graphql (publish False/True) | Verify that pipeline status result |  | 6 |  |  | 6 | [6 empty] | PP-1821 |  |  |  |  | 1 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0