## Description
Design document: | Preferred Partners Backend v3
Jira project: | P2 next gen (PP)
Jira label: | P2_v3
Number of tasks:
Number of reported bugs:
Estimated development time [h] (designer):
Estimated development time [h] (reviewer):
Estimated development time [h] (pm):
Estimated testing time [h] (tester):
Estimated testing time [h] (pm):
Total time spent [h]:

## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  | Assigned developer | Estimated testing time [h] |  | Assigned tester | Actual development time |  |  | Commit statistics |  | Estimated code documentation time [h] | Jira ID | Commit ID | Sprint | Comment | Order
|  |  |  | Designer | Reviewer | PM |  | Tester | PM |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Analytical API | [15 empty] | PP-226
1.1 | caseSummaryCollection endpoint | This is the basic functionality with filtering but without: benchmarks, pagination or sorting, some response elements are not present in the outputs | [14 empty] | PP-247
1.1.1 | Implement Filter and derived classes - ColumnFilter, DistanceFilter |  |  | 3 | 4 | 4 | Michał |  |  |  | February 22, 2021, 5:13 PM | February 23, 2021, 12:08 PM | 8 | 570 | 0 |  | PP-227 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/2 | Sprint 1 (based on reviewer estimation) | More time due to code analysis tool rejections.
1.1.2 | Implement extract_filters for the CaseSummaryFilterInputType input |  | 1.1.1 | 16 | 20 | 24 | Maciej |  |  |  | February 23, 2021, 2:11 PM | March 1, 2021, 6:13 PM | 32 | 391 | 1 |  | PP-228 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/8 | Sprint 1 (based on reviewer estimation)
1.1.3 | Implement extract_filters for the CaseSummaryActionsInputType input |  | 1.1.1 | 4 | 4 | 6 | Aleksandra |  |  |  | March 4, 2021, 1:38 PM | [5 empty] | PP-229 |  | Sprint 1 (based on reviewer estimation)
1.1.4 | Implement extract_filters for the RangeInputType input |  | 1.1.1 | 2 | 2 | 4 | Maciej |  |  |  | March 1, 2021, 12:13 PM | March 1, 2021, 6:13 PM | 4 | 391 | 1 |  | PP-230 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/8 | Sprint 1 (based on reviewer estimation)
1.1.5 | Implement filter_by method for pandas.DataFrame with the ColumnFilter |  | 1.1.1 | 4 | 4 | 6 | Michał |  |  |  | February 25, 2021, 5:46 PM | February 26, 2021, 4:25 PM | 7 | 86 | 18 |  | PP-231 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/6 | Sprint 1 (based on reviewer estimation) | More time due to code review rejection.
1.1.6 | Implement filter_by method for pandas.DataFrame with the DistanceFilter |  | 1.1.1 | 12 | 16 | 16 | Michał |  |  |  | February 26, 2021, 3:08 PM | March 1, 2021, 5:48 PM | 10 | 69 | 23 |  | PP-232 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/7 | Sprint 1 (based on reviewer estimation)
1.1.19 | Implement filter_by method for pandas.DataFrame with the RangeFilter |  | 1.1.1 | 2 |  | 4 | Maciej |  |  |  | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 2.5 | 77 | 13 |  | PP-307 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/11 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks.
1.1.7 | Implement Node, NodeTypeEnum and NodeSubTypeEnum classes, implement get_node_type_from_subtype method |  |  | 3 | 4 | 6 | Maciej |  |  |  | February 23, 2021, 1:06 PM | February 23, 2021, 1:42 PM | 3 | 98 | 0 |  | PP-233 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/3 | Sprint 1 (based on reviewer estimation) | Forgot to change jira status at the beginning of the work on task.
1.1.8 | Implement PandasProvider class (extending the AnalyticsProvider) | We should be able to pull data from files (available in the project) and join with entities_ac / entities_pac automatically / carelines |  | 8 | 12 | 16 | Michał |  |  |  | February 23, 2021, 12:12 PM | February 25, 2021, 3:43 PM | 19 | 130 | 0 |  | PP-234 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/4 | Sprint 1 (based on reviewer estimation) | More time spend due to fixes after code review + code fixes after more rigorous code analysis tool was implemented.
1.1.20 | Add computed column fiscal_date to PandasAnalyticalService | fiscal_date = fiscal_year * 10 + fiscal_quarter |  | 2 |  | 4 | Maciej |  |  |  | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 2.5 | 77 | 13 |  | PP-308 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/11 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks.
1.1.9 | Implement the PandasAnalyticalService find_nodes method | leave other methods unimplemented, all types of nodes should be supported | 1.1.8, 1.1.5, 1.1.6 | 16 | 20 | 24 | Michał |  |  |  | March 2, 2021, 10:32 AM | March 3, 2021, 05:45 PM | 16 | 120 | 6 |  | PP-235 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/13 | Sprint 1 (based on reviewer estimation)
1.1.10 | Implement AbstractGraphQuery class and make_abstract_graph_query method | for now only implement the methods get_nodes and get_filters, leave the others unimplemented | 1.1.1 - 1.1.9 | 3 | 4 | 4 | Aleksandra | [9 empty] | PP-236 |  | Sprint 1 (based on reviewer estimation)
1.1.11 | Implement AbstractGraphModel class and the make_abstract_graph_model method | for now do not handle the sorting or pagination info | 1.1.10 | 3 | 4 | 4 | Aleksandra | [9 empty] | PP-237 |  | Sprint 1 (based on reviewer estimation)
1.1.12 | Implement PandasAnalyticalService group_nodes method | All types of nodes should be supported | 1.1.8 | 32 | 40 | 48 | Maciej |  |  |  | March 4, 2021, 4:01 PM | [5 empty] | PP-238 |  | Sprint 1 (based on reviewer estimation) | postponed
1.1.13 | Implement SummaryStatistics class and extract_node_statistics method | All types of nodes should be supported | 1.1.12 | 18 | 24 | 24 | Maciej | [9 empty] | PP-239 |  | Sprint 1 (based on reviewer estimation) | postponed
1.1.14 | Implement extract_relation_statistics method |  | 1.1.13 | 5 | 8 | 8 | Maciej | [9 empty] | PP-240
1.1.15 | Implement PandasAnalyticalService get_entity_details method | Just pull matching data from entities data frames | 1.1.9 | 4 | 4 | 4 | Michał | [9 empty] | PP-241
1.1.16 | Implement copy_summary_statistics method |  | 1.1.13 | 4 | 4 | 4 | Aleksandra | [9 empty] | PP-242
1.1.17 | Implement CaseSummaryQueryRunner class | For now ignore the groupingInfo, benchmarkValues, count and legednData responses | 1.1.1 - 1.1.16 | 28 | 32 | 32 | Maciej | [9 empty] | PP-243
1.1.18 | implement caseSummaryCollection endpoint |  | 1.1.17 | 4 | 4 | 4 | Maciej | [9 empty] | PP-244
1.1.21 | Implement get_sql_filter for Node | should return python object | 1.1.7 | 5 |  | 8 | Maciej | [9 empty] | PP-309 |  | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks.
1.1.22 | Implement get_sql_group_column for Node | should return python object | 1.1.7 | 4 |  | 6 | Maciej | [9 empty] | PP-310 |  | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks.
1.2 | caseLocationDetails endpoint | For now we ignore the "state" output which is likely not used | [14 empty] | PP-248
1.2.1 | implement extract_filters method | The method takes CaseLocationOptionInputType as input, use already existing extract_filters method implementation for the nested types | 1.1.2 - 1.1.4 | 6 | 8 | 8 | [10 empty] | PP-249
1.2.2 | implement get_entity_counts method in PandasAnalyticalService | use data frames provided in the examples, calculate statistics both for PACs and hospitals | 1.1.8, 1.2.1 | 20 | 24 | 24 | [10 empty] | PP-250
1.2.3 | implement copy_location_details method |  |  | 8 | 12 | 16 | [10 empty] | PP-251
1.2.4 | implement caseLocationDetails endpoint |  | 1.2.1 - 1.2.3 | 4 | 8 | 8 | [10 empty] | PP-252
1.3 | caseLobCounts endpoint | [15 empty] | PP-253
1.3.1 | implement get_lob_statistics in PandasAnalyticalService |  | 1.1.8 | 4 | 4 | 4 | [10 empty] | PP-254
1.3.2 | implement copy_lob_statistics method |  |  | 3.5 | 4 | 2 | [10 empty] | PP-255
1.3.3 | Implement caseLobCounts endpoint |  | 1.3.1, 1.3.2 | 1 | 2 | 4 | [10 empty] | PP-256
1.4 | getAvailableYears endpoint | [15 empty] | PP-257
1.4.1 | Implement get_all_years method in PandasAnalitycalService |  | 1.1.8 | 2 | 2 | 2 | [10 empty] | PP-258
1.4.2 | Implement get_row_range helper method for pandas DF |  |  | 1 | 2 | 4 | [10 empty] | PP-259
1.4.3 | Implement getAvailableYears endpoint |  | 1.4.1, 1.4.2 | 1 | 2 | 4 | [10 empty] | PP-260
1.5 | getDateTimeStatsForListOfYears endpoint | [15 empty] | PP-261
1.5.1 | implement get_quarterly_statistics method in PandasAnalyticalService |  | 1.1.8 | 3 | 4 | 4 | [10 empty] | PP-262
1.5.2 | implement copy_quarterly_statistics method |  |  | 2 | 2 | 2 | [10 empty] | PP-263
1.5.3 | implement getDateTimeStatsForListOfYears endpoint |  | 1.5.1, 1.5.2 | 2 | 2 | 4 | [10 empty] | PP-264
1.6 | implement filteredCareUnitTypes endpoint | [15 empty] | PP-265
1.6.1 | Implement get_careunit_statistics method in PandasAnalyticalService |  | 1.1.8 | 3 | 4 | 4 | [10 empty] | PP-285
1.6.2 | Implement extract_careunit_statistics method |  |  | 2 | 2 | 4 | [10 empty] | PP-286
1.6.3 | Implement filteredCareUnitTypes endpoint |  | 1.6.1, 1.6.2 | 1 | 2 | 4 | [10 empty] | PP-287
1.7 | implement getDatasetsInitialFilters | [15 empty] | PP-288
1.7.1 | Implement get_diagnose_statistics method in PandasAnalyticalService |  |  | 3.5 | 4 | 4 | Aleksandra |  |  |  | February 25, 2021, 2:55 PM | [5 empty] | PP-289 |  | Sprint 1 | Added during sprint, due to earlier finish of research tasks.
1.7.2 | implement copy_diagnose_statistics method |  |  | 2 | 2 | 2 | Aleksandra |  |  |  | March 1, 2021, 5:02 PM | [5 empty] | PP-290 |  | Sprint 1 | Added during sprint, due to earlier finish of research tasks.
1.7.3 | implement getDatasetsInitialFilters endpoint | use existing queries / methods to populate data in the requested fields |  | 6 | 6 | 4 | Aleksandra |  |  |  | March 1, 2021, 5:03 PM | [5 empty] | PP-291 |  | Sprint 1 | Added during sprint, due to earlier finish of research tasks.
2 | Testing caseSummaryCollection query | [15 empty] | PP-266
2.1 | Test caseSummaryCollection - market share graph | Test filters and responsed for caseSummaryCollection with benchmark option set to false | [5 empty] | 24 | 16 | [7 empty] | PP-267
2.2 | Test caseSummaryCollection - benchmark graph | Test filters and responses for caseSummaryCollection with benchmark set to true | [5 empty] | 24 | 16 | [7 empty] | PP-268
2.3 | Test caseSummaryCollection - 2D graph | Test filters and responses for caseSummaryCollection with 2D graph benchmark settings | [5 empty] | 24 | 16 | [7 empty] | PP-269
3 | Dataset Management | [15 empty] | PP-270
3.1 | Define schema.py | Class that defines graphQL queries, endpoints and object structure. Python file will have definition of following ojects | [14 empty] | PP-271
3.1.1 | DatasetsType(ObjectType) |  |  | 2 | [12 empty] | PP-272
3.1.2 | DatasetPermissionType |  |  | 1 | [12 empty] | PP-273
3.1.3 | UploadStatisticsType |  | Upload processing Pipeline | 3 | [12 empty] | PP-274
3.1.4 | ValidationStatisticsType |  | Upload processing Pipeline | 3 | [12 empty] | PP-275
3.1.5 | CaseStatisticsType |  | Upload processing Pipeline | 1 | [12 empty] | PP-276
3.1.6 | get_lds_datasets_ids |  |  | 2 | [12 empty] | PP-277
3.1.7 | all_datasets |  |  | 3 | [12 empty] | PP-278
3.1.8 | CreateDataset |  | Upload processing Pipeline | 4 | [12 empty] | PP-279
3.1.9 | UpdateDataset |  |  | 2 | [12 empty] | PP-280
3.1.10 | upload file |  | Upload processing Pipeline | [13 empty] | PP-281
3.2 | Define model.py | Class that defines the Entity Relation of dataset as per OLTP database(Postgres) |  | 4 | [12 empty] | PP-282
3.3 | Define authorization.py | Class that interacts with applications authorization service. Checks users authorization for Create, Update, Delete and Retrieving datasets. |  | 6 | [12 empty] | PP-283
3.4 | Define dataset_api.py | This class has actual implementation of all the CRUD operations related to dataset management. This class interacts with schema, model and authorization and performs the actual operations. | 5.1, 5.2, 5.3 | 16 | [12 empty] | PP-284
4 | Report View Management | [15 empty] | PP-356
4.0 | Environment Setup | Setu development environment including DJangoand PGSql |  | 20 | [12 empty] | PP-357
4.1 | Define schema.py | Class that defines graphQL queries, endpoints and object structure. Python file will have definition of following ojects. Developer can refer existing P2BE code at p2backend\ReportView\schema.py file. |  | 6 | [12 empty] | PP-358
4.2 | Define reportview_api.py | Class that has actual implementation for all end points. Developer can refer p2backend\BigSense\Reportview\reportview_api.py file from existing P2BE code |  | 4 | [12 empty] | PP-359
4.3 | Define model.py | Class that defines the Entity Relation of report view as per OLTP database(Postgres) |  | 4 | [12 empty] | PP-360
4.4 | Implementing Endpoints | This implementation will have a resolve method in schema.py and corresponding method in reportview_api.py file | [14 empty] | PP-361
4.4.1 | ReportView |  |  | 4 | [12 empty] | PP-362
4.4.2 | ReportViews |  |  | 6 | [12 empty] | PP-363
4.4.3 | SearchReportViews |  |  | 6 | [12 empty] | PP-364
4.4.4 | CreateReportView |  |  | 6 | [12 empty] | PP-365
4.4.5 | UpdateReportView |  |  | 6 | [12 empty] | PP-366
4.4.6 | DeleteReportView |  |  | 6 | [12 empty] | PP-367

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions