## PMSummary
[10 empty] | Prioritization of categories | # of tasks | Primary Assignee | # of estimated hours
Tab Name | # of tasks | Estimated # of Hours | Completed # of Hours | % Completed | % Remaining | #hrs remaining | Code review time | Grand Total | 1 | Authentication & Authorization | 24 | Chandan | 136.5
Components | 104 | 726 | 573.757 | 79.03% | 20.97% | 152.243 | 44.249 | 618.006 | 2 | Visualization Generation | 59 | Michael | 490.25
Services | 49 | 200.25 | 156.5 | 78.15% | 21.85% | 43.75 | 14.58 | 171.08 | 3 | Visualization Navigation | 1 | Michael | 0
Utilities | 24 | 192.75 | 182.25 | 94.55% | 5.447% | 10.5 | 9.11 | 191.36 | 4 | View Dashboard | 9 | Daya | 7.5
Pipes | 17 | 13.25 | 13.25 | 100% | 0% | 0 | 0 | 13.25 | 5 | Commonly Used | 33 | Chandan | 38.5
Directives | 9 | 14.5 | 14.5 | 100% | 0% | 0 | 0 | 14.5 | 6 | Visualization Legend | 5 | Daya | 15.75
Misc. | 10 | 21.5 | 19.25 | 89.53% | 10.47% | 2.25 | 19.25 | 38.5 | 7 | Filters - Location filters | 7 | Daya | 102.75
Auth0 | 17 | 129 | 34.5 | 79.03% | 20.97% | 94.5 | 0 | 34.5 | 8 | Filters - Entity filters | 3 | Chandan | 32
TOTALS | 230 | 1297.25 | 959.507 | 73.96% | 26.04% | 337.743 | 87.189 | 1046.696 | 9 | Filters - Service Line filters | 3 | Chandan | 33.5
[9 empty] | 10 | Label settings | 11 | Daya | 31
[9 empty] | 11 | Filters - Time filters | 10 | Michael | 45.5
[9 empty] | 12 | Filters - LOB filters | 3 | Daya | 5.75
Staffing |  | hrs per week | Unit test creation | Code review hours | # of weeks | Total capacity |  |  | 13 | Filters - Convenience features | 29 | Chandan | 148.75
Michael |  | 30 | 25 | 5 | 6 | 180 |  |  | 14 | Filters or Visualization Navigation Convenience features | 1 | Chandan | 0.25
Daya |  | 40 |  |  | 4 | 160 |  |  | 15 | Benchmark settings customization & Benchmark Calculation | 8 | Daya | 61.75
Chandan |  | 20 |  |  | 6 | 120 |  |  | 16 | Save or export Visualization | 8 | Michael | 98
TOTAL | [5 empty] | 460 | -499.507 |  | 17 | Dataset upload and management | 13 | Daya | 48.25
[11 empty] | 227 |  | 1296
Tab |  | # of tasks | Services | Utilities | Pipes | Directives | Misc.
Components
Services
Utilities
Pipes
Directives
Misc.
Auth0

## Components
|  |  |  | 726 | [5 empty] | 44.249 | 573.757 | [10 empty] | 4.75
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id |  | time spent on task [h]
Visualization Generation | graph-view.component.ts | 3 | 2,2.1,2.3,2.4 | 86.5 | 80 | -20.75 | 65.75 | 0.5 | 6 | 5 | Y | Several methods are no longer called. This would cut down on the total Unit Test estimation but time would have to be spent on Code Cleanup to determine what should be removed. Move checkGraphFilters method to utils. | 96.21% | 84.57% | 92.44% | 96.65% | Sprint 5, Sprint 6 | 2021-04-26 | 2021-05-07 | Michael | PP-705 |  | 91.5
Commonly Used | back-to-top.component.ts | 9.4.3 |  | 0.5 |  | 0 |  | 0 | 0.5 | 0.083 | Y | Tests need to be copied over from Admin Panel and verified. | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-17 | 2021-05-17 | Chandan | PP-785 |  | 0.583
Visualization Generation | map-view.component.ts | 4 | 2,2.2,2.3,2.4,2.5,2.9 | 13 | 10 | 4 | 17 | 0.5 | 2.5 | 2.25 | Y | Move checkGraphFilters method to utils. | 94 | 82 | 96 | 94 | Sprint 3 | 2021-03-25 | 2021-03-25 | Daya | PP-707 |  | 15.25
Benchmark settings customization & Benchmark Calculation | benchmark.component.ts | 4.1.1 | 2,2.3,2.4 | 41.5 | 38.5 | -2.75 |  | 2 | 1 | 1.5 | Y |  | 88 | 80 | 90 | 88 | Sprint 5 | 2021-04-20 | 2021-04-30 | Chandan | PP-786 |  | 43
Visualization Generation | service-line-filter.component.ts | 5.1 |  | 22.75 | 21 | -1 | 21.75 | 0.75 | 1 | 2.5 | Y | Time needs to be spent researching D3 specific testing methods for majority of functions and logic. | 98.44% | 86.65% | 99.42% | 98.39% | Sprint 5 | 2021-04-14 | 2021-04-19 | Daya | PP-719 |  | 25.25
Visualization Generation | scatter-plot-parent.component.ts | 5 |  | 20.25 | 16 | 1.5 | 21.75 | 0.75 | 3.5 | 0.75 | Y | Move checkGraphFilters method to utils. | 97 | 82 | 96 | 97 | Sprint 4 | 2021-04-12 | 2021-04-14 | Daya | PP-710 |  | 21
Visualization Generation | blank-view.component.ts | 3.1.2 |  | 1.75 | 0.25 | 0 | 1.75 | 1 | 0.5 |  | Y | [5 empty] | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-706 |  | 1.75
View Dashboard | side-view-root.component.ts | 9.3 |  | 1.25 | 0.5 | 0 | 1.25 | 0.5 | 0.25 | 0.75 | Y | [5 empty] | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-712 |  | 2
View Dashboard | header-view-root.component | 9.4 |  | 0.5 | 0 |  | 0.5 | 0 | 0.5 |  | Y | Look into TODOs and moving, combining, or removing DTOs. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-713 |  | 0.5
Dataset upload and management | select-dataset.component.ts | 11.4 | 11.1 | 17.5 | 14 | 8 | 25.5 | 1 | 2.5 | 3 | Y | Dataset Selector and Dataset Details should also be tested/added. | 99.12% | 93.53% | 98.67% | 99.12% | Sprint 0 | 2021-03-23 | 2021-03-23 |  | PP-714 |  | 20.5
Dataset upload and management | o2-dataset-selector.component.ts | 11.5 | 11.1 | 5.75 | 3.5 | 4 | 9.75 | 1.25 | 1 | 1 | Y | Added to go with Select Dataset tests. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-715 |  | 6.75
Dataset upload and management | o2-dataset-details.component.ts | 11.6 | 11.1 | 8.5 | 4.5 | 4 | 12.5 | 2 | 2 | 1 | Y | Added to go with Select Dataset tests. |  |  |  |  | Sprint 0 | 2021-03-24 | 2021-03-24 |  | PP-716 |  | 9.5
Filters - Entity filters | entity-filter.component.ts | 7.3 | 2,7 | 27 | 23 | -2 | 25 | 1 | 3 | 1.5 | Y |  | 99.49% | 88.05% | 100% | 99.48% | Sprint 6 | 2021-05-19 | 2021-05-25 | Michael | PP-717 |  | 28.5
Visualization Generation | distribution-map.component.ts | 4.5.1 |  | 0.5 | 0 | 0.5 | 1 | 0.5 | 0 |  | Y | Tests not really needed since it just passes map details to child components. | 100% | 100% | 100% | 100% | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-738 |  | 0.5
Filters - Service Line filters | service-line-filter.component.ts | 8.2 | 8 | 28 | 23 | -1.5 | 6.5 | 1.5 | 3.5 | 1 | Y | Some logic and tests might overlap with other filter components. | 98.11% | 87.15% | 97.66% | 98.15% | Sprint 6 | 2021-05-12 | 2021-05-17 | Daya | PP-719 |  | 29
Filters - Time filters | time-filter.component.ts | 14.1.2 |  | 24.75 | 24 |  | 24.75 | 0.75 | 3-4? |  | Y | [5 empty] | Sprint 8 | 2021-06-01 | 2021-06-07 | Michael | PP-720 |  | 24.75
Filters - Time filters | time-filter-applied.component.ts | 14.6 |  | 3.75 | 2 |  | 3.75 | 1.25 | 0.5 |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 8 | 2021-06-01 | 2021-06-01 | Michael | PP-721 |  | 3.75
Filters - Time filters | time-filter-list.component.ts | 14.4 |  | 12.5 | 9.5 |  | 12.5 | 0.5 | 2.5 |  | Y | [5 empty] | Sprint 8 | 2021-06-07 | 2021-06-08 | Michael | PP-722 |  | 12.5
Filters - Time filters | time-filter-map.component.ts | 14.5 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-723 |  | 0
Filters - Time filters | time-filter-search.component.ts | 14.7 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-724 |  | 0
Filters - Time filters | time-frame.component.ts | 14.8 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-725 |  | 0
Label settings | label-styles.component.ts | 8.2.1 |  | 8.25 | 7.5 |  | 8.25 |  | 0.75 | 3 | Y |  | 89.4 | 80 | 92.86 | 90.26 |  | 2021-03-25 | 2021-03-25 | Daya | PP-726 |  | 11.25
Label settings | order-styles.component.ts | 8.2.2 |  | 5.5 | 4.5 | 0 | 5.5 |  | 1 | 1.5 | Y |  | 94.94 | 81.25 | 100 | 94.52 |  | 2021-03-25 | 2021-03-25 | Daya | PP-727 |  | 7
Filters - Convenience features | horizontal-bar-chart.component.ts | 14.9 |  | 35 | 30 |  | 35 | 2.5 | 2.5 |  | Y | Need to research testing these specific D3 methods. Some minor unit tests were previously done by Jared in another branch. |  |  |  |  | Sprint 8 | 2021-05-26 | 2021-06-02 | Daya | PP-728 |  | 35
Benchmark settings customization & Benchmark Calculation | o2-autocomplete.component.ts | 7.5.3 |  | 0 | 0 | 0 | 0 | N/A | 0 |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-729 |  | 0
Benchmark settings customization & Benchmark Calculation | o2-autocomplete-multiselect.component.ts | 7.5.4 |  | 2.5 | 2.5 |  | 2.5 | N/A |  |  | N | [5 empty] | Sprint 7 | 2021-05-18 | 2021-05-18 | Michael | PP-730 | 2.5 | 0
Benchmark settings customization & Benchmark Calculation | o2-autocomplete-search-filter.component.ts | 7.5.5 |  | 1.5 | 0 |  | 1.5 | N/A | 1.5 |  | N | Discuss TODOs for code cleanup. | 98.04% | 94.12% | 100% | 98.03% | Sprint 7 | 2021-05-18 | 2021-05-18 | Michael | PP-731 | 1.5 | 0
Filters - Convenience features | o2-bread-crumb.component.ts | 10.2 | 10 | 0.75 | 0.25 | -0.083 | 0.667 | 0.5 |  | 0.1 | Y |  | 100% | 100% | 100% | 100% | Sprint 7 | 2021-05-26 | 2021-05-26 | Michael | PP-732 |  | 0.85
Filters - Convenience features | o2-bread-crumb-sidenav.component.ts | 10.1 | 10 | 5 | 2 | -1.5 | 3.5 | 3 | 0 | 0.2 | Y |  | 100% | 100% | 100% | 100% | Sprint 7 | 2021-05-25 | 2021-05-26 | Michael | PP-733 |  | 5.2
Benchmark settings customization & Benchmark Calculation | o2-choice.component.ts | 7.5.6 |  | 0 | 0 |  | 0 | N/A | 0 |  | Y | [5 empty] | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-734 |  | 0
Visualization Navigation | o2-context-menu.component.ts | 3.2.5 |  | 0 | 0 | 0 | 0 | N/A | 0 |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-735 |  | 0
Dataset upload and management | o2-data-statistic.component.ts | 11.5 |  | 1.25 | 0.25 | -0.75 | 0.5 | 0.75 | 0.25 | 0.43 | Y | Verify previous TODO. | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-18 | 2021-05-18 | Daya | PP-736 |  | 1.68
Dataset upload and management | o2-data-statistic-case.component.ts | 11.6 |  | 1 | 0.25 | -0.5 | 0.5 | 0.75 |  | 0.1 | Y | Check if TODO in O2 Data Statistic component impacts this as well. | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-18 | 2021-05-18 | Daya | PP-737 |  | 1.1
Commonly Used | error-msg.component.ts | 9.4.4 |  | 0.5 | 0 | 0 |  | 0.5 | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-17 | 2021-05-17 | Chandan | PP-787 |  | 0.5
Visualization Generation | radius-map.component.ts | 4.1 | 2, | 19.5 | 17 | 0 | 19.5 | 0.5 | 2 | 3 | Y | Need to research testing Component Factory injection. Should we not test code that might be replaced in the future for faster rendering? Some methods aren't used anymore and can be removed to reduce the total unit test time. | 88.97% | 84.86% | 86% | 89.36% | Sprint 3 | 2021-03-09 | 2021-04-01 | Daya | PP-739 |  | 22.5
Visualization Generation | map-slider.component.ts | 4.2 |  | 5 | 3 | 0 | 5 | 0.5 | 1.5 | 0.5 | Y |  | 91.45 | 80 | 88.89 | 91.3 | Sprint 3 | 2021-03-25 | 2021-03-26 | Daya | PP-740 |  | 5.5
Visualization Generation | map-label.component.ts | 4.4 |  | 7 | 5.5 |  | 7 | 0.5 | 1 | 0.5 | Y |  | 98.4 | 95.18 | 100 | 98.37 | Sprint 3 | 2021-03-25 | 2021-03-26 | Daya | PP-741 |  | 7.5
Visualization Generation | map-cluster-label.component.ts | 4.5 |  | 5 | 4 |  | 5 | 0.5 | 0.5 | 0.5 | Y |  | 98.72 | 96.3 | 100 | 98.67 | Sprint 3 | 2021-03-25 | 2021-03-26 | Daya | PP-742 |  | 5.5
Save or export Visualization | o2-download-graph.component.ts | 13.5 | 13.1 | 27.5 | 22 | 6 | 33.5 | 3.5 | 2 | 1.75 | Y | There are some unit tests written but I don't believe they were done properly for code coverage before. Time to complete based on how much is actually covered and can be reused. | 90 | 80 | 91 | 80 | Sprint 3 | 2021-03-31 | 2021-04-05 | Daya | PP-743 |  | 29.25
Save or export Visualization | o2-download-graph-page.component.ts | 13.6 | 13.1 | 2 | 2 | -0.66 | 1.34 | 0 | 0 | 0.17 | Y | No functional unit tests needed. | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-19 | 2021-05-19 | Daya | PP-744 |  | 2.17
View Dashboard | search.component.ts | 9.4 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-26 | 2021-03-26 |  | PP-745 |  | 0
Filters - Convenience features | o2-spiral-graph.component.ts | 13.6.1 |  | 30 | 28 |  | 30 | 0 | 2 |  | Y | A lot of D3 code used here. |  |  |  |  | Sprint 7 | 2021-05-20 | 2021-05-25 | Daya | PP-746 |  | 30
Filters - Convenience features | o2-star-chart.component.ts | 7.5 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | Not currently used in Quality Filter. |  |  |  |  | Sprint 0 | 2021-03-23 | 2021-03-26 |  | PP-747 |  | 0
Filters - Convenience features | o2-tooltip.component.ts | 7.4 |  | 1 | 0 | -0.25 | 0.75 | N/A | 1 |  | N | Already completed. Verify TODOs and watch for any bugs from changes. | 99.59% | 97.64% | 100% | 99.59% | Sprint 6 | 2021-05-14 | 2021-05-14 | Michael | PP-748 | 0.75 | 0
Dataset upload and management | o2-upload-file.component.ts | 11.7 |  | 4.75 | 3 |  | 4.75 | 1.25 | 0.5 |  | Y | [5 empty] | Sprint 7 | 2021-05-18 | 2021-05-18 | Daya | PP-749 |  | 4.75
Dataset upload and management | o2-shareview.component.ts | 11.6 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | Shareview is hidden in the Select Dataset panel currently. |  |  |  |  | Sprint 0 | 2021-06-07 | 2021-06-07 |  | PP-750 |  | 0
Visualization Generation | base-chart.component.ts | 5.3 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-23 | 2021-03-25 |  | PP-751 |  | 0
Visualization Legend | benchmark-legend.component.ts | 3.1.4 |  | 2.75 | 1 | 0 | 2.75 | 1.25 | 0.5 | 0.75 | Y |  | 100 | 100 | 100 | 100 | Sprint 3 | 2021-03-25 | 2021-03-25 | Daya | PP-752 |  | 3.5
Visualization Generation | chart-wrapper.component.ts | 5.4 |  | 0.75 | 0.25 | 0.25 | 1 | 0.5 | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 5 | 2021-04-19 | 2021-04-19 | Daya | PP-753 |  | 0.75
Visualization Legend | legend-label.component.ts | 3.1.2 |  | 5.75 | 3.5 |  | 5.75 | 1.25 | 1 | 0.5 | Y |  | 98 | 98 | 100 | 98 | Sprint 3 | 2021-03-25 | 2021-03-25 | Daya | PP-754 |  | 6.25
Visualization Legend | legend-label-item.component.ts | 3.1.3 |  | 2 | 0.5 | 0 | 2 | 1.5 | 0 | 0.25 | Y |  | 100 | 100 | 100 | 100 | Sprint 3 | 2021-03-25 | 2021-03-25 | Daya | PP-755 |  | 2.25
Filters - Convenience features | field-icon.component.ts | 10.6 |  | 0.5 | 0.25 | 0 |  | 0.25 | 0 | 0.083 | Y |  | 100 | 100 | 100 | 100 | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan | PP-793 |  | 0.583
Commonly Used | inline-alert.component.ts | 9.4.7 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | Only used in a component which isn't in use. |  |  |  |  | Sprint 0 | 2021-03-23 | 2021-03-23 |  | PP-757 |  | 0
Filters - Convenience features | fieldset.component.ts | 10.3 |  | 0.25 | 0 | 0 |  | 0.25 | 0 | 0.083 | Y |  | 100 | 100 | 100 | 100 | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan | PP-794 |  | 0.333
Filters - Location filters | o2-radius-selector.component.ts | 6.4 |  | 20 | 13 | -2 | 18 | 4 | 3 | 2.25 | Y |  | 99.01% | 87.98% | 96.72% | 99% | Sprint 4 | 2021-04-06 | 2021-04-08 | Daya | PP-759 |  | 22.25
Filters - Location filters | o2-radius-component.ts | 6.3 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | Replaced by O2 Radius Selector. No longer used. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-760 |  | 0
Visualization Generation | node-graph.component.ts | 3.1 | 2,2.4 | 10.25 | 7.5 | 1.25 | 11.5 | 1.25 | 1.5 | 1 | Y |  | 98.94% | 91.25% | 97.37% | 98.91% | Sprint 3 | 2021-03-23 | 2021-03-25 | Michael | PP-761 |  | 11.25
Visualization Generation | node.component.ts | 3.2 | 2,2.1,2.4 | 24.5 | 20 | -1.25 | 23.25 | 1.5 | 3 | 2 | Y | Depends on how long it takes to write tests for HTML string creation. | 98.27% | 94.72% | 95.24% | 98.48% | Sprint 3 | 2021-03-17 | 2021-03-23 | Michael | PP-762 |  | 26.5
Visualization Generation | node-label.component.ts | 3.3 | 2,2.4 | 6.5 | 4.5 | -2 | 4.5 | 0 | 2 |  | Y |  | 100% | 100% | 100% | 100% | Sprint 3 | 2021-03-29 | 2021-03-29 | Michael | PP-763 |  | 6.5
Visualization Generation | node-details.component.ts | 3.4 | 2,2.4 | 19 | 18 | -9.5 | 9.5 | 0 | 1 | 0.75 | Y | Need to fix compile errors and check code coverage. | 93.13% | 94.17% | 89.09% | 93.3% | Sprint 4, Sprint 5 | 2021-04-15 | 2021-04-19 | Michael | PP-764 |  | 19.75
Commonly Used | input.component.ts | 9.4.1 |  | 3.25 | 1.5 | -1 |  | 0.25 | 1.5 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 4, Sprint 5 | 2021-05-17 | 2021-05-17 | Chandan | PP-788 |  | 3.25
Filters - Location filters | location-filter.component.ts | 6.6 |  | 28.5 | 24 | 0.25 | 28.75 | 1.5 | 3 | 1 | Y | Some logic and tests might overlap with other filter components. | 97.62% | 87.5% | 97.79% | 97.67% | Sprint 6 | 2021-05-13 | 2021-05-18 | Chandan | PP-718 |  | 29.5
Commonly Used | logo.component.ts | 9.4.5 |  | 0.25 | 0 |  |  | 0.25 | 0 |  | Y | [5 empty] | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan | PP-782 |  | 0.25
Visualization Generation | node-details-list-row.component.ts | 3.5 | 2.4 | 0.75 | 0.25 | 0.25 | 1 | 0 | 0.5 |  | Y | Need to fix compile errors and check code coverage. | 100% | 100% | 100% | 100% | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-765 |  | 0.75
Visualization Generation | node-details-map.component.ts | 3.6 |  | 2 | 1.5 | -0.5 | 1.5 | 0 | 0.5 |  | Y | Some design tests were previously written but none for functionality. | 77.14% | 72.22% | 69.23% | 76.47% | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-766 |  | 2
Visualization Generation | link.component.ts | 3.1.1 | 2,2.1,2.4 | 7.5 | 6 | 0.5 | 8 | 0.5 | 1 | 1 | Y | Depends on how long it takes to write tests for HTML string creation. | 97.38% | 91.3% | 91.67% | 97.85% | Sprint 3 | 2021-03-25 | 2021-03-26 | Michael | PP-770 |  | 8.5
Label settings | tooltip.component.ts | 8.2.1 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-771 |  | 0
Visualization Generation | node-details-panel.component.ts | 3.7 |  | 1 | 0.5 |  | 1 | 0 | 0.5 |  | Y | Need to fix compile errors and check code coverage. | 100% | 75% | 100% | 100% | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-767 |  | 1
Filters - Location filters | o2-map-select-filter.component.ts | 6.6 |  | 38.25 | 35 | -6.25 | 32 | 1.25 | 2 | 2 | Y |  | 90.78% | 84.82% | 83.49% | 91.12% | Sprint 6 | 2021-05-05 | 2021-05-11 | Daya | PP-773 |  | 40.25
Filters - Convenience features | o2-list-button-filter.component.ts | 6.5 |  | 0 | 0 |  | 0 | 0 | 0 |  | Y | Already completed. Just verify TODOs. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-774 |  | 0
Filters - Convenience features | o2-filter-container.component.ts | 6.5 |  | 6.5 | 4 | 0 | 6.5 | 1 | 1.5 | 0.5 | Y |  | 96.23% | 86.67% | 95.45% | 97.12% | Sprint 6 | 2021-05-04 | 2021-05-04 | Daya | PP-775 |  | 7
Filters - Convenience features | o2-filter-button.component.ts | 6.7 |  | 2 | 0 |  | 2 | 2 | 0 |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 | Michael | PP-776 |  | 2
Visualization Generation | node-details-paragraph-list.component.ts | 3.9 |  | 0.5 | 0 |  | 0.5 | 0 | 0.5 |  | Y | Need to fix compile errors and check code coverage. | 100% | 100% | 100% | 100% | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-769 |  | 0.5
Visualization Generation | node-details-paragraph.component.ts | 3.8 |  | 1.5 | 1 | -0.25 | 1.25 | 0 | 0.5 |  | Y | Need to fix compile errors and check code coverage. | 85.71% | 66.67% | 100% | 85% | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-768 |  | 1.5
Commonly Used | o2-error-modal.component.ts | 9.4.6 |  | 0 | N/A |  | 0 | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-23 | 2021-03-25 |  | PP-779 |  | 0
Label settings | o2-droppable-container.component.ts | 8.5.1 |  | 2.75 | 2 | -0.75 | 2 | 0.75 | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-17 | 2021-05-17 | Michael | PP-780 |  | 2.75
Label settings | threshold-styles.component.ts | 8.9 |  | 0 | N/A |  |  | N/A | N/A |  | Y | All usage of this component is commented out. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-781 |  | 0
Visualization Generation | node-tooltip.component.ts | 3.2.4 | 2 | 2.25 | 0.25 | 0 | -0.25 | 1.5 | 0.5 |  | Y |  | 100% | 100% | 100% | 100% | Sprint 5 | 2021-04-19 | 2021-04-19 | Chandan | PP-711 |  | 2.25
Save or export Visualization | o2-export-details.component.ts | 13.7 |  | 2.5 | 1.5 | -0.25 | 2.25 | 1 | 0 | 0.25 | Y |  | 100% | 100% | 100 | 100% | Sprint 6 | 2021-05-11 | 2021-05-11 | Chandan | PP-777 |  | 2.75
Filters - Convenience features | sidenav.component.ts | 10.2 | 10 | 42.5 | 32.5 | 4.5 |  | 5 | 5 | 2.5 | Y |  | 97.85% | 89.38% | 96.46% | 98.12% | Sprint 7 | 2021-05-19 | 2021-05-28 | Michael | PP-784 |  | 45
Save or export Visualization | o2-export.component.ts | 13.8 |  | 1 | 0.25 | -0.5 | 0.5 | 0.5 | 0.25 | 0.33 | Y |  | 100 | 100 | 100 | 100 | Sprint 6 | 2021-05-11 | 2021-05-11 | Chandan | PP-778 |  | 1.33
Filters - Convenience features | o2-modal.component.ts | 7.8 |  | 0.5 | 0.5 | 0 | 0.5 | 0 | 0 |  | Y | Design tests previously written but some minor tests can be added for functionality. | 100 | 100 | 100 | 100 | Sprint 6 | 2021-05-11 | 2021-05-11 | Chandan | PP-772 |  | 0.5
Filters - Convenience features | o2-search-filter.component.ts | 7.7 |  | 1 | 0.5 | -0.25 | 0.75 | 0.5 | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 6 | 2021-05-11 | 2021-05-11 | Chandan | PP-758 |  | 1
Filters - Convenience features | o2-selected-filter.component.ts | 7.6 |  | 1 | 0.5 | -0.5 | 0.5 | 0.5 | 0 | 0.167 | Y |  | 100 | 100 | 100 | 100 | Sprint 6 | 2021-05-11 | 2021-05-11 | Chandan | PP-756 |  | 1.167
Commonly Used | select.component.ts | 9.4.2 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-789 |  | 0
Commonly Used | header.component.ts | 9.5.1 |  | 0 | N/A |  |  | N/A | N/A |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-790 |  | 0
Commonly Used | logout-modal.componeont.ts | 9.5.2 |  | 0 | N/A |  |  | N/A | N/A |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-791 |  | 0
Filters - Convenience features | chips.component.ts | 10.7 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-792 |  | 0
View Dashboard | o2-view-list.ts | 9.1 | 9 | 1.5 | 0 |  | 1.5 | 0 | 1.5 |  | Y | Unit tests completed but some improvements and DTOs can be added if time permits. |  |  |  |  | Sprint 7 | 2021-05-19 | 2021-05-19 | Chandan | PP-708 |  | 1.5
View Dashboard | report-name-input.component.ts | 9.7 |  | 2 | 1 | 0 |  | 0.5 | 0.5 | 0.75 | Y |  | 100 | 100 | 100 | 100 | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan | PP-783 |  | 2.75
Filters - Convenience features | fieldset-body.component | 10.5 |  | 0 | 0 |  |  | 0 | 0 |  | Y | Tests not required for this file. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-795 |  | 0
Filters - Convenience features | fieldset-header.component.ts | 10.4 |  | 0 | 0 |  |  | 0 | 0 |  | Y | Tests not required for this file. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-796 |  | 0
Filters - Convenience features | incremental-input.component.ts | 10.8 |  | 0 | N/A |  |  | N/A | N/A |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-797 |  | 0
Filters - Convenience features | state-button.component.ts | 10.9 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-798 |  | 0
Filters - Convenience features | tab.component.ts | 6.8 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-799 |  | 0
Filters - Convenience features | tabs.component.ts | 6.9 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-800 |  | 0
Commonly Used | o2-choice.component.ts | 9.5 |  | 0 | N/A |  |  | N/A | N/A |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-801 |  | 0
View Dashboard | card.component.ts | 9.6 | 9,9.1 | 0 | N/A |  |  | N/A | N/A |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-802 |  | 0
Visualization Generation | patients-label.component.ts | 3.2.1 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code and should be removed from the source code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-803 |  | 0
Visualization Generation | rate-label.component.ts | 3.2.2 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code and should be removed from the source code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-804 |  | 0
Visualization Generation | readmission-label.component.ts | 3.2.3 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code and should be removed from the source code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-805 |  | 0
Label settings | threshold-line.component.ts | 8.9.1 |  | 3 | 2.5 |  |  | 0.5 | 0 |  | Y | Discarded |  |  |  |  | Sprint 7 | 2021-05-17 | 2021-05-18 | Chandan | PP-806 |  | 3
Filters - Convenience features | o2-range-inputs.component.ts | 6.1.2 |  | 0 | N/A |  |  | N/A | N/A |  | Y | This component isn't used anywhere in the current code. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-807 |  | 0
Commonly Used | timeout-modal.component.ts | 9.5.3 |  | 2.5 | 1.75 |  |  | 0.5 | 0.25 |  | Y | Requirement tests are done but not functionality. Possibly some can be added with o2-test tag. |  |  |  |  | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan | PP-808 |  | 2.5

## Services
|  |  |  | 200.25 | [5 empty] | 14.58 | 156.5 | [10 empty] | 0
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Code Cleanup (Hrs) | Unit Test (Requirement) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id |  | time spent on task [h]
Authentication & Authorization | user.service.ts | 12.6 |  | 1.75 | 1.5 |  |  | 0.25 |  |  | Y | [5 empty] | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-809 |  | 1.75
Authentication & Authorization | click-capture.service.ts | 12.7 |  | 0.25 | 0.25 |  | 0.5 | 0 |  |  | Y | [5 empty] | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-810 |  | 0.25
Authentication & Authorization | common-layout.service.ts | 12.4 |  | 0.5 | 0.5 |  | 1 | 0 |  |  | Y | [5 empty] | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-811 |  | 0.5
Authentication & Authorization | http.service.ts | 12.1 |  | 2.5 | 2.5 |  | 5 | 0 |  |  | Y | Some tests can be copied from Admin Panel project but there are differences between each method still. |  |  |  |  | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-812 |  | 2.5
Commonly Used | logging.service.ts | 12.5 |  | 0 | 0 |  | 0 | 0 |  |  | Y | This file is empty. Can it be removed or updated? |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-813 |  | 0
Authentication & Authorization | session-timeout.service.ts | 12.3 |  | 2 | 2 |  | 4 | 0 |  |  | Y | Have to look into testing event merge and switchMap. | 93 | 83 | 87 | 93 | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-814 |  | 2
Authentication & Authorization | account.service.ts | 12.2 |  | 0.5 | 0.5 | 0 | 1 | 0 |  | 0.167 | Y |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-815 |  | 0.667
Dataset upload and management | datasets.service.ts | 11 |  | 0 | 0 |  | 0 | 0 |  |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-816 |  | 0
Filters - Entity filters | entity.service.ts | 7 |  | 2.5 | 1.5 |  | 4 | 1 |  | 1 | Y |  | 100% | 100% | 100% | 100% | Sprint 0 | 2021-03-25 | 2021-03-25 | Michael | PP-817 |  | 3.5
Filters - LOB filters | lob.service.ts | 15 |  | 0.25 | 0.25 |  | 0.5 | 0 |  |  | Y | Response models to be created. | 100% | 100% | 100% | 100% | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-818 |  | 0.25
Filters - Location filters | location.service.ts | 6 |  | 2 | 1.5 |  | 3.5 | 0.5 |  | 1 | Y | Response models to be created. | 100% | 100% | 100% | 100% | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-819 |  | 3
Filters - Service Line filters | service-line.service.ts | 8 |  | 3 | 2 |  | 5 | 1 |  | 1 | Y | Response models to be created. | 66.67% | 100% | 55.56% | 63.64% | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-820 |  | 4
Filters - Time filters | time.service.ts | 14.2 |  | 2 | 1.5 |  | 3.5 | 0.5 |  | 1 | Y | Response models to be created. | 100% | 100% | 100% | 100% | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-821 |  | 3
Visualization Generation | graph.service.ts (API-related) | 2.6 |  | 2.5 | 1.5 | 1.75 | 4 | 1 |  | 0.5 | Y | Response models to be created. | 100 | 100 | 100 | 100 | Sprint 4 | 2021-04-09 | 2021-04-09 | Daya | PP-822 |  | 3
Visualization Generation | custom-tooltip.service.ts | 12.5.4 |  | 1.5 | 0 |  | 1.5 | 1.5 |  |  | Y | Need to verify TODO for hideTooltip method. | [5 empty] | 2021-03-25 | 2021-03-25 |  | PP-823 |  | 1.5
Visualization Generation | shared.service.ts | 2 |  | 29 | 25 |  | 54 | 4 |  | 4 | Y | Code cleanup includes finding which methods aren't used anymore. A few of the large methods aren't used and can be removed or commented out so time isn't wasted and can be reduced from Unit Test hours. | 94.86% | 81.93% | 90.91% | 95.56% | Spirint 3 | 2021-03-25 | 2021-03-25 | Michael | PP-824 |  | 33
Filters - Convenience features | sidenav-breadcrumb.service.ts | 2.5 |  | 14 | 14 | -3.5 | 28 | 0 |  | 0.5 | Y |  | 97 | 86 | 97 | 98 | Sprint 7 | 2021-05-28 | 2021-05-29 | Chandan | PP-825 |  | 14.5
Filters - Convenience features | o2-tooltip.service.ts | 12.5.6 |  | 0.25 | 0 |  | 0.25 | 0.25 |  |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-05-25 | 2021-05-25 | Chandan | PP-826 |  | 0.25
Filters - Convenience features | tooltip.service | 12.5.3 |  | 3 | 3 | -1 | 6 | 0 |  | 0.75 | Y | Unsure how to write test for HTML string creation. | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-25 | 2021-05-25 | Chandan | PP-827 |  | 3.75
Visualization Generation | p2-tooltip.service.ts | 12.5.2 |  | 2.5 | 2.5 | -0.5 | 5 | 0 |  |  | Y | Unsure how to write test for HTML string creation. | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-25 | 2021-05-25 | Chandan | PP-828 |  | 2.5
Visualization Generation | graph-view.service.ts | 2.1 | 2 | 4 | 2 | 1.5 | 6 | 2 |  | 0.5 | Y | Half of file not used. Decent amount of linting to be done. | 96 | 100 | 87 | 96 | Sprint 4 | 2021-04-09 | 2021-04-09 | Daya | PP-829 |  | 4.5
Visualization Generation | map-view.service.ts | 2.2 | 2 | 2.5 | 1.5 | 1 | 4 | 1 |  | 0.5 | Y | Half of file not used. | 100 | 86 | 100 | 100 | Sprint 4 | 2021-04-09 | 2021-04-09 | Daya | PP-830 |  | 3
View Dashboard | o2-view-list.service.ts | 9 |  | 0 | 0 |  | 0 | 0 |  |  | Y | Already completed. | [5 empty] | 2021-03-25 | 2021-03-25 |  | PP-831 |  | 0
Dataset upload and management | select-dataset.service.ts | 11.1 |  | 2.5 | 1.5 |  | 4 | 1 |  |  | Y | [5 empty] | Sprint 6 | 2021-05-21 | 2021-05-21 | Chandan | PP-832 |  | 2.5
Filters - Entity filters | entity-filter.service.ts | 7.1 |  | 2.5 | 1.5 |  | 4 | 1 |  |  | Y | Majority of file not used. | 100% | 100% | 100% | 100% |  | 2021-03-25 | 2021-03-25 |  | PP-833 |  | 2.5
Filters - Location filters | location-filter.service.ts | 6.1 |  | 4 | 2 |  | 6 | 2 |  |  | Y | Some overlap with LocationService file with similar named functions. This is somewhat confusing when using across the project. | 90.48% | 94.12% | 71.43% | 90.24% | Sprint 6 | 2021-05-19 | 2021-05-19 | Daya | PP-834 |  | 4
Filters - Service Line filters | service-line-filter.service.ts | 8.1 |  | 2.5 | 1.5 |  | 4 | 1 |  | 1 | Y | Majority of file not used. | 100% | 100% | 100% | 100% | Sprint 6 | 2021-05-17 | 2021-05-17 | Daya | PP-835 |  | 3.5
Filters - Time filters | time-filter.service.ts | 14.1 |  | 0.5 | 0 |  |  | 0.5 |  |  | Y | File is more or less empty (commented out). It can be removed or cleaned up. |  |  |  |  | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-836 |  | 0.5
Commonly Used | validation.service.ts | 12.8 |  | 0.5 | 0 |  |  | 0.5 |  |  | Y | Updates to file need to be copied over from Admin Panel repo and ran with updated import paths. |  |  |  |  | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-837 |  | 0.5
Dataset upload and management | data-statisticcase.service.ts | 11.2 |  | 0 | N/A |  |  | N/A |  |  | Y | Service not used anywhere. | [5 empty] | 2021-03-25 | 2021-03-25 | Chandan | PP-838 |  | 0
Visualization Generation | shareview.service.ts | 11.3 |  | 0 | N/A |  |  | N/A |  |  | Y | Nothing in this file is being used. | [5 empty] | 2021-03-25 | 2021-03-25 | Chandan | PP-839 |  | 0
Save or export Visualization | export.service.ts | 13 |  | 64 | 60 |  |  | 4 |  |  | Y | [5 empty] | Sprint 6 | 2021-05-19 | 2021-05-28 | Daya | PP-840 |  | 64
Label settings | drag-and-drop.service.ts | 8.5 |  | 2 | 2 |  |  | 0 |  |  | Y | [5 empty] | Sprint 7 | 2021-05-21 | 2021-05-21 | Chandan | PP-841 |  | 2
Visualization Generation | link-selection.service.ts | 2.1.2 |  | 1 | 0.75 | 0 | 1.75 | 0.25 |  |  | Y |  | 100% | 100% | 100% | 100% | Sprint 3 | 2021-03-26 | 2021-03-26 | Michael | PP-842 |  | 1
Visualization Generation | query-data.service.ts | 2.3 |  | 6 | 5 | 0 |  | 1 |  | 1.25 | Y | Some code cleanup done when working with Node, Link, and Node Graph components. | 99 | 85 | 96 | 99 | Sprint 4 | 2021-04-08 | 2021-04-08 | Daya | PP-843 |  | 7.25
Filters - Convenience features | sidenav.service.ts | 10 |  | 0.5 | 0.25 | 0 |  | 0.25 |  |  | Y |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-25 | 2021-05-25 | Chandan | PP-844 |  | 0.5
Commonly Used | google-analytics.service.ts | 12.1.4 |  | 1 | 1 |  |  | 0 |  |  | Y | [5 empty] | Sprint 7 | 2021-05-21 | 2021-05-21 | Chandan | PP-845 |  | 1
Benchmark settings customization & Benchmark Calculation | benchmark.service.ts | 2.1.1 | 2,2.3,2.4 | 15 | 14 | -1.75 |  | 1 |  | 1 | Y |  | 89 | 80 | 88 | 88 | Sprint 5 | 2021-04-21 | 2021-04-23 | Daya | PP-846 |  | 16
Filters - LOB filters | lob-filter.service.ts | 14.2 |  | 3.5 | 3 |  |  | 0.5 |  |  | Y | Discarded |  |  |  |  | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-847 |  | 3.5
Filters - LOB filters | quality-filter.service.ts | 14.3 |  | 2 | 1.5 |  |  | 0.5 |  |  | Y | Quality Filter not enabled in current P2. |  |  |  |  | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-848 |  | 2
Dataset upload and management | data-statistic.service.ts | 11.1 |  | 0 | N/A |  |  | N/A |  |  | N | Not being used. | [5 empty] | 2021-03-25 | 2021-03-25 | Chandan | PP-849 | 0 | 0
Visualization Generation | graph-node.service.ts (Graph Interaction) | 2.1.2 |  | 8 | 7 | 0 |  | 1 |  |  | Y | Not entirely sure how to test logic which has d3 dependencies. | 74.86% | 80.71% | 62.5% | 73.99% | Sprint 4 | 2021-05-11 | 2021-04-11 | Michael | PP-850 |  | 8
Commonly Used | data-storage.service.ts | 12.1.3 |  | 0 | N/A |  |  | N/A |  |  | N | No tests required for this file. | [5 empty] | 2021-03-25 | 2021-03-25 | Chandan | PP-851 | 0 | 0
View Dashboard | views.service.ts | 9.1.2 |  | 2.25 | 2 | -0.25 |  | 0.25 |  | 0.33 | Y |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-21 | 2021-05-21 | Daya | PP-852 |  | 2.58
Commonly Used | graphql-common.service.ts | 12.5.1 |  | 0.25 | 0 | 0 |  | 0.25 |  |  | Y | Need to copy over from Admin Panel. | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-21 | 2021-05-21 | Daya | PP-853 |  | 0.25
Commonly Used | p2.service.ts | 12.1.3 |  | 3.25 | 3 | 0 |  | 0.25 |  |  | Y |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-21 | 2021-05-21 | Daya | PP-854 |  | 3.25
Save or export Visualization | png.service.ts | 13.1 |  | 1 | 0.5 | 0 |  | 0.5 |  | 0.083 | Y |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-05-24 | 2021-05-24 | Chandan | PP-855 |  | 1.083
Commonly Used | data-access.service.ts | 12.1.1 |  | 1.25 | 1.25 |  |  | 0 |  |  | Y | [5 empty] | Sprint 7 | 2021-05-24 | 2021-05-24 | Chandan | PP-856 |  | 1.25
Commonly Used | storage.service.ts | 12.1.2 |  | 0.25 | 0 |  |  | 0.25 |  |  | Y | Need to copy over from Admin Panel. |  |  |  |  | Sprint 7 | 2021-05-24 | 2021-05-24 | Chandan | PP-857 |  | 0.25

## Utilities
|  |  |  | 192.75 | [5 empty] | 9.11 | 182.25 | [10 empty] | 10.5
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | Code Cleanup (Hrs) | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id |  | time spent on task [h]
Visualization Generation | axes.utils.ts | 5.7 |  | 2 | 1.5 | 0 | 0.5 |  |  | 0.25 | Y |  | 100 | 95 | 100 | 100 | Sprint 5 | 2021-04-19 | 2021-04-19 | Daya | PP-858 |  | 2.25
Visualization Generation | axesareas.utils.ts | 5.8 |  | 6.5 | 6 | 0.5 | 0.5 |  |  | 0.5 | Y | Look into unit testing D3. | 100 | 100 | 100 | 100 | Sprint 5 | 2021-04-20 | 2021-04-20 | Daya | PP-859 |  | 7
Visualization Generation | benchmark.utils.ts | 2.7 |  | 8.5 | 8 | -4 | 0.5 |  |  | 0.5 | Y | Look into unit testing D3. | 100% | 92.86% | 100% | 100% | Sprint 5 | 2021-04-21 | 2021-04-22 | Michael | PP-860 |  | 9
Visualization Legend | legends.utils.ts | 5.6 |  | 5 | 5 | 0 | 0 |  |  | 0.75 | Y |  | 95 | 81 | 95 | 97 | Sprint 6 | 2021-04-26 | 2021-04-26 | Daya | PP-861 |  | 5.75
Visualization Generation | quadrants.utils.ts | 5.1 |  | 2.25 | 2 | -0.25 | 0.25 |  |  | 0.5 | Y | Look into unit testing D3. | 100 | 100 | 100 | 100 | Sprint 5 | 2021-04-21 | 2021-04-21 | Daya | PP-862 |  | 2.75
Visualization Generation | renderEntity.utils.ts | 5 | 2,2.1.1 | 19 | 18 | -0.5 | 1 |  |  | 1.08 | Y | Look into unit testing D3. | 91 | 87 | 80 | 91 | Sprint 5 | 2021-04-22 | 2021-04-26 | Daya | PP-863 |  | 20.08
Visualization Generation | request2D.utils.ts | 5.4 |  | 6 | 6 | 0.5 | 0 |  |  | 0.8 | Y |  | 97 | 83 | 83 | 97 | Sprint 5 | 2021-04-21 | 2021-04-21 | Daya | PP-864 |  | 6.8
Visualization Generation | shapes.utils.ts | 5.3 |  | 1 | 1 | 0 | 0 |  |  |  | Y |  | 100 | 100 | 100 | 100 | Sprint 5 | 2021-04-19 | 2021-04-19 | Daya | PP-865 |  | 1
Visualization Generation | stacking.utils.ts | 5.2 |  | 40 | 35 | -24 | 5 |  |  | 1.58 | Y | This contains all of the 2D graph stacking logic which is fairly complex. | 100 | 100 | 100 | 100 | Sprint 6 | 2021-04-26 | 2021-05-03 | Daya | PP-866 |  | 41.58
Visualization Generation | title.utils.ts | 5.9 |  | 2 | 1.5 | 0 | 0.5 |  |  |  | Y | Single method that isn't called anywhere. | 100 | 100 | 100 | 100 | Sprint 5 | 2021-04-19 | 2021-04-19 | Daya | PP-867 |  | 2
Visualization Generation | node-graph.utils.ts | 2.4 | 2,2.3 | 60 | 55 | -21.75 | 5 |  |  | 2 | Y |  | 83.96% | 80.85% | 89.3% | 84.92% | Sprint 3, Sprint 4 | 2021-03-30 | 2021-04-12 | Michael | PP-868 |  | 62
Visualization Navigation | o2-context-menu.utils.ts | 11 |  | 0 | 0 |  | 0 |  |  |  | Y | Already completed. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-869 |  | 0
Filters - Location filters | location-filter.utils.ts | 6.2 |  | 10 | 8.5 | -0.5 | 1.5 |  |  | 0.5 | Y |  | 99 | 94 | 96 | 95 | Sprint 6 | 2021-05-12 | 2021-05-13 | Daya | PP-870 |  | 10.5
Filters - Time filters | time-filter.utils.ts | 14.3 |  | 0.5 | 0.5 | 0 | 0 |  |  |  | Y |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-06-09 | 2021-06-10 | Michael | PP-871 |  | 0.5
Commonly Used | logout.utils.ts | 10 |  | 0.5 |  |  | 0.5 |  |  |  | N | Copy over tests from Admin Panel and verify code coverage. | 100 | 100 | 100 | 100 | Sprint 7 | 2021-06-04 | 2021-06-04 | Chandan | PP-872 | 0.5 | 0
Visualization Generation | graph.utils.ts | 2.8 |  | 1.5 | 1.25 | -0.25 | 0.25 |  |  | 0.15 | Y |  | 100% | 100% | 100% | 100% | Sprint 4 | 2021-04-13 | 2021-04-13 | Michael | PP-873 |  | 1.65
Visualization Generation | p2-filters.utils | 2.9 |  | 4 | 3.5 | -1 | 0.5 |  |  | 0.25 | Y |  | 86.05% | 85% | 86.36% | 85.94% | Sprint 4 | 2021-04-14 | 2021-04-14 | Michael | PP-874 |  | 4.25
Visualization Generation | query-data.utils.ts | 2.3.1 |  | 4 | 3.5 | -1 | 0.5 |  |  | 0.25 | Y |  | 100% | 82.35% | 100% | 100% | Sprint 4 | 2021-04-13 | 2021-04-13 | Michael | PP-875 |  | 4.25
Commonly Used | user.utils.ts | 12.1.4 |  | 5 | 4.5 | 0 | 0.5 |  |  |  | Y |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-06-07 | 2021-06-07 | Chandan | PP-876 |  | 5
Commonly Used | data-storage.utils.ts | 12.1.5 |  | 3.5 | 3 |  | 0.5 |  |  |  | N |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-06-07 | 2021-06-08 | Chandan | PP-877 | 3.5 | 0
Dataset upload and management | datasets.utils.ts | 11.3 |  | 6.5 | 6 |  | 0.5 |  |  |  | N | [5 empty] | Sprint 7 | 2021-06-09 | 2021-06-10 | Michael | PP-878 | 6.5 | 0
View Dashboard | views.utilts.ts | 9.2 |  | 0 | N/A |  | N/A |  |  |  | Y | Already completed. | 100% | 100% | 100% | 100% | Sprint 0 | 2021-03-23 | 2021-03-26 | Chandan | PP-879 |  | 0
Commonly Used | client.utils.ts | 12.1.6 |  | 1 | 0.5 | 0.5 | 0.5 |  |  |  | Y | I believe most can be copied over and verified from Admin Panel. | 97 | 97 | 93 | 98 | Sprint 7 | 2021-06-08 | 2021-06-08 | Chandan | PP-880 |  | 1
Commonly Used | session.utils.ts | 12.1.7 |  | 4 | 3.5 | -1 | 0.5 |  |  |  | Y |  | 100 | 100 | 100 | 100 | Sprint 7 | 2021-06-08 | 2021-06-08 | Chandan | PP-881 |  | 4

## Pipes
|  |  |  | 13.25 | [5 empty] | 0 | 13.25 | [10 empty] | 0
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id
Filters - Convenience features | breadcrumb-button-order.pipe.ts | 12.6.7 |  | 3.5 | 3.5 | -0.25 |  |  | 0 |  | Y | Should unused methods have tests written? | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-882 |  | 3.25
Visualization Legend | benchmark-legend.pipe.ts | 12.6.8 |  | 0.25 | 0.25 | 0 |  |  | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-883 |  | 0.25
Commonly Used | counter-to-array.pipe | 12.6.5 |  | 0.25 | 0.25 | 0 |  |  | 0 |  | Y | I don't believe this is used anywhere. | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-884 |  | 0.25
Filters - Convenience features | filter-tag.pipe.ts | 12.6.4 |  | 1.5 | 1.5 | 0 |  |  | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-885 |  | 1.5
Benchmark settings customization & Benchmark Calculation | iterate-over-object.pipe.ts | 7.5.2 |  | 0.25 | 0.25 | 0 |  |  | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-886 |  | 0.25
Visualization Generation | parent-child-order.pipe.ts | 12.6.4 |  | 2 | 1.5 | -0.25 |  |  | 0.5 |  | Y | Possibly remove lodash package? | 100 | 93 | 100 | 100 | Sprint 4 | 2021-04-13 | 2021-04-13 | Michael | PP-887 |  | 1.75
Visualization Generation | rate-cost-item.pipe.ts | 12.6.3 |  | 0.75 | 0.75 | 0 |  |  | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 4 | 2021-04-13 | 2021-04-13 | Michael | PP-888 |  | 0.75
Filters - Time filters | time-filter-order.pipe.ts | 14.1.1 |  | 1.5 | 1 | -0.25 |  |  | 0.5 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-889 |  | 1.25
Label settings | label-style.pipe.ts | 8.6 |  | 0.5 | 0.25 | 0 |  |  | 0.25 |  | Y | Not used in code anywhere. | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-890 |  | 0.5
Benchmark settings customization & Benchmark Calculation | o2-autocomplete-search-filter.pipe.ts | 7.5.1 |  | 1 | 1 | 0 |  |  | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-891 |  | 1
Filters or Visualization Navigation Convenience features | o2-bread-crumb.pipe.ts | 12.6.2 |  | 0.25 | 0.25 | 0 |  |  | 0 |  | Y | Not used in code anywhere. | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-892 |  | 0.25
Visualization Generation | validate-value.pipe.ts | 12.6.1 |  | 0.25 | 0.25 | 0 |  |  | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 4 | 2021-04-13 | 2021-04-13 | Michael | PP-893 |  | 0.25
Graph sorting setting options | order-style.pipe.ts | 12.6.9 |  | 0.75 | 0.5 | 0 |  |  | 0.25 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-894 |  | 0.75
Save or export Visualization | kebab-case.pipe.ts | 13.4 |  | 0 | N/A |  |  |  | N/A |  | Y | I believe this is fully tested. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-895 |  | 0
Save or export Visualization | sentence-case.pipe.ts | 13.5 |  | 0 | N/A |  |  |  | N/A |  | Y | I believe this is fully tested. |  |  |  |  | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-896 |  | 0
Filters - Geography (Location) filters | o2-radius-to-miles-pipe.ts | 7.2 |  | 0 | N/A | 0.5 |  |  | N/A |  | Y | Not used in code anywhere. | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-897 |  | 0.5
Dataset upload and management | search-filter.pipe.ts | 11.1.1 |  | 0.5 | 0.5 | 0 |  |  | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 |  | PP-898 |  | 0.5

## Directives
|  |  |  | 14.5 | [5 empty] | 0 | 14.5
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id
Label settings | draggable.directive.ts [ediDraggableNode] | 8.7 |  | 1 | 1 | 0 |  |  | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 8 | 2021-06-11 | 2021-06-11 | Michael | PP-899 | Abandoned | 1
Label settings | draggable.directive.ts [o2Draggable] | 8.8 |  | 3 | 3 | 0 |  |  | 0 |  | Y |  | 94 | 100 | 77 | 93 | Sprint 8 | 2021-06-11 | 2021-06-11 | Michael | PP-900 | Abandoned | 3
Label settings | droppable.directive.ts | 8.9 |  | 5 | 5 | -1 |  |  | 0 |  | Y |  | 79 | 83 | 89 | 80 | Sprint 8 | 2021-06-11 | 2021-06-14 | Michael | PP-901 | Abandoned | 4
Commonly Used | autofocus.directive.ts [p2Autofocus] | 16.1 |  | 1.25 | 1.25 | 0 |  |  | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 8 | 2021-06-08 | 2021-06-08 | Chandan | PP-902 | Abandoned | 1.25
Commonly Used | click-redirect.directive.ts [p2ClickRedirect] | 16.2 |  | 1.25 | 1 | 0 |  |  | 0.25 |  | Y |  | 100 | 96 | 100 | 100 | Sprint 8 | 2021-06-08 | 2021-06-08 | Chandan | PP-903 | Abandoned | 1.25
Commonly Used | o2-click-outside.directive.ts | 16.3 |  | 0 | N/A | 0.25 |  |  | N/A |  | Y | Already completed. | 100 | 100 | 100 | 100 | Sprint 0 | 2021-03-25 | 2021-03-25 | Chandan | PP-904 | Abandoned | 0.25
Commonly Used | scroll.directive.ts [p2TrackScroll] | 16.4 |  | 1.5 | 0.5 | -0.25 |  |  | 1 |  | Y | Compare with cleaned/updated version in Admin Panel. | 100 | 100 | 100 | 100 | Sprint 8 | 2021-06-08 | 2021-06-08 | Chandan | PP-905 | Abandoned | 1.25
Visualization Generation | zoomable.directive.ts | 16.7 |  | 0.5 | 0.5 | 0 |  |  | 0 |  | Y |  | 100 | 100 | 100 | 100 | Sprint 8 | 2021-06-08 | 2021-06-08 | Chandan | PP-906 | Abandoned | 0.5
Commonly Used | clickable.directive.ts | 16.8 |  | 1 | 1 | 0 |  |  | 0 |  | Y | Have to look into testing timer Observable. | 95 | 100 | 85 | 95 | Sprint 8 | 2021-06-08 | 2021-06-08 | Chandan | PP-907 | Abandoned | 1

## Misc.
|  |  |  | 21.5 | [6 empty] | 19.25
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Cleanup (Story Points) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id
Commonly Used | error.handler.ts | 12.7 |  | 2 | 2 | 0 |  |  | Refactor to match updated handler in Admin Panel? |  | Y | Have to look into testing error handler methods. | 100 | 100 | 100 | 100 | Sprint 8 | 2021-06-11 | 2021-06-11 | Chandan | PP-908 | 2
Commonly Used | http.interceptor.ts | 12.7.2 |  | 1.5 | 1.5 | 0 |  |  | Refactor to match updated interceptor in Admin Panel? |  | Y | Have to look into testing interceptors. | 92 | 83 | 100 | 91 | Sprint 8 | 2021-06-11 | 2021-06-11 | Chandan | PP-909 | 1.5
Commonly Used | validators.ts | 12.7.3 |  | 2.25 | 2 | -0.25 |  |  | 0.25 |  | Y | Updates to file need to be copied over from Admin Panel repo first. | 100 | 100 | 100 |  | Sprint 8 | 2021-06-11 | 2021-06-11 | Chandan | PP-910 | 2
Visualization Generation | arc.helper.ts | 12.7.4 |  | 2.75 | 2.5 | 0 |  |  | 0.25 |  | Y | Unsure how much of this can be tested since it's just a file of variables as functions. | 100 | 93 | 100 | 100 | Sprint 9 | 2021-06-16 | 2021-06-16 | Daya | PP-911 | 2.75
Visualization Generation | size.helper.ts | 12.7.5 |  | 0 | N/A | 1 |  |  | N/A |  | N | Unsure how these would be tested. | 50 | 100 | 50 | 50 | Sprint 0 | 2021-03-24 | 2021-03-24 | Chandan | PP-912 | 0
Visualization Generation | transition.helper.ts | 12.7.6 |  | 2.5 | 2 | 0 |  |  | 0.5 |  | Y | Unsure how much of this can be tested since it's just a file of variables as functions. | 95 | 85 | 100 | 95 | Sprint 9 | 2021-06-15 | 2021-06-15 | Michael | PP-913 | 2.5
Visualization Generation | distribution-map.dto.ts | 12.7.7 |  | 2.25 | 2 | -0.25 |  |  | 0.25 |  | N |  | 94 | 77 | 85 | 93 | Sprint 9 | 2021-06-15 | 2021-06-15 | Michael | PP-914 | 0
Visualization Generation | graph-details.dto.ts | 12.7.8 |  | 4 | 3.5 | -1.5 |  |  | 0.5 |  | Y |  | 100 | 96 | 100 | 100 | Sprint 9 | 2021-06-15 | 2021-06-15 | Michael | PP-915 | 2.5
Visualization Generation | legend-label.dto.ts | 12.7.9 |  | 0.75 | 0.75 | 0 |  |  |  |  | Y |  | 100 | 100 | 100 | 100 | Sprint 9 | 2021-06-16 | 2021-06-16 | Daya | PP-916 | 0.75
Visualization Generation | o2-base-chart.dto.ts | 12.7.1 |  | 3.5 | 3 | 0 |  |  | 0.5 |  | Y |  | 95 | 92 | 81 | 100 | Sprint 9 | 2021-06-16 | 2021-06-16 | Daya | PP-917 | 3.5

## Auth0
|  |  |  | 129 | [5 empty] | 0 | 34.5 | [10 empty] | 49
Category | File Name | Priority | Depends On | Estimation (Hours) | Unit Tests (Hours) | Extra hour taken(Actual vs Planned) | ACTUAL Total Coding Hours Spent | Unit Test (Requirement) | Code Cleanup (Hrs) | Code Review (Hrs) | Completed | Additional Notes | Statements | Branches | Functions | Lines | Sprint | Start Date | End Date | Assignee | Jira Id |  | time spent on task [h]
Authentication & Authorization | Create sample application in Auth0 as SPA | 1.8.1 | [8 empty] | Y | [5 empty] | Sprint 4 |  |  | Chandan | PP-933 |  | 0
Authentication & Authorization | @auth0/auth0-angular library integration with p2 | 1.8.2 | [8 empty] | Y | [5 empty] | Sprint 4 |  |  | Chandan | PP-918 |  | 0
Authentication & Authorization | Create login authentication with Auth0 and retreive the token | 1.8.3 |  | 6 |  | 1 | 7 |  |  |  | Y | [5 empty] | Sprint 3 | 2021-04-02 | 2021-04-02 | Chandan | PP-919 |  | 7
Authentication & Authorization | Configure audience details in auth0 | 1.8.4 |  | 8 |  | -0.5 | 7.5 |  |  |  | Y | [5 empty] | Sprint 4 | 2021-04-05 | 2021-04-05 | Chandan | PP-920 |  | 7.5
Authentication & Authorization | Get the access token with audience info | 1.8.5 | 1.8.1 | 6 |  | 2 | 8 |  |  |  | Y | [5 empty] | Sprint 4 | 2021-04-06 | 2021-04-06 | Chandan | PP-921 |  | 8
Authentication & Authorization | Use Auth0 classic login page to customize to make it closure to our login UI | 1.8.6 |  | 12 |  | -11 | 1 |  |  |  | Y | [5 empty] | Sprint 4 | 2021-04-07 | 2021-04-09 | Chandan | PP-922 |  | 1
Authentication & Authorization | Write an interceptor to use the access token and send it across to API call | 1.8.7 |  | 10 | [6 empty] | Y | [8 empty] | Chandan | PP-923 |  | 0
Authentication & Authorization | Sample component which call Rep0 tokenort view API with valid Auth0 token | 1.8.8 |  | 4 | [6 empty] | Y | [5 empty] | Sprint 4 | 2021-04-12 | 2021-04-12 | Chandan | PP-924 |  | 0
Authentication & Authorization | Validate token at BE code for authorization | 1.9.1 | 1.8.5 | 4 | [6 empty] | Y | [5 empty] | Sprint 4 | 2021-04-06 | 2021-04-06 | Kamil | PP-925 |  | 0
Authentication & Authorization | Write util/decorator at BE to validate authorization for each API call | 1.9.2 |  | 8 | [6 empty] | Y | [5 empty] | Sprint 4 | 2021-04-06 | 2021-04-07 | Kamil | PP-926 |  | 0
Authentication & Authorization | Write HttpInterceptor at FE to send Auth0 token to each API call. | 1.9.3 |  | 10 | [6 empty] | Y | [5 empty] | Sprint 4 | 2021-04-12 | 2021-04-13 | Chandan | PP-927 |  | 0
Authentication & Authorization | Use AuthGaurd to protect component from unauthorize access | 1.9.3 |  | 12 |  | -1 | 11 |  |  |  | Y | [5 empty] | Sprint 5 | 2021-04-27 | 2021-04-28 | Chandan | PP-928 |  | 11
Authentication & Authorization | Use customized Login screen for Auth0 login integration | 1.9.4 | [8 empty] | N | [8 empty] | Chandan | PP-929 | 0 | 0
Authentication & Authorization | Implement forgot/reset password | 1.9.5 |  | 6 | [6 empty] | N | [5 empty] | Sprint 5 | 2021-05-07 | 2021-05-07 | Chandan | PP-930 | 6 | 0
Authentication & Authorization | UI changes for forgot password | 1.9.6 |  | 12 | [6 empty] | N | [5 empty] | Sprint 6 | 2021-05-13 | 2021-05-14 | Chandan | PP-931 | 12 | 0
Authentication & Authorization | How to configure different environments with different configurations | 1.9.7 |  | 16 | [6 empty] | N | [5 empty] | Sprint 7 | 2021-05-17 | 2021-05-18 |  | PP-932 | 16 | 0
Authentication & Authorization | Identify authenticaction related APIs used in existing application |  |  | 3 | [6 empty] | N | [5 empty] | Sprint 6 | 2021-05-14 | 2021-05-14 | Chandan |  | 3 | 0
Authentication & Authorization | Use refresh token from Authentication module and change the existing code to use new Auth module |  |  | 12 | [6 empty] | N | [5 empty] | Sprint 6 | 2021-05-12 | 2021-05-13 | Chandan |  | 12 | 0