## Description
Design document: | https://docs.google.com/document/d/1wZsXl8XMl21V3WNjHIGPi_brwDXqoCBx7Pxdo1Abudo/edit#
Jira project: | P2 next gen (PP)
Jira label: | P2_pipelines
Number of tasks: | 124
Number of reported bugs: | 1
Total planned development worktime [h]: | 649
Planned development worktime of finished tasks [h]: | 641
Current worktime spent [h]: | 436.5833
Planned time to finish project [h]: | 8
Project completeness based on planned worktime [%]: | 98.7673
Current worktime vs planned worktime [%]: | 68.1097 | > 100% - delay; < 100% - ahead
Last update | Jun 18, 2021 16:23:19
Number of updated tasks (during last update) | 0

## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  |  | Developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment | Category | Version
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | AWS Lambda | see design | [11 empty] | PP-328 |  | Sprint 5 |  | Dataset upload and management | MVP | 0
1.1 | Set up the empty o2-grouper-lambda project | prepare the dev / qa / release branches, use p2-backend-v3 as template |  | 6 | 0.5 | 1 | 1 | Adrian Z. | March 5, 2021, 10:52 AM | March 5, 2021, 11:24 AM | 0.5 | 721 | 1 | PP-329 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/commit/6e6f779574b800e2cd18cf806f01585869a33c88 | Sprint 2 |  | Dataset upload and management | MVP | 1
1.2 | Create AWS lambda o2-grouper function | dev / qa / release versions |  | 3 | 3 | 4 | 4 | Adrian Z. | March 5, 2021, 11:30 AM | March 5, 2021, 4:14 PM | 5 | 9 | 0 | PP-330 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/1 | Sprint 2 |  | Dataset upload and management | MVP | 4
1.3 | Create the API o2-grouper endpoints | dev / qa / release versions | 1.2 | 4 | 4 | 4 | 4 | Adrian Z. | March 8, 2021, 12:16 PM | March 8, 2021, 1:16 PM | 1 |  |  | PP-331 | - | Sprint 2 | No any commits - setup of AWS. | Dataset upload and management | MVP | 4
1.4 | Set up the CI/CD pipeline | deploy to AWS lambda | 1.1 - 1.2 | 6 | 8 | 8 | 8 | Adrian Z. | March 5, 2021, 4:47 PM | March 9, 2021, 2:34 PM | 15 | 35 | 8 | PP-332 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/5 | Sprint 2 |  | Dataset upload and management | MVP | 8
1.5 | Implement configuration validation |  | 1.4 | 4 | 4 | 6 | 6 | Adrian Z. | March 16, 2021, 11:19 AM | March 16, 2021, 4:53 PM | 5.5 | 360 | 1 | PP-333 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/10 | Sprint 2 |  | Dataset upload and management | MVP | 6
1.6 | Implement creation of pipeline description object | create from validated configuration | 1.5, 1.9 | 3 | 4 | 4 | 4 | Adrian Z. | Mar 18, 2021 09:22:59 | Mar 18, 2021 12:35:31 | 2 | 109 | 1 | PP-334 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/12 | Sprint 2 |  | Dataset upload and management | MVP | 4
1.7 | Register new pipeline in the database (or find existing) |  | 1.6, 3.1 | 3 | 3 | 2 | 2 | Adrian Z. | April 16, 2021, 3:28 PM | April 20, 2021, 5:00 PM | 9.5 | 327 | 42 | PP-335 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/15 | Sprint 5 |  | Dataset upload and management | MVP | 2
1.8 | Initiatie the pyspark job (databricks) |  | 1.7, 3.2 | 8 | 8 | 12 | 12 | Adrian Z. | March 15, 2021, 9:47 AM | March 16, 2021, 10:20 AM | 9 | 77 | 5 | PP-336 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/9 | Sprint 2 |  | Dataset upload and management | MVP | 12
1.9 | Auth token validation | extract user_id from token | 1.4 | 6 | 4 | 2 | 2 | Adrian Z. | Mar 16, 2021 14:59:26 | Mar 17, 2021 09:12:19 | 4 | 138 | 1 | PP-337 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/11 | Sprint 2 |  | Dataset upload and management | MVP | 2
1.10 | Protect AWS lambda | needs to validate AWS access key before launching |  | 8 | 8 |  | 8 | Adrian Z. | April 12, 2021, 12:57 PM | April 13, 2021, 4:48 PM | 12.25 |  |  | PP-935 | - | Sprint 4 | Added to sprint in Sprint 4 | Dataset upload and management | MVP | 8
1.11 | AWS Lambda configuration | allow passing configuration and user token to initiate a pipeline |  | 8 | 6 |  | 8 | Adrian Z. | April 9, 2021, 11:36 AM | April 12, 2021, 12:56 PM | 5.25 | 51.5 | 11 | PP-936 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/13 | Sprint 4 | Added to sprint in Sprint 4 | Dataset upload and management | MVP | 8
1.12 | AWS Lambda error handling | format error response objects |  | 6 | 3 |  | 6 | Adrian Z. | April 12, 2021, 12:57 PM | April 12, 2021, 12:08 PM | 2.75 | 51.5 | 11 | PP-937 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/13 | Sprint 4 | Added to sprint in Sprint 4 | Dataset upload and management | MVP | 6
1.13 | Add run_id column in pipeline repository | register both job_id and run_id for started jobs |  | 2 |  |  | 2 | Adrian Z. | May 12, 2021 10:33:53 | May 13, 2021 07:19:50 | 1 |  |  | PP-1357 |  | Sprint 6 |  | Dataset upload and management | MVP | 2
1.14 | Refactor configuration to match design, use shared app_config library | configure access variables in AWS secrets manager | P2/4 | 12 |  |  |  | Adrian Z. | June 2, 2021, 12:04 PM | June 7, 2021, 10:24 AM | 14.25 |  |  | PP-1455 |  | Sprint 8 |  | Dataset upload and management | 1
1.15 | Pass job_settings to o2-grouper-job | see design | 1.14 | 3 |  |  | 3 | Adrian Z. | May 31, 2021 09:34:08 | Jun 07, 2021 09:06:19 | 1.6667 |  |  | PP-1456 |  | Sprint 8 |  | Dataset upload and management | MVP | 3
2 | Pipeline Database | [12 empty] | PP-338 |  | Sprint 7 |  | Dataset upload and management | MVP | 0
2.1 | Set up dev / qa / release databases (postgres/aurora) | can use existing instances, create public schema for pipelines |  | 4 | 4 | 4 | 4 | Adrian Z. | [5 empty] | PP-339 |  | Sprint 7 | Partially done - only in dev environment | Dataset upload and management | MVP | 0
3.1 | O2 Grouper Job | [12 empty] | PP-340 |  | Sprint 2 |  | Dataset upload and management | MVP | 0
3.1.2 | Set up the empty o2-grouper-job project in python |  |  | 4 | 0.5 | 1 | 1 | Adrian Z. | March 5, 2021, 10:51 AM | March 5, 2021, 11:23 AM | 0.5 | 721 | 1 | PP-341 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/commit/6e6f779574b800e2cd18cf806f01585869a33c88 | Sprint 2 |  | Dataset upload and management | MVP | 1
3.1.3 | Prepare the CI/CD pipelines for the o2-grouper-job project | Must be deployed to databricks | 3.1 | 16 | 16 | 20 | 20 | Adrian Z. | March 9, 2021, 3:22 PM | March 11, 2021, 9:15 AM | 14 | 30 | 1 | PP-342 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/commit/6e6f779574b800e2cd18cf806f01585869a33c88 | Sprint 2 |  | Dataset upload and management | MVP | 20
3.1.4 | Refactor configuration to match design | Read access variables from job_settings object | 1.15 | 4 |  |  | 4 | Adrian Z. | [5 empty] | PP-1457 |  | Sprint 9 |  |  | MVP | 0
3.3 | Repository | see design | [11 empty] | PP-343 |  | Sprint 3 |  | Dataset upload and management | MVP | 0
3.3.1 | Define AbstractRepository and implement MockRepository (in-memory) | only implement the methods: add_pipeline, add_artifact, find_artifact in the MockRepository |  | 10 | 12 | 16 | 16 | Adrian Z. | Mar 19, 2021 09:07:40 | Mar 22, 2021 10:15:04 | 8 | 198 | 5 | PP-344 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/4 | Sprint 3 | Sprint 2 and Sprint 3 | Dataset upload and management | MVP | 16
3.3.5 | Read o2-grouper.config file | see design |  | 2 | 1 | 1 | 1 | Adrian Z. | Mar 22, 2021 10:14:20 | Mar 22, 2021 11:00:12 | 1 | 60 | 0 | PP-412 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/5 | Sprint 3 |  | Dataset upload and management | MVP | 1
3.3.2 | Implent PipelineRepository | use postgres database connector, use SQLAlchemy for implementation of queries, only implement the methods: add_pipeline, add_artifact, find_artifact |  | 12 | 12 | 16 | 16 | Adrian Z. | Mar 22, 2021 11:00:49 | Mar 24, 2021 09:19:40 | 14 | 257 | 5 | PP-413 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/6 | Sprint 3 |  | Dataset upload and management | MVP | 16
3.3.3 | Define AbstractFileSystem and implement MockFileSystem (for tests) | see design |  | 6 | 8 | 8 | 8 | Adrian Z. | Mar 24, 2021 08:23:33 | Mar 24, 2021 11:45:46 | 3 | 160 | 2 | PP-414 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/7 | Sprint 3 |  | Dataset upload and management | MVP | 8
3.3.4 | Implement DBFS class implementing AbstractFileSystem interface | see design |  | 8 | 16 | 16 | 16 | Adrian Z. | Mar 24, 2021 11:46:11 | Mar 25, 2021 09:00:57 | 5 | 114 | 31 | PP-415 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/8 | Sprint 3 | Spent some time for help for Manoj ~7h | Dataset upload and management | MVP | 16
3.4 | Dataset schema recognition | see design | [11 empty] | PP-345 |  | Sprint 3 |  | Dataset upload and management | MVP | 0
3.4.1 | Implement detect_schema method |  | 3.2, 3.3 | 3 | 3 | 4 | 4 | Adrian Z. | Mar 25, 2021 09:01:44 | Mar 25, 2021 15:12:11 | 3 | 88.5 | 0 | PP-346 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/9 | Sprint 3 |  | Dataset upload and management | MVP | 4
3.4.2 | Implement resolve_dataset_id method |  | 3.2, 3.3 | 4 | 4 | 4 | 4 | Adrian Z. | Mar 25, 2021 09:36:16 | Mar 25, 2021 15:12:28 | 3 | 88.5 | 0 | PP-347 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/9 | Sprint 3 |  | Dataset upload and management | MVP | 4
3.4.3 | Implement get_dataset_schema method |  | 3.4.1, 3.4.2 | 5 | 4 | 8 | 8 | Adrian Z. | Mar 25, 2021 15:18:22 | Mar 29, 2021 10:01:00 | 12 | 261 | 29 | PP-348 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/10 | Sprint 3 |  | Dataset upload and management | MVP | 8
3.5 | LDS dataset validation | see design | [11 empty] | PP-349 |  | Sprint 3 |  | Dataset upload and management | MVP | 0
3.5.1 | Implement get_claim_file_type method |  |  | 3 | 3 | 2 | 2 | Adrian Z. | March 29, 2021, 12:04 PM | March 29, 2021, 1:54 PM | 2 | 77 | 1.5 | PP-350 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/11 | Sprint 3 |  | Dataset upload and management | MVP | 2
3.5.2 | Implement find_fts_file method |  |  | 3.5 | 2 | 2 | 2 | Adrian Z. | March 29, 2021, 1:55 PM | March 29, 2021, 5:04 PM | 2 | 77 | 1.5 | PP-351 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/11 | Sprint 3 |  | Dataset upload and management | MVP | 2
3.5.3 | Implement read_fts method |  |  | 5.5 | 8 | 8 | 8 | Adrian Z. | March 30, 2021, 10:03 AM | March 30, 2021, 2:36 PM | 4.5 | 82 | 1 | PP-352 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/12 | Sprint 3 |  | Dataset upload and management | MVP | 8
3.5.4 | Implement read_claims_file method |  |  | 3.5 | 4 | 4 | 4 | Adrian Z. | March 30, 2021, 2:37 PM | March 30, 2021, 4:31 PM | 2 | 62 | 9 | PP-353 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/13 | Sprint 3 | Added to sprint 3 | Dataset upload and management | MVP | 4
3.5.5 | Implement LDSDataset class |  | 3.5.1 - 3.5.4 | 6.5 | 8 | 10 | 10 | Adrian Z. | March 30, 2021, 4:43 PM | April 1, 2021, 9:46 AM | 10 | 276 | 37 | PP-354 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/14 | Sprint 3 | Added to sprint 3 | Dataset upload and management | MVP | 10
3.6 | P2 dataset validation | see design | [11 empty] | PP-355 |  | Sprint 5 |  | Dataset upload and management | MVP | 0
3.6.1 | Adapt validation code from the existing project | use pandas for validation, drop invalid lines, store validation statistics | 3.3.1 | 24 | 32 | 32 | 32 | Adrian Z. | April 1, 2021, 9:47 AM | April 6, 2021, 12:02 PM | 13.25 | 705 | 3 | PP-416 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/15 | Sprint 4 |  | Dataset upload and management | MVP | 32
3.6.2 | Implement P2UploadDataset | implement all methods |  | 18 | 20 | 24 | 24 | Adrian Z. | Apr 06, 2021 10:10:19 | Apr 07, 2021 10:02:11 | 5.25 | 143.5 | 16 | PP-417 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/16 | Sprint 4 |  | Dataset upload and management | MVP | 24
3.6.3 | Implement import_as_parquet method | see design |  | 16 | 16 | 16 | 16 | Adrian Z. | April 7, 2021, 12:00 PM | April 8, 2021, 10:01 AM | 6.25 | 72 | 4 | PP-418 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/17 | Sprint 4 | ? | Dataset upload and management | MVP | 16
3.6.4 | Implement pipeline steps: schema recognition, validation, import and integrate with the pipeline | Integrate already implemented functions and classes | 3.4, 3.5, 3.6.1 | 24 | 32 | 40 | 40 | Adrian Z. | April 8, 2021, 10:03 AM | April 20, 2021, 5:00 PM | 39.75 | 578 | 73 | PP-419 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/18 | Sprint 5 |  | Dataset upload and management | MVP | 40
3.6.5 | Collect and report validation statistics | see also pipeline statistics | 3.6.4 | 8 | 8 | 16 | 16 | Adrian Z. | Apr 06, 2021 14:11:30 | Apr 07, 2021 10:02:14 | 3.75 | 143.5 | 16 | PP-420 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/16 | Sprint 4 |  | Dataset upload and management | MVP | 16
3.7 | Stay Maker 1 (CMS) | see design | [11 empty] | PP-421 |  | Sprint 7 | Low priority | Dataset upload and management | MVP | 0
3.7.1 | Implement make_lds_stays | use the existing scala implementation | 3.2, 3.3.2 | 40 | 40 | 40 | 40 | Adrian Z. | May 24, 2021 07:31:31 | May 31, 2021 07:10:13 | 37.1667 |  |  | PP-422 |  | Sprint 7 |  | Dataset upload and management | MVP | 40
3.7.2 | Integrate stay maker 1 with the pipeline |  | 3.7.1 | 4 | 8 | 8 | 4 | Adrian Z. | May 31, 2021 06:35:07 | May 31, 2021 09:34:58 | 3.0833 |  |  | PP-423 |  | Sprint 7 |  | Dataset upload and management | MVP | 4
3.8 | Stay Maker 2 (P2 Upload) | see design | [11 empty] | PP-424 |  | Sprint 5 |  | Dataset upload and management | MVP | 0
3.8.1 | Implement make_p2_stays method |  |  | 32 | 40 | 40 | 32 | Wojtek | April 20, 2021, 10:21 AM | April 22, 2021, 9:21 AM | 13.75 | 236 | 2 | PP-425 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/19 | Sprint 5 |  | Dataset upload and management | MVP | 32
3.8.2 | Integrate stay maker 2 with the pipeline |  |  | 4 | 8 | 8 | 4 | Wojtek | April 22, 2021, 9:27 AM |  | 4.75 | 257 | 105 | PP-426 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/22 | Sprint 5 |  | Dataset upload and management | MVP | 4
3.8.3 | Collect and report stay maker's statistics | see design | 3.8.2, 4.6 | 8 | 8 | 8 | 8 | Wojtek | Apr 22, 2021 14:32:41 | Apr 23, 2021 09:49:08 | 1.5 | 53 | 10 | PP-427 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/23 | Sprint 5 |  | Dataset upload and management | MVP | 8
3.9 | Episode Maker | [12 empty] | PP-428 |  | Sprint 5 |  | Dataset upload and management | MVP | 0
3.9.1 | Implement get_anchor_drgs in PipelineRepository |  | 3.3.2 | 6 | 4 | 4 | 6 | Adrian Z. | April 21, 2021, 7:19 AM | April 21, 2021, 12:26 PM | 5.5 | 94 | 0.66667 | PP-429 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/21 | Sprint 5 |  | Dataset upload and management | MVP | 6
3.9.2 | Implement get_excluded_drgs in PipelineRepository |  | 3.3.2 | 3 | 4 | 4 | 3 | Adrian Z. | April 21, 2021, 12:27 PM | April 22, 2021, 9:56 AM | 2.5 | 94 | 0.66667 | PP-430 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/21 | Sprint 5 |  | Dataset upload and management | MVP | 3
3.9.3 | Implement get_excluded_icds in PipelineRepository |  | 3.3.2 | 3 | 4 | 4 | 3 | Adrian Z. | April 22, 2021, 9:56 AM | April 22, 2021, 12:17 PM | 2.25 | 94 | 0.66667 | PP-431 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/21 | Sprint 5 |  | Dataset upload and management | MVP | 3
3.9.4 | Implement make_episodes method | use the existing scala implementation | 3.9.1 - 3.9.3, 3.2, 3.3.2 | 32 | 40 | 40 | 32 | Adrian Z. | April 22, 2021, 12:19 PM |  | 28 | 581 | 25 | PP-432 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/29 | Sprint 5 |  | Dataset upload and management | MVP | 32
3.9.5 | Integrate episode maker with the pipeline |  | 3.9.4 | 4 | 8 | 8 | 4 | Adrian Z. | Apr 27, 2021 14:21:40 | Apr 28, 2021 12:12:24 | 1.75 | 41.5 | 1.5 | PP-433 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/30 | Sprint 5 |  | Dataset upload and management | MVP | 4
3.9.6 | Collect and report the episode maker's statistics |  | 3.9.5, 4.6 | 8 | 8 | 8 | 8 | Adrian Z. | Apr 28, 2021 08:05:53 | Apr 28, 2021 12:11:53 | 4 | 41.5 | 1.5 | PP-434 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/30 | Sprint 5 |  | Dataset upload and management | MVP | 8
3.10 | Relation Maker | see design | [11 empty] | PP-435 |  | Sprint 6 |  | Dataset upload and management | MVP | 0
3.10.1 | Implement get_valid_entities method in PipelineRepository | fetch data generated by the "Entities PIpeline", return only the NPI number column | 3.3.2 | 10 | 4 | 2 | 10 | Adrian Z. | May 04, 2021 14:33:44 | May 05, 2021 11:06:02 | 6.25 | 54.5 | 1 | PP-436 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/33 | Sprint 6 |  | Dataset upload and management | MVP | 10
3.10.2 | Implement make_relations method | translate and refactor the scala code | 3.9.1 - 3.9.3, 3.2, 3.3.2 | 32 | 40 | 40 | 32 | Adrian Z. | Apr 28, 2021 12:16:58 | May 04, 2021 11:48:11 | 16 | 138 | 1 | PP-437 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/32 | Sprint 6 |  | Dataset upload and management | MVP | 32
3.10.3 | Integrate relation maker with the pipeline |  | 3.10.2 | 4 | 8 | 8 | 4 | Adrian Z. | May 04, 2021 10:42:11 | May 05, 2021 11:06:24 | 1 | 54.5 | 1 | PP-438 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/33 | Sprint 6 |  | Dataset upload and management | MVP | 4
3.10.4 | Collect and report the relation maker's statistics |  | 3.10.2, 4.6 | 6 | 8 | 8 | 6 | Adrian Z. | May 05, 2021 10:47:11 | May 05, 2021 12:58:10 | 2 | 33 | 4 | PP-439 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/34 | Sprint 6 |  | Dataset upload and management | MVP | 6
4 | Pipeline Logs & Status Reporting | see design | [11 empty] | PP-440 |  | Sprint 6 |  | Dataset upload and management | MVP | 0
4.1 | Implement add_log method in PipelineRepository |  | 3.3.2 | 2 | 2 | 4 | 2 | Wojtek | Apr 23, 2021 09:51:09 | Apr 23, 2021 11:44:12 | 2 | 274 | 207 | PP-441 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/24 | Sprint 5 |  | Dataset upload and management | MVP | 2
4.2 | Add global error handler, log errorr |  | 3.2 | 2 | 2 | 4 | 2 | Wojtek | Apr 23, 2021 16:45:18 | Apr 26, 2021 07:42:02 | 0.75 | 79 | 30 | PP-442 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/26 | Sprint 5 |  | Dataset upload and management | MVP | 2
4.3 | Implement set_status method in PipelineRepository |  | 3.3.2 | 1.5 | 2 | 4 | 1.5 | Wojtek | Apr 23, 2021 11:45:20 | Apr 23, 2021 15:38:31 | 1.5 | 72.5 | 33 | PP-443 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/25 | Sprint 5 |  | Dataset upload and management | MVP | 1.5
4.4 | Implement set_stage method in PIpelineRepository |  | 3.3.2 | 1.5 | 2 | 4 | 1.5 | Wojtek | Apr 23, 2021 12:22:25 | Apr 23, 2021 15:38:04 | 1.5 | 72.5 | 33 | PP-444 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/25 | Sprint 5 |  | Dataset upload and management | MVP | 1.5
4.5 | Set status, stage and progress during pipeline execution | progress can be estimated from status | 3.6 - 3.10 | 4 | 2 | 4 | 4 | Adrian | May 24, 2021 06:03:28 | May 24, 2021 07:40:16 | 3.1667 |  |  | PP-445 |  | Sprint 7 |  | Dataset upload and management | MVP | 4
4.6 | Implement the update_statistics method in PipelineRepository |  | 3.3.2 | 16 | 16 | 12 | 16 | Wojtek | Apr 23, 2021 16:46:41 | Apr 26, 2021 08:03:28 | 2 | 166 | 172 | PP-446 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/27 | Sprint 6 |  | Dataset upload and management | MVP | 16
5 | Dataset publishing and pipelne control | [12 empty] | PP-447 |  | Sprint 6 |  | Dataset upload and management | MVP | 0
5.1 | Implement publish_relations_dataset method | mostly done but postponed, depends on DM integration with P2 | DM, 3.3 | 24 | 28 | 32 | 24 | Wojtek | April 27, 2021, 11:17 AM | May 17, 2021, 9:37 AM | 12 |  |  | PP-448 |  | Sprint 6 | Another 3 hours needed, awaits DM dependency (an example in p2be) | Dataset upload and management | MVP | 24
5.2 | Handle the pipeline_id control parameter |  | 1 - 3 | 3 | 3 | 3 | 3 | Wojtek | Apr 26, 2021 12:47:45 | Apr 27, 2021 09:07:36 | 4 | 139 | 87 | PP-449 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/28 | Sprint 5 |  | Dataset upload and management | MVP | 3
5.3 | Handle the template_pipeline_id parameter |  | 1 - 3 | 6.5 | 8 | 8 | 6.5 | Wojtek | Apr 27, 2021 06:45:28 | Apr 27, 2021 09:11:11 | 3 |  |  | PP-450 | - | Sprint 5 |  | Dataset upload and management | MVP | 6.5
5.4 | Handle start_from / stop_at parameters |  | 1 - 3 | 8 | 8 | 8 | 8 | Wojtek | Apr 27, 2021 09:14:21 | Apr 27, 2021 09:17:01 | 0 |  |  | PP-451 | - | Sprint 5 |  | Dataset upload and management | MVP | 8
5.5 | Implement published variables validation | integrate with the configuration validation (see design) | 1 | 3 |  | 4 | 3 | Wojtek | Apr 28, 2021 14:42:16 | Apr 29, 2021 07:26:49 | 2 |  |  | PP-535 | - | Sprint 5 |  | Dataset upload and management | MVP | 3
5.6 | Fill in published variable values | process publish_to JSON object | 5.5 | 3.5 |  | 4 | 3.5 | Wojtek | Apr 28, 2021 16:31:06 | Apr 29, 2021 07:26:26 | 0.75 | 507 | 1 | PP-536 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/31 | Sprint 5 |  | Dataset upload and management | MVP | 3.5
5.7 | Add dataset_manager_url to publish_to object | dataset_manager_url parameter should be required when starting pipeline | 5.6 | 4 |  | 4 | 4 | Michał | May 31, 2021 09:52:00 | Jun 09, 2021 11:26:26 | 2.5 |  |  | PP-1362 |  |  |  | Dataset upload and management | MVP | 4
5.8 | Use atomic operation when registering multiple datasets with DM |  | DM | 1.5 |  | 1.5 |  | Michał | [5 empty] | PP-1458 |  | Sprint 9 |  | Dataset upload and management | 1 | 0
6 | Pipeline Server | see design | [11 empty] | PP-1009 |  | Sprint 6 |  | Dataset upload and management | MVP | 0
6.1 | New project set-up | set up python project based on a template |  | 2 |  | 1 | 2 | Wojtek | Apr 29, 2021 06:47:41 | Apr 29, 2021 07:24:40 | 0.5 |  |  | PP-1010 | https://gitlab-01.itx.pl/p2-project/o2-grouper-pipeline-server | Sprint 5 |  | Dataset upload and management | MVP | 2
6.2 | Set up CI/CD pipelines | configure test, build and deployment pipelines |  | 6 |  | 4 | 6 | Wojtek | Apr 29, 2021 08:21:20 | Apr 29, 2021 08:21:24 | 1 |  |  | PP-1011 | https://gitlab-01.itx.pl/p2-project/o2-grouper-pipeline-server | Sprint 5 |  | Dataset upload and management | MVP | 6
6.3 | Implement AppConfig | validate configuration variables, see design |  | 4 |  | 4 | 4 | Wojtek | Apr 29, 2021 08:22:53 | Apr 29, 2021 14:05:14 | 2 | 165 | 8 | PP-1012 | https://gitlab-01.itx.pl/p2-project/o2-grouper-pipeline-server/-/merge_requests/6 | Sprint 5 |  | Dataset upload and management | MVP | 4
6.4 | Implement getPipeline endpoint | integrate with Graphene, set up flask server, implement data model based on SQLAlchemy |  | 24 |  | 24 | 24 | Wojtek | Apr 29, 2021 12:19:50 | May 04, 2021 12:54:41 | 10.5 | 631 | 15 | PP-1013 | https://gitlab-01.itx.pl/p2-project/o2-grouper-pipeline-server/-/merge_requests/7 | Sprint 6 |  | Dataset upload and management | MVP | 24
6.5 | Refactor configuration to match design, use shared app_config library | configure access variables in AWS secrets manager | P2/4 | 4 |  |  | 4 | Adrian Z | June 7, 2021, 3:19 PM | June 8, 2021, 12:21 PM | 3.5 | 94 | 81 | PP-1459 | https://gitlab-01.itx.pl/p2-project/o2-grouper-pipeline-server/-/merge_requests/8 | Sprint 8 |  | Dataset upload and management | MVP | 4
7 | Enhancements and extensions | [12 empty] | PP-1460 |  |  |  | Dataset upload and management | MVP | 0
7.1 | Implement split_by operation support for the publish step | see design, assign suffix to distinguish data parts, make sure to implement as atomic operation |  | 8 |  |  | 8 | Adrian Z | May 13, 2021 07:20:48 | May 17, 2021 07:38:30 | 13.5 |  |  | PP-1358 |  | Sprint 6 |  | Dataset upload and management | MVP | 8
8 | Handling compressed files | see design | [11 empty] | PP-1461 |  |  |  | Dataset upload and management | 1 | 0
8.1 | Implement get_file_password method |  |  | 1.5 | [9 empty] | PP-1462 |  |  |  | Dataset upload and management | 1 | 0
8.2 | Implement is_file_compressed method | add to AbstractFileSystem and implement in DBFSFileSystem |  | 2.5 | [9 empty] | PP-1463 |  |  |  | Dataset upload and management | 1 | 0
8.3 | Implement add_temp_dir method | add to AbstractFileSystem and implement in DBFSFileSystem |  | 2 | [9 empty] | PP-1464 |  |  |  | Dataset upload and management | 1 | 0
8.4 | Implement extract_file method | add to AbstractFileSystem and implement in DBFSFileSystem |  | 2 | [9 empty] | PP-1465 |  |  |  | Dataset upload and management | 1 | 0
8.5 | Handle compressed and password protected files as input_files | see design, make sure to remove temp directory when no longer needed |  | 4 | [9 empty] | PP-1466 |  |  |  | Dataset upload and management | 1 | 0
9 | User Notifications | see design | [11 empty] | PP-1467 |  |  |  | Dataset upload and management | 1 | 0
9.1 | Set up notifications project (python package) | Create template for package projects and use it |  | 6 | [9 empty] | PP-1468 |  |  |  | Dataset upload and management | 1 | 0
9.2 | Set up CI/CD pipelines for the notifications package | Send package to nexus repository | 9.1 | 4 | [9 empty] | PP-1469 |  |  |  | Dataset upload and management | 1 | 0
9.3 | Implement send method in Notifications class | implement the simple airtable SDK, copy AppThreads class from the P2Backend project | 9.1 - 9.2 | 16 | [9 empty] | PP-1470 |  |  |  | Dataset upload and management | 1 | 0
9.4 | Implement airtable cleanup in send method | delete single oldest notification before adding one | 9.3 | 2 | [9 empty] | PP-1471 |  |  |  | Dataset upload and management | 1 | 0
9.5 | Implement check_configuration method in Notifications class |  | 9.3 | 1.5 | [9 empty] | PP-1472 |  |  |  | Dataset upload and management | 1 | 0
9.6 | Read airtable configuration variables in o2-grouper-lambda | run check_configuration to test variables, do not allow partial configuration | 9.5 | 1.5 | [9 empty] | PP-1473 |  |  |  | Dataset upload and management | 1 | 0
9.7 | Send notifications from o2-grouper-lambda | resolve tenant name from auth token, use notifications library | 9.6 | 8 | [9 empty] | PP-1474 |  |  |  | Dataset upload and management | 1 | 0
9.8 | Add airtable variables to o2-grouper config | run check_configuration to test variables, do not allow partial configuration | 9.5 | 1.5 | [9 empty] | PP-1475 |  |  |  | Dataset upload and management | 1 | 0
9.9 | Send notifications from o2-grouper-job | resolve tenant name from auth token, use notifications library | 9.8 | 8 | [9 empty] | PP-1476 |  |  |  | Dataset upload and management | 1 | 0
10 | Pipeline Validation Statistics | see design | [11 empty] | PP-1477 |  |  |  | Dataset upload and management | 1 | 0
10.1 | Add input_schema column to pipelines table and implement set_input_schema method in PipelineRepository | Set the input_schema value as soon as it's recognized, see design |  | 3 | [9 empty] | PP-1478 |  |  |  | Dataset upload and management | 1 | 0
10.2 | Define additional pipeline stages (database and in-code enums) | define input_statistics, stay_maker_statistics, episode_maker_statistics, relation_maker_statistics |  | 1.5 | [9 empty] | PP-1479 |  |  |  | Dataset upload and management | 1 | 0
10.3 | Prepare data model for validation statistics, implement methods for adding statistics in PipelineRepository | see design | 10.2 | 12 | [9 empty] | PP-1480 |  |  |  | Dataset upload and management | 1 | 0
10.4 | Implement input_statistics step for P2 data | Define data model, add data to PipelineRepository, see design | 10.3 | 4 | [9 empty] | PP-1481 |  |  |  | Dataset upload and management | 1 | 0
10.5 | Implement input_statistics step for CMS data |  | 10.3, 3.5 | 12 | [9 empty] | PP-1482 |  |  |  | Dataset upload and management | 1 | 0
10.6 | Implement stay_maker_statistics step | Define data model, add data to PipelineRepository, see design | 10.3 | 4 | [9 empty] | PP-1483 |  |  |  | Dataset upload and management | 1 | 0
10.7 | Implement episode_maker_statistics step | Define data model, add data to PipelineRepository, see design | 10.3 | 16 | [9 empty] | PP-1484 |  |  |  | Dataset upload and management | 1 | 0
10.8 | Implement relation_make_statistics step | Define data model, add data to PipelineRepository, see design | 10.3 | 4 | [9 empty] | PP-1485 |  |  |  | Dataset upload and management | 1 | 0
10.9 | Handle validation_statistics argument in pipeline control object | see design | 10.1 - 10.8 | 2 | [9 empty] | PP-1486 |  |  |  | Dataset upload and management | 1 | 0
11 | Data Cleanup | see design | [11 empty] | PP-1487 |  |  |  | Dataset upload and management | 1 | 0
11.1 | Implement find_files method in DBFSFilesystem |  |  | 2 | [9 empty] | PP-1488 |  |  |  | Dataset upload and management | 1 | 0
11.2 | Implement delete_file method in DBFSFilesystem |  |  | 1 | [9 empty] | PP-1489 |  |  |  | Dataset upload and management | 1 | 0
11.3 | Implement get_expired_artifacts in PIpelineRepository |  |  | 2 | [9 empty] | PP-1490 |  |  |  | Dataset upload and management | 1 | 0
11.4 | Implement delete_artifacts in PipelineRepository |  |  | 1 | [9 empty] | PP-1491 |  |  |  | Dataset upload and management | 1 | 0
11.5 | Implement clean_expired_artifacts method | send notifications | 11.1 - 11.4 | 2.5 | [9 empty] | PP-1492 |  |  |  | Dataset upload and management | 1 | 0
11.6 | Implement clean_expired_files method | send notifications | 11.1 - 11.2 | 1 | [9 empty] | PP-1493 |  |  |  | Dataset upload and management | 1 | 0
11.6 | Execute clean_expired_artifacts and clean_expired_files methods every time a job starts |  | 11.5, 11.6 | 1 | [9 empty] | PP-1494 |  |  |  | Dataset upload and management | 1 | 0
12 | Refactor | [12 empty] | PP-1495 |  |  |  | Dataset upload and management | 1 | 0
12.1 | Set-up o2-grouper-base package to be imported from other o2-grouper projects: o2-grouper-lambda, o2-grouper-job, o2-grouper-pipeline-server |  |  | 3 | [9 empty] | PP-1496 |  |  |  | Dataset upload and management | 1 | 0
12.2 | Move PipelineRepository class to o2-grouper-base | move class and dependencies, import from other projects | 12.1 | 8 | [9 empty] | PP-1497 |  |  |  | Dataset upload and management | 1 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0