## Description
Design document: | Dataset Manager Technical Design
Jira project: | P2 next gen (PP)
Jira label: | Tests
Number of tasks: | 369
Number of reported bugs: | 0
`
Total planned development worktime [h]: | 1986
Planned development worktime of finished tasks [h]: | 1491
Current worktime spent [h]: | 1325.92
Planned time to finish project [h]: | 495
Planned availability (until 28 May) [h]: | 0
Project completeness based on planned worktime [%]: | 75.0755
Current worktime vs planned worktime [%]: | 88.9282 | > 100% - delay; < 100% - ahead
Last update | Jun 25, 2021 08:56:16
Number of updated tasks (during last update) | 1
Note on A1: Added dependency tasks -Kamil Jabłoński

## Tasks
WBS | Name | Description | Depends on | Estimated work time [h] |  |  |  | Assignee | Actual work time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment | Category | Version
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Make a cleanup in tests library | [12 empty] | PP-246 |  | Sprint 3 |  | Dataset upload and management | MVP | 0
1.1 | ‘2D graph’ - finish and update the unfinished tests. |  |  | 20 | 20 | 16 |  | Swatantra | March 24, 2021, 1:00 PM | April 1, 2021, 2:59 PM |  |  |  | PP-301 |  | Sprint 3 | Abandoned | Visualization Generation | MVP | 0
1.2 | Changes in columns |  |  | 1 | 2 | 4 | [7 empty] | PP-303 |  | Sprint 3 | Abandoned |  | MVP | 0
1.3 | Update graph combination filter tests to use all existing types of filters | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 |  | Monika | March 19, 2021, 8:18 AM |  |  |  |  | PP-304 |  | Sprint 3 | Abandoned | Visualization Generation | MVP | 0
1.4 | Update map view filter combination tests to use all existing filter types | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 |  | Monika | March 26, 2021, 8:26 AM |  |  |  |  | PP-305 |  | Sprint 3 | Abandoned | Visualization Generation | MVP | 0
1.5 | Update 2D graph view filter combination tests to use all existing filter types | Add LOB filter to existing all-filter-combination tests (time filter feature will be discarded) |  | 16 | 16 | 20 |  | Paulina | March 23, 2021, 8:51 AM | March 26, 2021, 8:51 AM |  |  |  | PP-306 |  | Sprint 3 | Abandoned | Visualization Generation | MVP | 0
1.6 | Review and prune tests from Benchmark Average on Graph tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 |  | Piotr | [5 empty] | PP-493 |  | Sprint 3 | Abandoned | Benchmark settings customization & Benchmark Calculation | MVP | 0
1.7 | Review and prune tests from Benchmark Perecentile on Graph tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | [7 empty] | PP-494 |  | Sprint 3 | Abandoned | Benchmark settings customization & Benchmark Calculation | MVP | 0
1.8 | Review and prune tests from Benchmark Average&Percentile_Map tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 | [7 empty] | PP-495 |  | Sprint 3 | Abandoned | Benchmark settings customization & Benchmark Calculation | MVP | 0
1.9 | Review and prune tests from Dataset Management tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 14 | 16 | 20 |  | Paulina | March 18, 2021, 3:56 PM | March 26, 2021, 8:26 AM |  |  |  | PP-457 |  | Sprint 3 | Abandoned | Dataset upload and management | MVP | 0
1.10 | Review and prune tests from Labels tab | Delete/Archive redundant tests, improve existing ones to have more clear steps and cover the functionality better |  | 16 | 16 | 20 |  | Kamil | March 18, 2021, 4:16 PM |  |  |  |  | PP-459 |  | Sprint 3 | Abandoned | Label settings | MVP | 0
1.11 | Prepare statistics of automated testcases for old suite | [12 empty] | PP-498 |  | Sprint 3 | Added during sprint |  | MVP | 0
1.11.1 | Statistics for 1st part of the testcases |  |  |  |  | 8 |  | Kamil | March 24, 2021, 8:16 AM | March 24, 2021, 5:16 PM |  |  |  | PP-499 |  | Sprint 3 | Added during sprint |  | MVP | 0
1.11.2 | Statistics for 2nd part of the testcases |  |  |  |  | 8 |  | Piotr | March 24, 2021, 8:16 AM | March 24, 2021, 5:16 PM |  |  |  | PP-500 |  | Sprint 3 | Added during sprint |  | MVP | 0
1.12 | Add categories types to missing testcases after initial cleanup |  |  |  |  | 8 |  | Paulina | March 24, 2021, 10:04 AM | March 24, 2021, 3:08 PM |  |  |  | PP-501 |  | Sprint 3 | Added during sprint |  | MVP | 0
2 | Integration tests of p2backend | [12 empty] | PP-1048 |  | Sprint 7 |  |  | MVP | 0
2.1 | Testing caseSummaryCollection query | [12 empty] | PP-266 |  | Sprint 7 |  | Visualization Generation | MVP | 0
2.1.1 | Test caseSummaryCollection - market share graph | - Check response with multiple normal/LDS datasets - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: 1.1 | 24 | 24 | 16 | 24 | Paulina, Piotr | Apr 09, 2021 11:14:25 | May 17, 2021 13:40:36 | 47.25 |  |  | PP-267 |  | Sprint 6 | Moved from Sprint 3, postponed due to reported bugs | Visualization Generation | MVP | 24
2.1.2 | Test caseSummaryCollection - benchmark graph | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: | 24 | 24 | 16 | 24 | Piotr | May 19, 2021 07:05:17 | May 25, 2021 11:38:06 | 21 |  |  | PP-268 |  | Sprint 6 |  | Visualization Generation | MVP | 24
2.1.3 | Test caseSummaryCollection - 2D graph | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings and combinations - Check all filter types combinations - Check count, legend data, ungroup range and orders fields | BE: | 24 | 24 | 16 | 24 | [6 empty] | PP-269 |  |  |  | Visualization Generation | MVP | 0
2.2 | Test caseLobCounts query | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests)" | BE: 1.3 | 6 | 8 | 8 | 8 | Swatantra | April 5, 2021, 2:03 PM | April 7, 2021, 8:49 AM | 15 | 51 | 2 | PP-546 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/5 | Sprint 4 | Moved from Sprint 3 | Filters - LOB filters | MVP | 8
2.3 | Test getAvailableYears query | see design - Check results for multiple normal/LDS datasets - Check pagination | BE: 1.4 | 4 | 4 | 4 | 4 | Swatantra | April 1, 2021, 4:32 PM | April 5, 2021, 2:01 PM | 19 | 37 | 0 | PP-547 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/4 | Sprint 4 | Moved from Sprint 3 | Visualization Generation | MVP | 4
2.4 | Test getDateTimeStatsForListOfYears query | see design - Check results for multiple normal/LDS datasets - Check pagination | BE: 1.5 | 6 | 8 | 8 | 8 | Swatantra | April 12, 2021, 8:43 AM | April 13, 2021, 1:19 AM | 15 | 47 | 0 | PP-548 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/9 | Sprint 4 | Moved from Sprint 3 | Visualization Generation | MVP | 8
2.5 | Test filteredCareUnitTypes query | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests) | BE: 1.6 | 8 | 8 | 8 | 8 | Paulina | April 6, 2021, 1:00 PM | April 8, 2021, 12:43 PM | 8 | 325 | 0 | PP-549 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/6 | Sprint 4 | Moved from Sprint 3 | Visualization Generation | MVP | 8
2.6 | Test getDatasetsInitialFilters query | see design - Check normal/LDS datasets in combinations - Check boolean input fields | BE: 1.7 | 10 | 12 | 16 | 16 | Paulina | April 7, 2021, 2:29 PM | April 8, 2021, 1:03 PM | 5 | 102 | 2 | PP-550 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/7 | Sprint 4 | Moved from Sprint 3 | Visualization Generation | MVP | 16
2.7 | Report view | [12 empty] | PP-551 |  | Sprint 7 |  | View Dashboard | MVP | 0
2.7.1 | Test ReportView query | design - Check if returne fields are correct and the if the response structure is as expected | BE: 3 | 12 | 12 | 16 | 16 | Paulina | April 1, 2021, 8:18 AM | April 6, 2021, 1:02 PM | 11 | 527 | 1 | PP-552 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/2 | Sprint 4 | Moved from Sprint 3 | View Dashboard | MVP | 16
2.7.2 | Test ReportViews query | design - Check if the number of views returned is correct - Check if different user's id can be provided | BE: 3 | 10 | 12 | 16 | 16 | Piotr | April 15, 2021, 11:24 AM | April 15, 2021, 4:06 PM | 9.5 | 527 | 1 | PP-553 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/2 | Sprint 4 | Moved from Sprint 3 | View Dashboard | MVP | 16
2.7.3 | Test SearchReportViews query | design - Search Report Views based on their names - Search Report Views based on the datasets used by the views | BE: 3 | 10 | 12 | 16 | 16 | Paulina | Apr 13, 2021 12:29:26 | Apr 14, 2021 10:53:39 | 7 | 58 | 2 | PP-554 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/15 | Sprint 4 | Moved from Sprint 3 | View Dashboard | MVP | 16
2.7.4 | Test CreateReportView query | design - Check all possible input parameters with the special focus on: reportViewType, datasets and filters - Check if a view can be created for another user | BE: 3 | 16 | 16 | 16 | 16 | Paulina | March 30, 2021, 8:36 AM | April 1, 2021, 8:17 AM | 18 | 527 | 1 | PP-555 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/2 | Sprint 4 | Moved from Sprint 3 | View Dashboard | MVP | 16
2.7.5 | Test UpdateReportView query | design - Check all possible input parameters with the special focus on: reportViewType, datasets and filters - Cases when an updated view doesn't exist or is deleted - Check if another user's view can e updated | BE: 3 | 16 | 16 | 16 | 16 | Paulina | April 2, 2021, 3:36 PM | April 7, 2021, 1:39 PM | 9.5 | 527 | 1 | PP-556 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/2 | Sprint 4 | Moved from Sprint 3 | View Dashboard | MVP | 16
2.7.6 | Test DeleteReportView mutation | design - Delete existing ReportView and check if it was truly deleted (no appearing in ReportView and ReportViews queries) - Try deleting a ReportView that doesn't exist and/or the one that was already deleted | BE: 3 | 4 | 4 | 8 | 8 | Piotr | April 15, 2021, 3:41 PM | April 15, 2021, 3:43 PM | 2.5 | 57 | 0 | PP-557 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/26 | Sprint 4 | Moved from Sprint 3 | View Dashboard | MVP | 8
2.8 | Getting datasets list | [12 empty] | PP-558 |  | Sprint 7 |  |  | MVP | 0
2.8.1 | allDatasets endpoint | see design - Check if datasets are returned correctly (the amount and names) | BE: 1.17 | 14 |  | 12 | 4 | Piotr | April 13, 2021, 2:22 PM | April 13, 2021, 3:31 PM | 2 | 67 | 0 | PP-559 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/12 | Sprint 4 | Moved from Sprint 3, task splitted into two due to availability of endpoint from BE (2.8.3) | Dataset upload and management | MVP | 4
2.8.2 | getLDSDatasetsIDs endpoint | see design Check the query when there're multiple LDS and normal datasets uploaded | BE: 1.16 | 4 |  | 4 | 4 | Swatantra | April 13, 2021, 2:12 PM | April 16, 2021, 8:45 AM | 4.5 |  |  | PP-560 |  | Sprint 4 | Moved from Sprint 3 | Dataset upload and management | MVP | 4
2.8.3 | allDatasets endpoint - upload status | - Check the correctness of upload status (upload can be finished, failed or in progress) - if possible now - Check if upload start and finish time are correct - if possible for now | BE: 1.17 |  |  |  | 10 | [6 empty] | PP-1006 |  |  | Move to the next sprint, because of PP-538 have to be closed. | Dataset upload and management | MVP | 0
2.9 | caseLocationDetails endpoint | see design - Check results for different dataset type - Check results for CBSA, FIPS, state, no option chosen |  | 10 |  | 8 | 10 | Paulina | April 8, 2021, 3:02 PM | April 9, 2021, 12:19 PM | 7.5 | 228 | 7 | PP-561 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/8 | Sprint 4 | Added to sprint in Sprint 4 | Filters - Geography (Location) filters | MVP | 10
2.10 | searchCareUnitAndDetail endpoint | see design - Check data for different types of datasets - Check data for every type of entity |  | 14 |  | 16 | 16 | Piotr | Apr 09, 2021 10:26:50 | May 13, 2021 12:36:35 | 8 |  |  | PP-562 |  | Sprint 6 |  | Visualization Generation | MVP | 16
2.11 | filteredCareUnits endpoint | see design - Check data returned for multiple normal/LDS datasets - Check pagination - Check ordering of results - Check different searchInput scenarios (similar to testing search features in FE tests) |  | 10 |  | 10 | 10 | Swatantra | April 16, 2021, 3:47 PM | April 19, 2021, 3:25 PM | 12.5 |  |  | PP-626 |  | Sprint 5 |  | Visualization Generation | MVP | 10
2.12 | caseSummaryCollectionMapView endpoint | see design | [11 empty] | PP-627 |  |  |  | Visualization Generation | MVP | 0
2.12.1 | caseSummaryCollectionMapView - marketshare map | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings |  | 16 |  | 20 | 20 | Piotr | May 26, 2021 08:01:15 | May 27, 2021 10:28:39 | 9 |  |  | PP-628 |  | Sprint 7 |  | Visualization Generation | MVP | 20
2.12.2 | caseSummaryCollectionMapView - benchmark map | - Check response with multiple normal/LDS datasets - Check different benchmark fields settings - Check all filter types combinations |  | 16 |  | 20 | 20 | Piotr | Jun 01, 2021 07:31:22 | Jun 02, 2021 08:43:37 | 7 |  |  | PP-629 |  | Sprint 8 |  | Visualization Generation | MVP | 20
2.13 | Node Expand and Collapse | see design | [11 empty] | PP-630 |  |  |  | Visualization Navigation | MVP | 0
2.13.1 | Node Expand and Collapse - marketshare graph | see design Check expanding/collapsing all AC/PAC types on all layers |  | 12 |  | 16 | 16 | Piotr | May 13, 2021 12:40:46 | May 18, 2021 11:59:40 | 11 |  |  | PP-631 |  | Sprint 6 |  | Visualization Navigation | MVP | 16
2.13.2 | Node Expand and Collapse - benchmark graph | see design Check expanding/collapsing all AC/PAC types and all Service Lines on all layers |  | 12 |  | 16 | 16 | Piotr | Jun 02, 2021 10:21:50 | Jun 08, 2021 10:39:34 | 8.5 |  |  | PP-632 |  | Sprint 8 |  | Visualization Navigation | MVP | 16
2.14 | Integration tests of p2backend report generator | [12 empty] | PP-563 |  | Sprint 3 |  |  | MVP | 0
2.14.1 | Research - pytest tools to generate tests report | Research about available tools to generate report for p2 integration tests. The following libraries were tested: pytest-csv pytest-excel pytest-html |  | 8 |  | 8 | 8 | Piotr | March 29, 2021, 2:29 PM | March 29, 2021, 4:30 PM | 6 |  |  | PP-564 | - | Sprint 3 |  |  | MVP | 8
2.14.2 | Implementation of tests report generator - structure of worksheets |  |  | 8 |  | 8 | 8 | Piotr | March 29, 2021, 4:31 PM | March 30, 2021, 11:40 AM | 8.5 |  |  | PP-565 | - | Sprint 3 |  |  | MVP | 8
2.14.3 | Implementation of tests report generator - summarize tabs |  |  | 8 |  | 8 | 8 | Piotr | March 30, 2021, 11:41 AM | March 31, 2021, 12:24 PM | 8.5 |  |  | PP-566 | - | Sprint 3 |  |  | MVP | 8
2.15 | ServiceLine API | [12 empty] | PP-633 |  | Sprint 6 |  | Filters - Service Line filters | MVP | 0
2.15.1 | test searchServiceLine endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 4 |  |  | 4 | Piotr | Jun 09, 2021 06:55:34 | Jun 09, 2021 07:03:48 | 0 |  |  | PP-634 |  | Sprint 8 |  | Filters - Service Line filters | MVP | 4
2.15.2 | test searchAllDiagnose endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | Piotr | Jun 09, 2021 07:06:18 | Jun 09, 2021 08:09:04 | 3.5 |  |  | PP-635 |  | Sprint 8 |  | Filters - Service Line filters | MVP | 8
2.15.3 | test filteredServiceLines endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 4 |  |  | 4 | Paulina | April 15, 2021, 11:23 AM | April 15, 2021, 2:40 PM | 4 | 39 | 0 | PP-636 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/24 | Sprint 4 | Added to sprint in Sprint 4 | Filters - Service Line filters | MVP | 4
2.15.4 | test filteredClinicalEpisodes endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | Monika | April 15, 2021, 2:26 PM | April 19, 2021, 8:42 AM | 5 | 97 | 0 | PP-637 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/31 | Sprint 4 | Added to sprint in Sprint 4 | Filters - Service Line filters | MVP | 8
2.15.5 | test filteredDRGs endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | Paulina | April 15, 2021, 3:23 PM | April 16, 2021, 9:36 AM | 2.5 |  |  | PP-638 |  | Sprint 4 |  | Filters - Service Line filters | MVP | 8
2.16 | Location API | [12 empty] | PP-639 |  | Sprint 4 |  |  | MVP | 0
2.16.1 | test allUSStates endpoint | - check correctness of the response |  | 4 |  |  | 4 | Paulina | April 13, 2021, 1:06 PM | April 13, 2021, 2:28 PM | 1.5 | 34 | 0 | PP-640 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/11 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | 4
2.16.2 | test usState endpoint | - check correctness of the response |  | 4 |  |  | 4 | Paulina | April 14, 2021, 12:59 PM | April 15, 2021, 9:39 AM | 3 | 59 | 0 | PP-641 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/22 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | 4
2.16.3 | test searchUsLocation endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 6 |  |  | 6 | Paulina | April 14, 2021, 3:17 PM | April 15, 2021, 9:13 AM | 2.5 | 106 | 0 | PP-642 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/21 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | 6
2.16.4 | test usStateGeoAll endpoint | - check correctness of the response |  | 4 |  |  | 4 | Monika | April 14, 2021, 12:58 PM | April 15, 2021, 9:50 AM | 3.5 | 44 | 0 | PP-643 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/20 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | 4
2.16.5 | test usCountyGeoForState endpoint | - check correctness of the response |  | 4 |  |  | 4 | Monika | April 15, 2021, 8:32 AM | April 15, 2021, 2:07 PM | 4.5 |  |  | PP-644 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/23 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | 4
2.16.6 | test usStateGeoSearch | - call the endpoint with different search inputs and check the correctness of results |  | 8 |  |  | 8 | Piotr | April 14, 2021, 11:58 AM | April 15, 2021, 11:24 AM | 4 | 43 | 2 | PP-645 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/17 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | 8
2.16.7 | test usCountyGeoAll endpoint | - check correctness of the response |  | 5 |  |  | 5 | Piotr | April 14, 2021, 9:28 AM | April 14, 2021, 11:38 AM | 2 | 42 | 0 | PP-646 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/14 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | 5
2.16.8 | test locationByRadialLocation endpoint | - call the endpoint with different search inputs and check the correctness of results |  | 12 |  |  | 12 | Piotr | April 13, 2021, 4:10 PM | April 14, 2021, 9:21 AM | 2 | 49 | 0 | PP-647 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/13 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | 12
3 | Front End tests | [12 empty] | PP-648 |  | Sprint 10 |  |  | MVP | 0
3.1 | Changes in regression library | [12 empty] | PP-649 |  | Sprint 10 |  |  | MVP | 0
3.1.1 | Authentication & Authorization | make a cleanup in the tab following the rules from the design | [11 empty] | PP-650 |  |  |  | Authentication & Authorization | MVP | 0
3.1.1.1 | Authentication Module |  |  | 4 |  |  | 4 | [6 empty] | PP-1049 |  |  |  | Authentication & Authorization | MVP | 0
3.1.1.2 | Multi-tenancy |  |  | 4 |  |  | 4 | [6 empty] | PP-1050 |  |  |  | Authentication & Authorization | MVP | 0
3.1.1.3 | Password requirements |  |  | 2 |  |  | 2 | [6 empty] | PP-1051 |  |  |  | Authentication & Authorization | MVP | 0
3.1.1.4 | Change password |  |  | 4 |  |  | 4 | [6 empty] | PP-1052 |  |  |  | Authentication & Authorization | MVP | 0
3.1.1.5 | Email Notifications & New email templates |  |  | 4 |  |  | 4 | [6 empty] | PP-1053 |  |  |  | Authentication & Authorization | MVP | 0
3.1.2 | Dataset Upload & Management | make a cleanup in the tab following the rules from the design | [11 empty] | PP-698 |  |  |  |  | MVP | 0
3.1.2.1 | Dataset upload |  |  | 4 |  |  | 4 | Paulina | [5 empty] | PP-1054 |  |  |  | Dataset Upload & Management | MVP | 0
3.1.2.2 | Dataset permissions |  |  | 4 |  |  | 4 | [6 empty] | PP-1055 |  |  |  | Dataset Upload & Management | MVP | 0
3.1.2.3 | View datasets details |  |  | 4 |  |  | 4 | [6 empty] | PP-1056 |  |  |  | Dataset Upload & Management | MVP | 0
3.1.2.4 | Delete Dataset |  |  | 2 |  |  | 2 | [6 empty] | PP-1057 |  |  |  | Dataset Upload & Management | MVP | 0
3.1.2.5 | Export datasets statistics details as Excel file |  |  | 4 |  |  | 4 | [6 empty] | PP-1058 |  |  |  | Dataset Upload & Management | MVP | 0
3.1.2.6 | Statistics preview of a dataset by entity type |  |  | 2 |  |  | 2 | [6 empty] | PP-1059 |  |  |  | Dataset Upload & Management | MVP | 0
3.1.3 | View Dashboard | make a cleanup in the tab following the rules from the design | [11 empty] | PP-651 |  | Sprint 5 |  |  | MVP | 0
3.1.3.1 | View Creation |  |  | 6 |  |  | 6 | Paulina | Apr 20, 2021 06:53:33 | Apr 23, 2021 14:08:23 | 5 |  |  | PP-1060 |  | Sprint 5 |  | View Dashboard | MVP | 6
3.1.3.2 | View Management (delete, search, etc) + search by dataset + save view/new view |  |  | 8 |  |  | 8 | Paulina | Apr 20, 2021 13:09:01 | Apr 23, 2021 14:08:03 | 8.25 |  |  | PP-1061 |  | Sprint 5 |  | View Dashboard | MVP | 8
3.1.3.3 | View duplication |  |  | 2 |  |  | 2 | Paulina | Apr 20, 2021 13:09:01 | Apr 23, 2021 14:08:03 | 1 |  |  | PP-1062 |  | Sprint 5 |  | View Dashboard | MVP | 2
3.1.3.4 | View name editing |  |  | 2 |  |  | 2 | Paulina | Apr 20, 2021 13:09:01 | Apr 23, 2021 14:08:03 | 2 |  |  | PP-1063 |  | Sprint 5 |  | View Dashboard | MVP | 2
3.1.4 | Location Filter | make a cleanup in the tab following the rules from the design | [11 empty] | PP-652 |  | Sprint 6 |  |  | MVP | 0
3.1.4.1 | Location filter by states & FIPS & CBSA [2nd and 3rd panel] |  |  | 10 |  |  | 10 | Piotr | Apr 20, 2021 08:08:00 | Apr 28, 2021 10:02:33 | 8.5 |  |  | PP-1064 |  | Sprint 5 |  | Location filter by FIPS | MVP | 10
3.1.4.2 | Location filter by Radius map [2nd and 3rd panel] |  |  | 10 |  |  | 10 | Piotr | Apr 26, 2021 06:29:46 | Apr 28, 2021 10:02:38 | 9 |  |  | PP-1065 |  | Sprint 5 |  | Location filter by FIPS | MVP | 10
3.1.4.3 | Location filter switch between grayscale and terrain |  |  | 2 |  |  | 2 | Piotr | Apr 22, 2021 08:15:26 | Apr 28, 2021 10:02:42 | 1.5 |  |  | PP-1066 |  | Sprint 5 |  | Location filter by FIPS | MVP | 2
3.1.4.4 | Location filter applies to |  |  | 8 |  |  | 8 | Piotr | Apr 27, 2021 08:52:05 | Apr 28, 2021 10:02:46 | 6.5 |  |  | PP-1067 |  | Sprint 5 |  | Location filter by FIPS | MVP | 8
3.1.4.5 | Tooltips for location filters |  |  | 2 |  |  | 2 | Piotr | Apr 23, 2021 13:28:18 | Apr 28, 2021 10:02:51 | 3 |  |  | PP-1068 |  | Sprint 5 |  | Location filter by FIPS | MVP | 2
3.1.4.6 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features e.g. scrolling/zooming map] |  |  | 4 |  |  | 4 | Piotr | Apr 28, 2021 10:04:35 | Apr 28, 2021 10:06:12 | 1 |  |  | PP-1069 |  | Sprint 5 |  | Filters - Convenience features | MVP | 4
3.1.4.7 | Pagination of the Entity, Service Lines,..Filters |  |  | 2 |  |  | 2 | Piotr | Apr 22, 2021 12:09:37 | Apr 28, 2021 10:03:05 | 1.5 |  |  | PP-1070 |  | Sprint 5 |  | Filters - Convenience features | MVP | 2
3.1.4.8 | Filter search |  |  | 4 |  |  | 4 | Piotr | Apr 22, 2021 12:59:10 | Apr 28, 2021 10:03:08 | 3 |  |  | PP-1071 |  | Sprint 5 |  | Filters - Convenience features | MVP | 4
3.1.4.9 | Clear filters feature |  |  | 2 |  |  | 2 | Piotr | Apr 22, 2021 10:14:32 | Apr 28, 2021 10:03:14 | 1.5 |  |  | PP-1072 |  | Sprint 6 |  | Filters - Convenience features | MVP | 2
3.1.4.10 | Filters breadcrumb (tree structures) |  |  | 6 |  |  | 6 | Piotr | Apr 23, 2021 06:02:22 | Apr 28, 2021 10:03:18 | 4 |  |  | PP-1073 |  | Sprint 6 |  | Filters or Visualization Navigation Convenience features | MVP | 6
3.1.4.11 | Filters breadcrumb navigation to the selected layer |  |  | 2 |  |  | 2 | Piotr | Apr 23, 2021 11:02:08 | May 04, 2021 07:09:44 | 1 |  |  | PP-1074 |  | Sprint 6 |  | Filters or Visualization Navigation Convenience features | MVP | 2
3.1.5 | Entity Filter | make a cleanup in the tab following the rules from the design | [11 empty] | PP-653 |  | Sprint 5 |  |  | MVP | 0
3.1.5.1 | Entity-post acute type filter & Entity-Hospital filter [2nd and 3rd panel] |  |  | 8 |  |  | 8 | Monika | Apr 21, 2021 06:07:01 | Apr 28, 2021 09:06:15 | 12 |  |  | PP-1075 |  | Sprint 5 |  | Filters - Entity filters | MVP | 8
3.1.5.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  |  | 4 |  |  | 4 | Monika | Apr 22, 2021 08:43:53 | Apr 28, 2021 11:00:16 | 5 |  |  | PP-1076 |  | Sprint 5 |  | Filters - Entity filters | MVP | 4
3.1.5.3 | Pagination of the Entity, Service Lines,..Filters |  |  | 4 |  |  | 4 | Monika | Apr 22, 2021 08:43:56 | Apr 28, 2021 11:20:58 | 3.75 |  |  | PP-1077 |  | Sprint 5 |  | Filters - Convenience features | MVP | 4
3.1.5.4 | Filter search |  |  | 4 |  |  | 4 | Monika | Apr 26, 2021 10:42:22 | Apr 28, 2021 12:00:34 | 4.25 |  |  | PP-1078 |  | Sprint 5 |  | Filters - Convenience features | MVP | 4
3.1.5.5 | Tooltips when hovering over filters |  |  | 2 |  |  | 2 | Monika | Apr 26, 2021 10:44:37 | Apr 28, 2021 12:50:46 | 2 |  |  | PP-1079 |  | Sprint 5 |  | Filters - Convenience features | MVP | 2
3.1.5.6 | Clear filters feature |  |  | 2 |  |  | 2 | Monika | Apr 26, 2021 10:44:40 | Apr 28, 2021 12:51:48 | 1.75 |  |  | PP-1080 |  | Sprint 5 |  | Filters - Convenience features | MVP | 2
3.1.5.7 | Filters breadcrumb (tree structures) for Service Line and Entity filters |  |  | 6 |  |  | 6 | Monika | Apr 26, 2021 05:13:41 | Apr 28, 2021 12:52:12 | 6.75 |  |  | PP-1081 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | MVP | 6
3.1.5.8 | Filters breadcrumb navigation to the selected layer |  |  | 2 |  |  | 2 | Monika | Apr 26, 2021 05:13:47 | Apr 28, 2021 12:53:06 | 2 |  |  | PP-1082 |  | Sprint 5 |  | Filters or Visualization Navigation Convenience features | MVP | 2
3.1.6 | Service Line filter | make a cleanup in the tab following the rules from the design | [11 empty] | PP-654 |  | Sprint 6 |  |  | MVP | 0
3.1.6.1 | Service line filter [SL, Episode, DRG levels - 2nd and 3rd panel] |  |  | 10 |  |  | 10 | Swatantra | Apr 20, 2021 14:08:03 | May 07, 2021 07:25:34 | 19.5 |  |  | PP-1083 |  | Sprint 6 |  | Filters - Service Line filters | MVP | 10
3.1.6.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  |  | 2 |  |  | 2 | Swatantra | Apr 28, 2021 11:11:52 | May 04, 2021 09:39:05 | 4.5 |  |  | PP-1084 |  | Sprint 6 |  | Filters - Convenience features | MVP | 2
3.1.6.3 | Pagination of the Entity, Service Lines,..Filters |  |  | 4 |  |  | 4 | Swatantra | Apr 28, 2021 11:12:53 | May 04, 2021 09:40:14 | 7 |  |  | PP-1085 |  | Sprint 6 |  | Filters - Convenience features | MVP | 4
3.1.6.4 | Filter search |  |  | 4 |  |  | 4 | Swatantra | Apr 28, 2021 11:13:56 | May 04, 2021 09:57:07 | 7.5 |  |  | PP-1086 |  | Sprint 6 |  | Filters - Convenience features | MVP | 4
3.1.6.5 | Tooltips when hovering over filters |  |  | 2 |  |  | 2 | Swatantra | Apr 28, 2021 11:14:53 | May 04, 2021 09:57:30 | 6.5 |  |  | PP-1087 |  | Sprint 6 |  | Filters - Convenience features | MVP | 2
3.1.6.6 | Clear filters feature |  |  | 2 |  |  | 2 | Swatantra | Apr 28, 2021 11:16:01 | May 04, 2021 09:57:45 | 4 |  |  | PP-1088 |  | Sprint 6 |  | Filters - Convenience features | MVP | 2
3.1.6.7 | Filters breadcrumb (tree structures) for Service Line and Entity filters |  |  | 6 |  |  | 6 | Swatantra | Apr 28, 2021 11:17:13 | May 04, 2021 10:16:21 | 12 |  |  | PP-1089 |  | Sprint 6 |  | Filters or Visualization Navigation Convenience features | MVP | 6
3.1.6.8 | Filters breadcrumb navigation to the selected layer |  |  | 2 |  |  | 2 | Swatantra | Apr 28, 2021 11:18:03 | May 04, 2021 10:16:37 | 4 |  |  | PP-1090 |  | Sprint 6 |  | Filters or Visualization Navigation Convenience features | MVP | 2
3.1.7 | LOB Filter | make a cleanup in the tab following the rules from the design | [11 empty] | PP-655 |  | Sprint 5 |  |  | MVP | 0
3.1.7.1 | LOB filter [2nd and 3rd panel] |  |  | 4 |  |  | 4 | Paulina | Apr 22, 2021 07:32:08 | Apr 26, 2021 12:02:16 | 7 |  |  | PP-1091 |  | Sprint 5 |  | Filters - LOB filters | MVP | 4
3.1.7.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  |  | 2 |  |  | 2 | Paulina | Apr 22, 2021 14:11:50 | Apr 27, 2021 08:23:30 | 2.75 |  |  | PP-1092 |  | Sprint 5 |  | Filters - Convenience features | MVP | 2
3.1.7.3 | Filter search |  |  | 2 |  |  | 2 | Paulina | Apr 23, 2021 08:46:13 | Apr 27, 2021 08:23:35 | 2.75 |  |  | PP-1093 |  | Sprint 5 |  | Filters - Convenience features | MVP | 2
3.1.7.4 | Tooltips when hovering over filters |  |  | 2 |  |  | 2 | Paulina | Apr 23, 2021 09:22:20 | Apr 27, 2021 08:23:41 | 2.5 |  |  | PP-1094 |  | Sprint 5 |  | Filters - Convenience features | MVP | 2
3.1.7.5 | Clear filters feature |  |  | 2 |  |  | 2 | Paulina | Apr 23, 2021 11:20:56 | Apr 27, 2021 08:23:45 | 2.5 |  |  | PP-1095 |  | Sprint 5 |  | Filters - Convenience features | MVP | 2
3.1.8 | Graph View | make a cleanup in the tab following the rules from the design | [11 empty] | PP-656 |  | Sprint 7 |  |  | MVP | 0
3.1.8.1 | Loading the default view/report |  |  | 1 |  |  | 1 | Monika | May 12, 2021 07:07:13 | May 21, 2021 11:04:45 | 0.66667 |  |  | PP-1096 |  | Sprint 7 |  | Visualization Generation | MVP | 1
3.1.8.2 | Market share Graph + filters [check calculations results here] |  |  | 20 |  |  | 20 | Monika | May 19, 2021 07:31:55 | May 25, 2021 07:38:56 | 4.8333 |  |  | PP-1097 |  | Sprint 7 |  | Visualization Generation | MVP | 20
3.1.8.3 | Benchmark Graph + filters [general cases, calculations checked in benchmark tab] |  |  | 16 |  |  | 16 | Monika | May 12, 2021 08:07:57 | May 25, 2021 07:38:58 | 8.25 |  |  | PP-1098 |  | Sprint 7 |  | Visualization Generation | MVP | 16
3.1.8.4 | Multi-layer Graph view (all navigation types checked in here) |  |  | 10 |  |  | 10 | Monika | May 19, 2021 07:32:43 | May 25, 2021 07:38:59 | 4.8333 |  |  | PP-1099 |  | Sprint 7 |  | Graph visualization convenience features | MVP | 10
3.1.8.5 | Graph view maximum number of nodes display |  |  | 6 |  |  | 6 | Monika | May 19, 2021 07:30:48 | May 21, 2021 11:05:02 | 3.5 |  |  | PP-1100 |  | Sprint 7 |  | Graph visualization convenience features | MVP | 6
3.1.8.6 | Highlight a node for re-calculation |  |  | 6 |  |  | 6 | Monika | May 17, 2021 06:36:39 | May 25, 2021 07:39:01 | 7.5 |  |  | PP-1101 |  | Sprint 7 |  | Graph visualization convenience features | MVP | 6
3.1.8.7 | Orders settings |  |  | 4 |  |  | 4 | Monika | May 14, 2021 12:13:21 | May 21, 2021 11:05:07 | 3 |  |  | PP-1102 |  | Sprint 7 |  | Graph visualization convenience features | MVP | 4
3.1.8.8 | Legend for Graph [general tests only, check calculations along with graph + filters category, dynamic legend with navigation/multi-layer graph] |  |  | 4 |  |  | 4 | Monika | May 14, 2021 12:13:12 | May 21, 2021 11:05:11 | 3 |  |  | PP-1103 |  | Sprint 7 |  | Visualization Legend | MVP | 4
3.1.8.9 | Custom error messages related to filter choice |  |  | 4 |  |  | 4 | Monika | May 13, 2021 11:33:39 | May 21, 2021 11:05:14 | 3 |  |  | PP-1104 |  | Sprint 7 |  | System | MVP | 4
3.1.8.10 | Exit the view and warning popups |  |  | 1 |  |  | 1 | Monika | May 13, 2021 07:22:49 | May 21, 2021 11:05:17 | 1 |  |  | PP-1105 |  | Sprint 7 |  | System | MVP | 1
3.1.8.11 | Navigation menu (switching between view types, market share and benchmark modes) |  |  | 2 |  |  | 2 | Monika | May 13, 2021 10:45:07 | May 21, 2021 11:05:21 | 2 |  |  | PP-1106 |  | Sprint 7 |  | Visualization Navigation | MVP | 2
3.1.9 | Map View | make a cleanup in the tab following the rules from the design | [11 empty] | PP-657 |  | Sprint 7 |  |  | MVP | 0
3.1.9.1 | Market share Map + filters [check calculations results here] |  |  | 20 |  |  | 20 | Paulina | May 11, 2021 15:05:49 | May 21, 2021 06:33:18 | 12 |  |  | PP-1107 |  | Sprint 7 |  | Visualization Generation | MVP | 20
3.1.9.2 | Benchmark view Map + filters [general cases, calculations checked in benchmark tab] |  |  | 16 |  |  | 16 | Paulina | May 14, 2021 11:56:41 | May 21, 2021 06:34:38 | 5 |  |  | PP-1108 |  | Sprint 7 |  | Visualization Generation | MVP | 16
3.1.9.3 | Map view navigation |  |  | 6 |  |  | 6 | Paulina | May 13, 2021 06:48:43 | May 21, 2021 06:35:27 | 5.75 |  |  | PP-1109 |  | Sprint 7 |  | Visualization Navigation | MVP | 6
3.1.9.4 | Opacity slider for map |  |  | 2 |  |  | 2 | Paulina | May 13, 2021 12:06:26 | May 18, 2021 14:20:25 | 1 |  |  | PP-1110 |  | Sprint 7 |  | Graph visualization convenience features | MVP | 2
3.1.9.5 | Legend for Map [general tests only, check calculations along with graph + filters category] + dynamic legend |  |  | 4 |  |  | 4 | Paulina | May 13, 2021 12:56:04 | May 21, 2021 06:47:19 | 3.25 |  |  | PP-1111 |  | Sprint 7 |  | Visualization Legend | MVP | 4
3.1.9.6 | Custom error messages related to filter choice |  |  | 4 |  |  | 4 | Paulina | May 14, 2021 07:37:25 | May 18, 2021 14:59:00 | 3 |  |  | PP-1112 |  | Sprint 7 |  | System | MVP | 4
3.1.9.7 | Exit the view and warning popups |  |  | 1 |  |  | 1 | Paulina | May 14, 2021 11:03:33 | May 19, 2021 05:44:58 | 1.5 |  |  | PP-1113 |  | Sprint 7 |  | System | MVP | 1
3.1.10 | 2D Graph View | make a cleanup in the tab following the rules from the design | [11 empty] | PP-658 |  |  |  |  | MVP | 0
3.1.10.1 | 2D graph view + filters [general cases, calculations checked in benchmark tab] |  |  | 16 |  |  | 16 | Paulina |  |  | 4 |  |  | PP-1114 |  | Sprint 7 |  | Visualization Generation | MVP | 16
3.1.10.2 | 2D Navigation |  |  | 8 |  |  | 8 | Paulina | May 17, 2021 09:49:10 | May 21, 2021 07:16:31 | 6 |  |  | PP-1115 |  | Sprint 7 |  | Visualization Navigation | MVP | 8
3.1.10.3 | Legend for 2D [general tests only, check calculations along with graph + filters category] + dynamic legend |  |  | 4 |  |  | 4 | Paulina | May 18, 2021 07:02:34 | May 21, 2021 07:16:34 | 3 |  |  | PP-1116 |  | Sprint 7 |  | Visualization Legend | MVP | 4
3.1.10.4 | Custom error messages related to filter choice |  |  | 4 |  |  | 4 | Paulina | May 18, 2021 09:32:51 | May 21, 2021 07:16:37 | 3 |  |  | PP-1117 |  | Sprint 7 |  | System | MVP | 4
3.1.10.5 | Exit the view and warning popups |  |  | 1 |  |  | 1 | Paulina | May 18, 2021 13:00:36 | May 21, 2021 07:16:40 | 1 |  |  | PP-1118 |  | Sprint 7 |  | System | MVP | 1
3.1.11 | Benchmark Settings and calculations on Graph | make a cleanup in the tab following the rules from the design | [11 empty] | PP-659 |  |  |  |  | MVP | 0
3.1.11.1 | Benchmarking default settings for Graph and benchmark calculation |  |  | 1 |  |  | 1 | Monika | May 19, 2021 13:21:13 | May 25, 2021 08:23:39 | 0.5 |  |  | PP-1119 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 1
3.1.11.2 | Benchmarking Measures |  |  | 6 |  |  | 6 | Monika | May 19, 2021 13:45:25 | May 25, 2021 08:23:40 | 1 |  |  | PP-1120 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.1.11.3 | Benchmark standard level of aggregations |  |  | 6 |  |  | 6 | Monika | May 20, 2021 06:31:33 | May 25, 2021 08:23:42 | 0.5 |  |  | PP-1121 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.1.11.4 | Benchmark additional Level of aggregations (Regional) |  |  | 4 |  |  | 2 | [6 empty] | PP-1122 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.1.11.5 | Benchmark metrics by percentile & average |  |  | 4 |  |  | 4 | Monika | May 20, 2021 06:31:59 | May 25, 2021 08:23:43 | 0.5 |  |  | PP-1123 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 4
3.1.11.6 | Benchmark time range |  |  | 6 |  |  | 6 | Monika | May 20, 2021 06:32:22 | May 25, 2021 08:23:44 | 1 |  |  | PP-1124 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.1.11.7 | Benchmark to LOB settings |  |  | 4 |  |  | 2 | [6 empty] | PP-1125 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.1.11.8 | Search function on benchmark settings |  |  | 4 |  |  | 4 | Monika | May 21, 2021 06:45:16 | May 25, 2021 08:23:45 | 1.5 |  |  | PP-1126 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 4
3.1.11.9 | Benchmark calculations (all filters + various benchmark settings) |  |  | 20 |  |  | 20 | Monika | May 24, 2021 06:03:55 | Jun 02, 2021 08:02:10 | 10.5 |  |  | PP-1127 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 20
3.1.12 | Benchmark Settings and calculations on Map | make a cleanup in the tab following the rules from the design | [11 empty] | PP-660 |  |  |  |  | MVP | 0
3.1.12.1 | Benchmarking default settings for Map and benchmark calculation |  |  | 1 |  |  | 1 | Monika | May 24, 2021 10:35:13 | May 28, 2021 07:09:05 | 0.5 |  |  | PP-1128 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 1
3.1.12.2 | Benchmarking Measures |  |  | 6 |  |  | 6 | Monika | May 24, 2021 11:07:37 | May 28, 2021 07:09:06 | 0.5 |  |  | PP-1129 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.1.12.3 | Benchmark standard level of aggregations |  |  | 6 |  |  | 6 | Monika | May 24, 2021 11:34:15 | May 28, 2021 07:09:08 | 0.5 |  |  | PP-1130 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.1.12.4 | Benchmark additional Level of aggregations (Regional) |  | 3.1.11.4 | 4 |  |  | 1 | [6 empty] | PP-1131 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.1.12.5 | Benchmark metrics by percentile & average |  |  | 4 |  |  | 4 | Monika | May 25, 2021 07:41:50 | May 28, 2021 07:09:10 | 1 |  |  | PP-1132 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 4
3.1.12.6 | Benchmark time range |  |  | 6 |  |  | 6 | Monika | May 25, 2021 10:04:04 | May 28, 2021 07:09:11 | 1 |  |  | PP-1133 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.1.12.7 | Benchmark to LOB settings |  | 3.1.11.7 | 4 |  |  | 1 | [6 empty] | PP-1134 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.1.12.8 | Search function on benchmark settings |  |  | 4 |  |  | 4 | Monika | May 25, 2021 10:18:09 | May 28, 2021 07:09:13 | 1.5 |  |  | PP-1135 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 4
3.1.12.9 | Benchmark calculations (all filters + various benchmark settings) |  |  | 20 |  |  | 20 | Monika | May 25, 2021 10:19:12 | Jun 02, 2021 07:46:34 | 8.5 |  |  | PP-1136 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 20
3.1.13 | Benchmark Settings and calculations on 2D | make a cleanup in the tab following the rules from the design | [11 empty] | PP-661 |  |  |  |  | MVP | 0
3.1.13.1 | Benchmarking default settings for 2D and benchmark calculation |  |  | 1 |  |  | 1 | Monika | May 26, 2021 09:59:29 | May 31, 2021 12:02:03 | 0.5 |  |  | PP-1137 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 1
3.1.13.2 | Benchmarking Measures |  |  | 6 |  |  | 6 | Monika | May 27, 2021 06:27:12 | May 31, 2021 12:02:04 | 2 |  |  | PP-1138 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.1.13.3 | Benchmark standard level of aggregations |  |  | 6 |  |  | 6 | Monika | May 27, 2021 06:27:54 | May 31, 2021 12:02:06 | 0.5 |  |  | PP-1139 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.1.13.4 | Benchmark additional Level of aggregations (Regional) |  | 3.1.11.4 | 4 |  |  | 1 | [6 empty] | PP-1140 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.1.13.5 | Benchmark metrics by percentile & average |  |  | 4 |  |  | 4 | Monika | May 27, 2021 06:29:30 | May 31, 2021 12:02:07 | 1 |  |  | PP-1141 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 4
3.1.13.6 | Benchmark time range |  |  | 6 |  |  | 6 | Monika | May 27, 2021 06:31:07 | May 31, 2021 12:02:09 | 1.5 |  |  | PP-1142 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.1.13.7 | Benchmark to LOB settings |  | 3.1.11.7 | 4 |  |  | 1 | [6 empty] | PP-1143 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.1.13.8 | Search function on benchmark settings |  |  | 4 |  |  | 4 | Monika | May 27, 2021 09:08:26 | May 31, 2021 12:02:10 | 1 |  |  | PP-1144 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 4
3.1.13.9 | Benchmark calculations (all filters + various benchmark settings) |  |  | 20 |  |  | 20 | Monika | May 27, 2021 09:17:15 | Jun 07, 2021 13:26:50 | 13 |  |  | PP-1145 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 20
3.1.14 | Label settings | make a cleanup in the tab following the rules from the design | [11 empty] | PP-662 |  | Sprint 6 |  |  | MVP | 0
3.1.14.1 | Labels on Graph |  |  | 12 |  |  | 12 | Swatantra | May 13, 2021 09:19:53 | May 20, 2021 11:00:11 | 16.5 |  |  | PP-1146 |  | Sprint 6 |  | Label settings | MVP | 12
3.1.14.2 | Labels on Map |  |  | 6 |  |  | 6 | Swatantra | May 13, 2021 12:12:56 | May 20, 2021 11:00:09 | 7.5 |  |  | PP-1147 |  | Sprint 6 |  | Label settings | MVP | 6
3.1.14.3 | Labels on 2D Graph |  |  | 6 |  |  | 6 | Swatantra | May 18, 2021 13:07:38 | May 20, 2021 11:00:08 | 8.5 |  |  | PP-1148 |  | Sprint 6 |  | Label settings | MVP | 6
3.1.15 | LDS suppression rule-11 (after implementation add LDS test cases to check CC11 ) | make a cleanup in the tab following the rules from the design | [11 empty] | PP-663 |  | Sprint 9 |  |  | MVP | 0
3.1.15.1 | LDS suppression rule-11 |  |  | 38 |  |  | 38 | [6 empty] | PP-1149 |  | Sprint 9 |  | LDS suppression rule-11 | MVP | 0
3.1.15.2 | LDS rule-11 in screen floating message |  |  | 2 |  |  | 2 | [6 empty] | PP-1150 |  | Sprint 9 |  | LDS suppression rule-11 | MVP | 0
3.1.16 | Save or export Visualization | make a cleanup in the tab following the rules from the design | [11 empty] | PP-664 |  | Sprint 9 |  |  | MVP | 0
3.1.16.1 | Export as PNG |  |  | 4 |  |  | 4 | Monika, Paulina | Apr 26, 2021 07:27:36 | May 04, 2021 10:20:07 | 12.5 |  |  | PP-1151 |  | Sprint 6 |  | Save or export Visualization | MVP | 4
3.1.16.2 | Export the View as Excel |  |  | 8 |  |  | 8 | Kamil | [5 empty] | PP-1152 |  | Sprint 9 |  | Save or export Visualization | MVP | 0
3.1.17 | System | make a cleanup in the tab following the rules from the design | [11 empty] | PP-665 |  | Sprint 9 |  |  | MVP | 0
3.1.17.1 | Inactivity countdown timer |  |  | 2 |  |  | 2 | [6 empty] | PP-1153 |  | Sprint 9 |  | System | MVP | 0
3.1.17.2 | View user manual |  |  | 1 |  |  | 1 | [6 empty] | PP-1154 |  | Sprint 9 |  | System | MVP | 0
3.1.17.3 | Customer support contact information icons |  |  | 1 |  |  | 1 | [6 empty] | PP-1155 |  | Sprint 9 |  | System | MVP | 0
3.1.17.4 | Versioning and copyright maintenance |  |  | 1 |  |  | 1 | [6 empty] | PP-1156 |  | Sprint 9 |  | System | MVP | 0
3.1.18 | Show Details | make a cleanup in the tab following the rules from the design | [11 empty] | PP-1157 |  | Sprint 9 |  |  | MVP | 0
3.1.18.1 | Contex menu - Graph View |  |  | 2 |  |  | 2 | Monika | Jun 04, 2021 04:52:37 | Jun 08, 2021 12:40:13 | 1.5 |  |  | PP-1158 |  | Sprint 9 |  | Visualization Generation | MVP | 2
3.1.18.2 | Context menu - 2D Graph View |  |  | 1 |  |  | 1 | Monika | Jun 04, 2021 06:10:58 | Jun 08, 2021 12:40:14 | 1 |  |  | PP-1159 |  | Sprint 9 |  | Visualization Generation | MVP | 1
3.1.18.3 | Context menu - Map view |  |  | 1 |  |  | 1 | Monika | Jun 04, 2021 06:53:23 | Jun 08, 2021 12:40:15 | 1 |  |  | PP-1160 |  | Sprint 9 |  | Visualization Generation | MVP | 1
3.1.18.4 | Show details panel |  |  | 8 |  |  | 8 | Monika | Jun 01, 2021 14:15:23 | Jun 08, 2021 12:40:16 | 7.5 |  |  | PP-1161 |  | Sprint 9 |  | Visualization Generation | MVP | 8
3.2 | Automating regression library test cases | [12 empty] | PP-666 |  | Sprint 9 |  |  | MVP | 0
3.2.1 | Authentication & Authorization | automate tests from the tab | 3.1.1 | [10 empty] | PP-667 |  |  |  |  | MVP | 0
3.2.1.1 | Authentication Module |  | 3.1.1.1 | 6 |  |  | 6 | [6 empty] | PP-1162 |  |  |  | Authentication & Authorization | MVP | 0
3.2.1.2 | Multi-tenancy |  | 3.1.1.2 | 4 |  |  | 5 | [6 empty] | PP-1163 |  |  |  | Authentication & Authorization | MVP | 0
3.2.1.3 | Password requirements |  | 3.1.1.3 | 2 |  |  | 4 | [6 empty] | PP-1164 |  |  |  | Authentication & Authorization | MVP | 0
3.2.1.4 | Change password |  | 3.1.1.4 | 8 |  |  | 8 | [6 empty] | PP-1165 |  |  |  | Authentication & Authorization | MVP | 0
3.2.1.5 | Email Notifications & New email templates |  | 3.1.1.5 | 8 |  |  | 8 | [6 empty] | PP-1166 |  |  |  | Authentication & Authorization | MVP | 0
3.2.2 | Dataset Upload & Management | automate tests from the tab | 3.1.2 | [10 empty] | PP-699 |  |  |  |  | MVP | 0
3.2.2.0 | Implement DatasetMangementPage and methods | Draft: https://gitlab-01.itx.pl/p2-project/tests/p2-selenium-tests-v2/-/merge_requests/5/diffs |  | 6 |  |  | 6 | [6 empty] | PP-1392 |  |  |  |  | MVP | 0
3.2.2.1 | Dataset upload |  | 3.1.2.1, 3.2.2.0 | 6 |  |  | 6 | [6 empty] | PP-1167 |  |  |  | Dataset Upload & Management | MVP | 0
3.2.2.2 | Dataset permissions |  | 3.1.2.2, 3.2.2.0 | 4 |  |  | 4 | [6 empty] | PP-1168 |  |  |  | Dataset Upload & Management | MVP | 0
3.2.2.3 | View datasets details |  | 3.1.2.3, 3.2.2.0 | 5 |  |  | 5 | [6 empty] | PP-1169 |  |  |  | Dataset Upload & Management | MVP | 0
3.2.2.4 | Delete Dataset |  | 3.1.2.4, 3.2.2.0 | 3 |  |  | 3 | [6 empty] | PP-1170 |  |  |  | Dataset Upload & Management | MVP | 0
3.2.2.5 | Export datasets statistics details as Excel file |  | 3.1.2.5, 3.2.2.0 | 6 |  |  | 6 | [6 empty] | PP-1171 |  |  |  | Dataset Upload & Management | MVP | 0
3.2.2.6 | Statistics preview of a dataset by entity type |  | 3.1.2.6, 3.2.2.0 | 3 |  |  | 5 | [6 empty] | PP-1172 |  |  |  | Dataset Upload & Management | MVP | 0
3.2.3 | View Dashboard | automate tests from the tab | 3.1.3 | [10 empty] | PP-668 |  | Sprint 6 |  |  | MVP | 0
3.2.3.1 | View Creation |  | 3.1.3.1 | 6 |  |  | 6 | Paulina | Apr 27, 2021 11:08:53 | Apr 28, 2021 08:40:41 | 5.5 |  |  | PP-1173 |  | Sprint 5 |  | View Dashboard | MVP | 6
3.2.3.2 | View Management (delete, search, etc) + search by dataset + save view/new view |  | 3.1.3.2 | 10 |  |  | 10 | Paulina | Apr 28, 2021 08:23:02 | May 06, 2021 07:45:36 | 12 |  |  | PP-1174 |  | Sprint 6 |  | View Dashboard | MVP | 10
3.2.3.3 | View duplication |  | 3.1.3.3 | 2 |  |  | 2 | Paulina | Apr 21, 2021 11:54:35 | May 06, 2021 07:45:42 | 2 |  |  | PP-1175 |  | Sprint 5 |  | View Dashboard | MVP | 2
3.2.3.4 | View name editing |  | 3.1.3.4 | 2 |  |  | 2 | Paulina | Apr 21, 2021 12:56:39 | May 06, 2021 07:45:45 | 2.75 |  |  | PP-1176 |  | Sprint 5 |  | View Dashboard | MVP | 2
3.2.4 | Location Filter | automate tests from the tab | 3.1.4, 3.2.19.1 | [10 empty] | PP-669 |  |  |  |  | MVP | 0
3.2.4.1 | Location filter by states & FIPS & CBSA [2nd and 3rd panel] |  | 3.1.4.1, 3.2.19.1 | 16 |  |  | 16 | Paulina | May 04, 2021 11:05:35 | May 17, 2021 13:23:22 | 22.5 |  |  | PP-1177 |  | Sprint 6 |  | Location filter by FIPS | MVP | 16
3.2.4.2 | Location filter by Radius map [2nd and 3rd panel] |  | 3.1.4.2, 3.2.19.1 | 16 |  |  | 16 | Piotr | May 06, 2021 07:38:49 | May 14, 2021 10:37:46 | 28 |  |  | PP-1178 |  | Sprint 6 |  | Location filter by FIPS | MVP | 16
3.2.4.3 | Location filter switch between grayscale and terrain |  | 3.1.4.3, 3.2.19.1 | 2 |  |  | 2 | Paulina | May 07, 2021 07:20:41 | May 07, 2021 09:46:12 | 2 |  |  | PP-1179 |  | Sprint 6 |  | Location filter by FIPS | MVP | 2
3.2.4.4 | Location filter applies to |  | 3.1.4.4, 3.2.19.1 | 8 |  |  | 8 | Paulina | May 31, 2021 12:21:38 | Jun 01, 2021 11:03:03 | 2.5 |  |  | PP-1180 |  | Sprint 8 |  | Location filter by FIPS | MVP | 8
3.2.4.5 | Tooltips for location filters |  | 3.1.4.5, 3.2.19.1 | 4 |  |  | 4 | Paulina | May 31, 2021 13:46:28 | Jun 08, 2021 11:18:00 | 9.5 |  |  | PP-1181 |  | Sprint 8 |  | Location filter by FIPS | MVP | 4
3.2.4.6 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features e.g. scrolling/zooming map] |  | 3.1.4.6, 3.2.19.1 | 8 |  |  | 8 | Paulina | Jun 02, 2021 06:03:25 | Jun 07, 2021 13:22:30 | 3 |  |  | PP-1182 |  | Sprint 8 |  | Filters - Convenience features | MVP | 8
3.2.4.7 | Pagination of the Entity, Service Lines,..Filters |  | 3.1.4.7, 3.2.19.1 | 4 |  |  | 4 | Paulina | May 10, 2021 08:54:07 | May 12, 2021 14:24:19 | 2 |  |  | PP-1183 |  | Sprint 6 |  | Filters - Convenience features | MVP | 4
3.2.4.8 | Filter search |  | 3.1.4.8, 3.2.19.1 | 4 |  |  | 4 | Paulina | May 07, 2021 09:56:59 | May 11, 2021 09:16:47 | 6 |  |  | PP-1184 |  | Sprint 6 |  | Filters - Convenience features | MVP | 4
3.2.4.9 | Clear filters feature |  | 3.1.4.9, 3.2.19.1 | 2 |  |  | 2 | Paulina | May 10, 2021 10:51:13 | May 13, 2021 06:58:12 | 2 |  |  | PP-1185 |  | Sprint 6 |  | Filters - Convenience features | MVP | 2
3.2.4.10 | Filters breadcrumb (tree structures) |  | 3.1.4.10, 3.2.19.1 | 8 |  |  | 8 | Paulina | May 10, 2021 13:19:02 | May 13, 2021 11:58:29 | 4 |  |  | PP-1186 |  | Sprint 6 |  | Filters or Visualization Navigation Convenience features | MVP | 8
3.2.4.11 | Filters breadcrumb navigation to the selected layer |  | 3.1.4.11, 3.2.19.1 | 4 |  |  | 4 | Paulina | May 11, 2021 10:21:28 | May 14, 2021 10:38:10 | 1 |  |  | PP-1187 |  | Sprint 6 |  | Filters or Visualization Navigation Convenience features | MVP | 4
3.2.5 | Entity Filter | automate tests from the tab | 3.1.5, 3.2.19.1 | [10 empty] | PP-670 |  |  |  |  | MVP | 0
3.2.5.1 | Entity-post acute type filter & Entity-Hospital filter [2nd and 3rd panel] |  | 3.1.5.1, 3.2.19.1 | 16 |  |  | 16 | Swatantra | Jun 08, 2021 13:45:05 | Jun 17, 2021 08:29:39 | 18 |  |  | PP-1188 |  |  |  | Filters - Entity filters | MVP | 16
3.2.5.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  | 3.1.5.2, 3.2.19.1 | 8 |  |  | 8 | Swatantra | Jun 04, 2021 14:53:26 | Jun 10, 2021 08:33:50 | 11.5 |  |  | PP-1189 |  | Sprint 8 |  | Filters - Entity filters | MVP | 8
3.2.5.3 | Pagination of the Entity, Service Lines,..Filters |  | 3.1.5.3, 3.2.19.1 | 4 |  |  | 4 | Monika | May 10, 2021 10:53:59 | May 13, 2021 14:14:07 | 8.5 |  |  | PP-1190 |  | Sprint 6 |  | Filters - Convenience features | MVP | 4
3.2.5.4 | Filter search |  | 3.1.5.4, 3.2.19.1 | 4 |  |  | 4 | Monika | May 10, 2021 10:51:57 | May 13, 2021 12:29:02 | 12.5 |  |  | PP-1191 |  | Sprint 6 |  | Filters - Convenience features | MVP | 4
3.2.5.5 | Tooltips when hovering over filters |  | 3.1.5.5, 3.2.19.1 | 4 |  |  | 4 | Swatantra | Jun 03, 2021 10:41:44 | Jun 10, 2021 12:23:41 | 6.5 |  |  | PP-1192 |  | Sprint 8 |  | Filters - Convenience features | MVP | 4
3.2.5.6 | Clear filters feature |  | 3.1.5.6, 3.2.19.1 | 2 |  |  | 2 | Monika | May 11, 2021 12:33:24 | May 14, 2021 07:19:23 | 7 |  |  | PP-1193 |  | Sprint 6 |  | Filters - Convenience features | MVP | 2
3.2.5.7 | Filters breadcrumb (tree structures) for Service Line and Entity filters |  | 3.1.5.7, 3.2.19.1 | 6 |  |  | 6 | Swatantra | Jun 11, 2021 14:32:18 | Jun 17, 2021 10:27:48 | 10 |  |  | PP-1194 |  |  |  | Filters or Visualization Navigation Convenience features | MVP | 6
3.2.5.8 | Filters breadcrumb navigation to the selected layer |  | 3.1.5.8, 3.2.19.1 | 4 |  |  | 4 | Swatantra | Jun 04, 2021 07:30:55 | Jun 17, 2021 10:33:01 | 6.5 |  |  | PP-1195 |  |  |  | Filters or Visualization Navigation Convenience features | MVP | 4
3.2.5.9 | Filters overview |  | 3.1.5.8, 3.2.19.1 |  |  |  | 5 | Swatantra | Jun 23, 2021 12:07:20 | Jun 23, 2021 12:41:45 | 5 |  |  | PP-1636 |  |  |  | Filters or Visualization Navigation Convenience features | MVP
3.2.5.10 | Context menu |  | 3.1.5.8, 3.2.19.1 |  |  |  | 2 | Swatantra | Jun 23, 2021 15:13:17 | Jun 24, 2021 08:41:20 | 2.5 |  |  | PP-1637 |  |  |  | Filters or Visualization Navigation Convenience features | MVP
3.2.6 | Service Line filter | automate tests from the tab | 3.1.6, 3.2.19.1 | [10 empty] | PP-671 |  |  |  |  | MVP | 0
3.2.6.1 | Service line filter [SL, Episode, DRG levels - 2nd and 3rd panel] |  | 3.1.6.1, 3.2.19.1 | 16 |  |  | 16 | Bartek | May 17, 2021 12:06:21 | May 20, 2021 10:59:31 | 7.5 |  |  | PP-1196 |  | Sprint 6 |  | Filters - Service Line filters | MVP | 16
3.2.6.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  | 3.1.6.2, 3.2.19.1 | 8 |  |  | 8 | Swatantra | May 24, 2021 06:03:58 | May 25, 2021 07:06:50 | 17 |  |  | PP-1197 |  | Sprint 6 |  | Filters - Convenience features | MVP | 8
3.2.6.3 | Pagination of the Entity, Service Lines,..Filters |  | 3.1.6.3, 3.2.19.1 | 4 |  |  | 2 | [6 empty] | PP-1198 |  |  |  | Filters - Convenience features | MVP | 0
3.2.6.4 | Filter search |  | 3.1.6.4, 3.2.19.1 | 4 |  |  | 4 | Swatantra | May 25, 2021 14:07:20 | May 26, 2021 06:18:37 | 7 |  |  | PP-1199 |  | Sprint 6 |  | Filters - Convenience features | MVP | 4
3.2.6.5 | Tooltips when hovering over filters |  | 3.1.6.5, 3.2.19.1 | 4 |  |  | 4 | Swatantra | May 26, 2021 13:28:31 | Jun 01, 2021 07:09:18 | 10 |  |  | PP-1200 |  | Sprint 8 |  | Filters - Convenience features | MVP | 4
3.2.6.6 | Clear filters feature |  | 3.1.6.6, 3.2.19.1 | 2 |  |  | 2 | Swatantra | May 27, 2021 12:29:31 | Jun 01, 2021 11:43:10 | 7 |  |  | PP-1201 |  | Sprint 8 |  | Filters - Convenience features | MVP | 2
3.2.6.7 | Filters breadcrumb (tree structures) for Service Line and Entity filters |  | 3.1.6.7, 3.2.19.1 | 6 |  |  | 6 | Swatantra | Jun 02, 2021 15:38:08 | Jun 07, 2021 13:35:03 | 6 |  |  | PP-1202 |  | Sprint 8 |  | Filters or Visualization Navigation Convenience features | MVP | 6
3.2.6.8 | Filters breadcrumb navigation to the selected layer |  | 3.1.6.8, 3.2.19.1 | 4 |  |  | 4 | Swatantra | Jun 02, 2021 15:38:39 | Jun 07, 2021 14:03:18 | 5.5 |  |  | PP-1203 |  | Sprint 8 |  | Filters or Visualization Navigation Convenience features | MVP | 4
3.2.7 | LOB Filter | automate tests from the tab | 3.1.7, 3.2.19.1 | [10 empty] | PP-672 |  | Sprint 6 |  | Filters - LOB filters | MVP | 0
3.2.7.1 | LOB filter [2nd and 3rd panel] |  | 3.1.7.1, 3.2.19.1 | 8 |  |  | 8 | Bartek | Apr 22, 2021 07:01:33 | May 12, 2021 10:14:12 | 26 |  |  | PP-1204 |  | Sprint 6 |  | Filters - LOB filters | MVP | 8
3.2.7.2 | Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] |  | 3.1.7.2, 3.2.19.1 | 4 |  |  | 4 | Bartek | May 12, 2021 10:14:45 | May 12, 2021 10:15:00 | 7.5 |  |  | PP-1205 |  | Sprint 6 |  | Filters - Convenience features | MVP | 4
3.2.7.3 | Filter search |  | 3.1.7.3, 3.2.19.1 | 2 |  |  | 2 | Bartek | May 13, 2021 12:14:49 | May 13, 2021 13:06:24 | 4.5 |  |  | PP-1206 |  | Sprint 6 |  | Filters - Convenience features | MVP | 2
3.2.7.4 | Tooltips when hovering over filters |  | 3.1.7.4, 3.2.19.1 | 2 |  |  | 2 | Bartek | May 13, 2021 13:06:31 | May 13, 2021 13:49:33 | 2.5 |  |  | PP-1207 |  | Sprint 6 |  | Filters - Convenience features | MVP | 2
3.2.7.5 | Clear filters feature |  | 3.1.7.5, 3.2.19.1 | 2 |  |  | 2 | Bartek | May 17, 2021 09:26:27 | May 18, 2021 06:35:18 | 12.5 |  |  | PP-1208 |  | Sprint 6 |  | Filters - Convenience features | MVP | 2
3.2.8 | Graph View | automate tests from the tab | 3.1.8 | [10 empty] | PP-673 |  |  |  | Visualization Generation | MVP | 0
3.2.8.0 | Implement GraphViewPage and methods |  |  | 12 |  |  | 12 | Paulina | May 24, 2021 07:14:23 | May 24, 2021 13:08:15 | 12.25 |  |  | PP-1393 |  | Sprint 7 |  | Visualization Generation | MVP | 12
3.2.8.1 | Loading the default view/report |  | 3.1.8.1, 3.2.8.0 | 2 |  |  | 2 | Monika | Jun 04, 2021 09:13:55 | Jun 22, 2021 10:51:05 | 2.5 |  |  | PP-1209 |  |  |  | Visualization Generation | MVP | 2
3.2.8.2 | Market share Graph + filters [check calculations results here] |  | 3.1.8.2, 3.2.8.0, 3.2.19.2, 6.5 | 12 |  |  | 12 | Monika | [5 empty] | PP-1210 |  |  |  | Visualization Generation | MVP | 0
3.2.8.3 | Benchmark Graph + filters [general cases, calculations checked in benchmark tab] |  | 3.1.8.3, 3.2.8.0, 3.2.19.2 | 10 |  |  | 8 | Monika | Jun 10, 2021 07:05:41 | Jun 22, 2021 11:41:37 | 8 |  |  | PP-1211 |  |  |  | Visualization Generation | MVP | 8
3.2.8.4 | Multi-layer Graph view (all navigation types checked in here) |  | 3.1.8.4, 3.2.8.0, 3.2.19.2 | 12 |  |  | 10 | Monika | Jun 11, 2021 05:42:48 | Jun 22, 2021 12:27:35 | 12 |  |  | PP-1212 |  |  |  | Graph visualization convenience features | MVP | 10
3.2.8.5 | Graph view maximum number of nodes display |  | 3.1.8.5, 3.2.8.0 | 6 |  |  | 6 | [6 empty] | PP-1213 |  |  |  | Graph visualization convenience features | MVP | 0
3.2.8.6 | Highlight a node for re-calculation |  | 3.1.8.6, 3.2.8.0 | 6 |  |  | 6 | Monika | [5 empty] | PP-1214 |  |  |  | Graph visualization convenience features | MVP | 0
3.2.8.7 | Orders settings |  | 3.1.8.7, 3.2.8.0, 3.2.19.4 | 6 |  |  | 7 | Monika | Jun 16, 2021 12:11:19 | Jun 23, 2021 12:05:26 | 8 |  |  | PP-1215 |  |  |  | Graph visualization convenience features | MVP | 7
3.2.8.8 | Legend for Graph [general tests only, check calculations along with graph + filters category, dynamic legend with navigation/multi-layer graph] |  | 3.1.8.8, 3.2.8.0, 3.2.19.2 | 4 |  |  | 4 | Monika | [5 empty] | PP-1216 |  |  |  | Visualization Legend | MVP | 0
3.2.8.9 | Custom error messages related to filter choice |  | 3.1.8.9, 3.2.8.0 | 4 |  |  | 4 | [6 empty] | PP-1217 |  |  |  | System | MVP | 0
3.2.8.10 | Exit the view and warning popups |  | 3.1.8.10, 3.2.8.0 | 2 |  |  | 2 | [6 empty] | PP-1218 |  |  |  | System | MVP | 0
3.2.8.11 | Navigation menu (switching between view types, market share and benchmark modes) |  | 3.1.8.11, 3.2.8.0 | 2 |  |  | 2 | [6 empty] | PP-1219 |  |  |  | Visualization Navigation | MVP | 0
3.2.9 | Map View | automate tests from the tab | 3.1.9 | [10 empty] | PP-674 |  |  |  | Visualization Generation | MVP | 0
3.2.9.0 | Implemet MapViewPage and methods |  |  | 12 |  |  | 12 | Kamil | May 24, 2021 08:12:37 | May 25, 2021 07:03:58 | 5.5 |  |  | PP-1394 |  | Sprint 7 |  | Visualization Generation | MVP | 12
3.2.9.1 | Market share Map + filters [check calculations results here] |  | 3.1.9.1, 3.2.9.0, 3.2.19.2, 6.5 | 16 |  |  | 12 | Paulina | [5 empty] | PP-1220 |  |  |  | Visualization Generation | MVP | 0
3.2.9.2 | Benchmark view Map + filters [general cases, calculations checked in benchmark tab] |  | 3.1.9.2, 3.2.9.0, 3.2.19.2 | 12 |  |  | 12 | Paulina | May 28, 2021 11:37:29 | Jun 01, 2021 09:23:02 | 4.25 |  |  | PP-1221 |  | Sprint 8 |  | Visualization Generation | MVP | 1p
3.2.9.3 | Map view navigation |  | 3.1.9.3, 3.2.9.0 | 12 |  |  | 12 | Paulina | May 27, 2021 10:02:31 | Jun 01, 2021 07:11:27 | 6.5 |  |  | PP-1222 |  | Sprint 8 |  | Visualization Navigation | MVP | 12
3.2.9.4 | Opacity slider for map |  | 3.1.9.4, 3.2.9.0 | 4 |  |  | 3 | Paulina | May 25, 2021 14:17:33 | May 27, 2021 08:25:29 | 2 |  |  | PP-1223 |  | Sprint 7 |  | Graph visualization convenience features | MVP | 3
3.2.9.5 | Legend for Map [general tests only, check calculations along with graph + filters category] + dynamic legend |  | 3.1.9.5, 3.2.9.0, 3.2.19.2 | 4 |  |  | 4 | Paulina | May 28, 2021 06:49:46 | Jun 01, 2021 09:14:49 | 4.5 |  |  | PP-1224 |  | Sprint 8 |  | Visualization Legend | MVP | 4
3.2.9.6 | Custom error messages related to filter choice |  | 3.1.9.6, 3.2.9.0 | 4 |  |  | 4 | Paulina | May 26, 2021 07:30:27 | May 27, 2021 08:25:36 | 4.5 |  |  | PP-1225 |  | Sprint 7 |  | System | MVP | 4
3.2.9.7 | Exit the view and warning popups |  | 3.1.9.7, 3.2.9.0 | 2 |  |  | 2 | Paulina | May 31, 2021 09:09:35 | Jun 01, 2021 10:15:47 | 3.25 |  |  | PP-1226 |  | Sprint 8 |  | System | MVP | 2
3.2.10 | 2D Graph View | automate tests from the tab | 3.1.10 | [10 empty] | PP-675 |  |  |  | Visualization Generation | MVP | 0
3.2.10.0 | Implement 2DGraphViewPage and methods |  |  | 12 |  |  | 12 | Kamil | May 25, 2021 13:53:30 | May 27, 2021 13:56:46 | 8.5 |  |  | PP-1395 |  | Sprint 7 |  | Visualization Generation | MVP | 12
3.2.10.1 | 2D graph view + filters [general cases, calculations checked in benchmark tab] |  | 3.1.10.1, 3.2.10.0, 3.2.19.2 | 16 |  |  | 16 | Paulina | May 31, 2021 12:12:01 | Jun 11, 2021 07:12:30 | 3.5 |  |  | PP-1227 |  | Sprint 8 |  | Visualization Generation | MVP | 16
3.2.10.2 | 2D Navigation |  | 3.1.10.2, 3.2.10.0, 3.2.19.2 | 12 |  |  | 12 | Paulina | Jun 02, 2021 11:51:42 | Jun 10, 2021 13:24:41 | 11 |  |  | PP-1228 |  | Sprint 8 |  | Visualization Navigation | MVP | 12
3.2.10.3 | Legend for 2D [general tests only, check calculations along with graph + filters category] + dynamic legend |  | 3.1.10.3, 3.2.10.0, 3.2.19.2 | 4 |  |  | 4 | Paulina | Jun 07, 2021 07:30:32 | Jun 11, 2021 06:46:10 | 5.75 |  |  | PP-1229 |  | Sprint 8 |  | Visualization Legend | MVP | 4
3.2.10.4 | Custom error messages related to filter choice |  | 3.1.10.4, 3.2.10.0 | 4 |  |  | 4 | Paulina | Jun 08, 2021 06:11:11 | Jun 11, 2021 06:51:32 | 3 |  |  | PP-1230 |  | Sprint 8 |  | System | MVP | 4
3.2.10.5 | Exit the view and warning popups |  | 3.1.10.5, 3.2.10.0 | 2 |  |  | 2 | Paulina | Jun 08, 2021 07:57:23 | Jun 11, 2021 07:12:42 | 3 |  |  | PP-1231 |  | Sprint 8 |  | System | MVP | 2
3.2.11 | Benchmark Settings and calculations on Graph | automate tests from the tab | 3.1.11 | [10 empty] | PP-676 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.11.1 | Benchmarking default settings for Graph and benchmark calculation |  | 3.1.11.1, 3.2.8.0, 3.2.19.2, 3.2.19.3 | 2 |  |  | 2 | Paulina | Jun 16, 2021 10:45:58 | Jun 18, 2021 11:36:07 | 1.5 |  |  | PP-1232 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 2
3.2.11.2 | Benchmarking Measures |  | 3.1.11.2, 3.2.8.0, 3.2.19.3 | 8 |  |  | 2 | Paulina | Jun 16, 2021 10:54:27 | Jun 18, 2021 11:36:08 | 1.5 |  |  | PP-1233 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 2
3.2.11.3 | Benchmark standard level of aggregations |  | 3.1.11.3, 3.2.8.0, 3.2.19.3 | 8 |  |  | 2 | Paulina | Jun 16, 2021 12:29:42 | Jun 18, 2021 11:36:10 | 2 |  |  | PP-1234 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 2
3.2.11.4 | Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) |  | 3.1.11.4, 3.2.8.0, 3.2.19.3 | 4 |  |  | 2 | [6 empty] | PP-1235 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.11.5 | Benchmark metrics by percentile & average |  | 3.1.11.5, 3.2.8.0, 3.2.19.3, 3.2.13.5 | 6 |  |  | 2 | Paulina | Jun 17, 2021 06:29:54 | Jun 18, 2021 11:36:11 | 1.5 |  |  | PP-1236 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 2
3.2.11.6 | Benchmark time range |  | 3.1.11.6, 3.2.8.0, 3.2.19.3 | 8 |  |  | 3 | Paulina | Jun 17, 2021 11:16:41 | Jun 18, 2021 11:36:12 | 2.5 |  |  | PP-1237 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 3
3.2.11.7 | Benchmark to LOB settings |  | 3.1.11.7, 3.2.8.0, 3.2.19.3 | 4 |  |  | 4 | [6 empty] | PP-1238 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.11.8 | Search function on benchmark settings |  | 3.1.11.8, 3.2.8.0, 3.2.19.3 | 6 |  |  | 4 | Paulina | Jun 17, 2021 07:34:05 | Jun 18, 2021 11:36:14 | 3.5 |  |  | PP-1239 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 4
3.2.11.9 | Benchmark calculations (all filters + various benchmark settings) |  | 3.1.11.9, 3.2.8.0, 3.2.19.3, 6.5 | 16 |  |  | 12 | Paulina | Jun 18, 2021 09:22:56 | Jun 22, 2021 11:21:20 | 10 |  |  | PP-1240 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 12
3.2.11.10 | Benchmark entity type for graph |  | 3.1.11.9, 3.2.8.0, 3.2.19.3, 6.5 |  |  |  | 3 | Paulina | Jun 21, 2021 06:12:13 | Jun 21, 2021 06:32:17 | 2.5 |  |  | PP-1638 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP
3.2.12 | Benchmark Settings and calculations on Map | automate tests from the tab | 3.1.12 | [10 empty] | PP-677 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.12.1 | Benchmarking default settings for Map and benchmark calculation |  | 3.1.12.1, 3.2.9.0, 3.2.19.2, 3.2.19.3, 3.2.11.1 | 2 |  |  | 1 | Paulina | Jun 21, 2021 12:05:27 | Jun 24, 2021 08:53:51 | 1 |  |  | PP-1241 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 1
3.2.12.2 | Benchmarking Measures |  | 3.1.12.2, 3.2.9.0, 3.2.19.3, 3.2.11.2 | 7 |  |  | 2 | Paulina | Jun 21, 2021 14:05:59 | Jun 24, 2021 08:55:38 | 2 |  |  | PP-1242 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 2
3.2.12.3 | Benchmark standard level of aggregations |  | 3.1.12.3, 3.2.9.0, 3.2.19.3, 3.2.11.3 | 7 |  |  | 2 | Paulina | Jun 22, 2021 09:42:56 | Jun 24, 2021 09:00:49 | 2 |  |  | PP-1243 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 2
3.2.12.4 | Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) |  | 3.1.12.4, 3.2.9.0, 3.2.19.3, 3.2.11.4 | 4 |  |  | 1 | [6 empty] | PP-1244 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.12.5 | Benchmark metrics by percentile & average |  | 3.1.12.5, 3.2.9.0, 3.2.19.3, 3.2.11.5 | 6 |  |  | 1 | Paulina | Jun 22, 2021 11:41:36 | Jun 24, 2021 09:14:17 | 1 |  |  | PP-1245 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 1
3.2.12.6 | Benchmark time range |  | 3.1.12.6, 3.2.9.0, 3.2.19.3, 3.2.11.6 | 8 |  |  | 3 | Paulina | Jun 22, 2021 06:29:57 | Jun 24, 2021 09:31:09 | 3 |  |  | PP-1246 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 3
3.2.12.7 | Benchmark to LOB settings |  | 3.1.12.7, 3.2.9.0, 3.2.19.3, 3.2.11.7 | 4 |  |  | 2 | [6 empty] | PP-1247 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.12.8 | Search function on benchmark settings |  | 3.1.12.8, 3.2.9.0, 3.2.19.3, 3.2.11.8 | 6 |  |  | 2 | Paulina | Jun 22, 2021 12:42:59 | Jun 24, 2021 09:42:57 | 2 |  |  | PP-1248 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 2
3.2.12.9 | Benchmark calculations (all filters + various benchmark settings) |  | 3.1.12.9, 3.2.9.0, 3.2.19.3, 6.5 | 16 |  |  | 15 | Paulina | [5 empty] | PP-1249 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.13 | Benchmark Settings and calculations on 2D | automate tests from the tab | 3.1.13 | [10 empty] | PP-678 |  | Sprint 9 |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.13.0 | Implement 2DBenchmarkSettingsPage |  | 3.2.19.3 | 8 |  |  | 8 | Paulina | May 24, 2021 11:33:43 | May 25, 2021 10:29:01 | 5.5 |  |  | PP-1396 |  | Sprint 7 |  | Benchmark settings customization & Benchmark Calculation | MVP | 8
3.2.13.1 | Benchmarking default settings for 2D and benchmark calculation |  | 3.1.13.1, 3.2.10.0, 3.2.19.2, 3.2.13.0 | 2 |  |  | 2 | Paulina | Jun 10, 2021 14:07:11 | Jun 11, 2021 13:31:07 | 2.6667 |  |  | PP-1250 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | MVP | 2
3.2.13.2 | Benchmarking Measures |  | 3.1.13.2, 3.2.10.0, 3.2.13.0 | 7 |  |  | 4 | Paulina | Jun 09, 2021 06:12:36 | Jun 11, 2021 08:56:12 | 3.5 |  |  | PP-1251 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | MVP | 4
3.2.13.3 | Benchmark standard level of aggregations |  | 3.1.13.3, 3.2.10.0, 3.2.13.0 | 7 |  |  | 7 | Paulina | Jun 08, 2021 11:36:00 | Jun 11, 2021 09:20:15 | 4.25 |  |  | PP-1252 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | MVP | 7
3.2.13.4 | Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) |  | 3.1.13.4, 3.2.10.0, 3.2.13.0, 3.2.11.4 | 4 |  |  | 2 | [6 empty] | PP-1253 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.13.5 | Benchmark metrics by percentile & average |  | 3.1.13.5, 3.2.10.0, 3.2.13.0 | 6 |  |  | 5 | Paulina | Jun 09, 2021 09:13:07 | Jun 11, 2021 09:36:40 | 3.5 |  |  | PP-1254 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | MVP | 5
3.2.13.6 | Benchmark time range |  | 3.1.13.6, 3.2.10.0, 3.2.13.0 | 8 |  |  | 4 | Paulina | Jun 09, 2021 13:29:45 | Jun 11, 2021 09:41:08 | 6.5 |  |  | PP-1255 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | MVP | 4
3.2.13.7 | Benchmark to LOB settings |  | 3.1.13.7, 3.2.10.0, 3.2.13.0, 3.2.11.7 | 4 |  |  | 2 | [6 empty] | PP-1256 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.13.8 | Search function on benchmark settings |  | 3.1.13.8, 3.2.10.0, 3.2.13.0 | 6 |  |  | 6 | Paulina | Jun 10, 2021 06:08:56 | Jun 11, 2021 11:55:35 | 7.5 |  |  | PP-1257 |  | Sprint 8 |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.2.13.9 | Benchmark calculations (all filters + various benchmark settings) |  | 3.1.13.9, 3.2.10.0, 3.2.13.0, 6.5 | 16 |  |  | 12 | Paulina | [5 empty] | PP-1258 |  | Sprint 9 |  | Benchmark settings customization & Benchmark Calculation | MVP | 0
3.2.13.10 | Benchmark settings update after applying filters |  | 3.1.13.9, 3.2.10.0, 3.2.13.0, 6.5 | 4 |  |  | 4 | Paulina | Jun 14, 2021 07:55:01 | Jun 21, 2021 09:10:21 | 2.5 |  |  | PP-1601 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 4
3.2.13.11 | Benchmark filters by 2D Graph |  | 3.1.13.9, 3.2.10.0, 3.2.13.0, 6.5 | 6 |  |  | 6 | Paulina | Jun 14, 2021 07:16:48 | Jun 21, 2021 09:10:31 | 5 |  |  | PP-1602 |  |  |  | Benchmark settings customization & Benchmark Calculation | MVP | 6
3.2.14 | Label settings | automate tests from the tab | 3.1.14 | [10 empty] | PP-679 |  | Sprint 9 |  | Label settings | MVP | 0
3.2.14.0 | Implement LabelsPage and methods |  |  | 6 |  |  | 6 | Swatantra | May 18, 2021 13:17:25 | May 21, 2021 07:17:51 | 10.5 |  |  | PP-1397 |  | Sprint 7 |  | Label settings | MVP | 6
3.2.14.1 | Labels on Graph |  | 3.1.14.1, 3.2.14.0, 3.2.8.0 | 12 |  |  | 12 | [6 empty] | PP-1259 |  | Sprint 9 |  | Label settings | MVP | 0
3.2.14.2 | Labels on Map |  | 3.1.14.2, 3.2.14.0, 3.2.9.0 | 7 |  |  | 7 | Swatantra | Jun 21, 2021 13:35:37 | Jun 23, 2021 07:36:40 | 7 |  |  | PP-1260 |  | Sprint 9 |  | Label settings | MVP | 7
3.2.14.3 | Labels on 2D Graph |  | 3.1.14.3, 3.2.14.0, 3.2.10.0 | 7 |  |  | 7 | [6 empty] | PP-1261 |  | Sprint 9 |  | Label settings | MVP | 0
3.2.15 | LDS suppression rule-11 (after implementation add LDS test cases to check CC11 ) | automate tests from the tab | 3.1.15 | [10 empty] | PP-680 |  | Sprint 9 |  | LDS suppression rule-10 | MVP | 0
3.2.15.1 | LDS suppression rule-11 |  | 3.1.15.1, 3.2.8.0 - 3.2.10.0 | 36 |  |  | 36 | [6 empty] | PP-1262 |  | Sprint 9 |  | LDS suppression rule-11 | MVP | 0
3.2.15.2 | LDS rule-11 in screen floating message |  | 3.1.15.2 | 4 |  |  | 4 | [6 empty] | PP-1263 |  | Sprint 9 |  | LDS suppression rule-11 | MVP | 0
3.2.16 | Save or export Visualization | automate tests from the tab | 3.1.16 | [10 empty] | PP-681 |  | Sprint 9 |  | Save or export Visualization | MVP | 0
3.2.16.1 | Export as PNG |  | 3.1.16.1, 3.2.19.1 | 16 |  |  | 8 | Kamil | Jun 21, 2021 13:44:12 | Jun 22, 2021 11:09:11 | 7 |  |  | PP-1264 |  |  |  | Save or export Visualization | MVP | 8
3.2.16.2 | Export the View as Excel |  | 3.1.16.2, 3.2.19.1 | 16 |  |  | 22 | [6 empty] | PP-1265 |  | Sprint 9 |  | Save or export Visualization | MVP | 0
3.2.17 | System | automate tests from the tab | 3.1.17 | [10 empty] | PP-682 |  | Sprint 9 |  | System | MVP | 0
3.2.17.1 | View user manual |  | 3.1.17.2 | 1 |  |  | 1 | [6 empty] | PP-1266 |  | Sprint 9 |  | System | MVP | 0
3.2.17.2 | Customer support contact information icons |  | 3.1.17.3 | 1 |  |  | 2 | [6 empty] | PP-1267 |  | Sprint 9 |  | System | MVP | 0
3.2.17.3 | Versioning and copyright maintenance |  | 3.1.17.4 | 1 |  |  | 2 | [6 empty] | PP-1268 |  | Sprint 9 |  | System | MVP | 0
3.2.18 | Show Details | automate tests from the tab | 3.1.18 | [10 empty] | PP-1269 |  | Sprint 9 |  |  | MVP | 0
3.2.18.0 | Implement ShowDetailsPage and methods |  |  | 6 |  |  | 6 | Monika | May 31, 2021 06:31:01 | Jun 01, 2021 12:26:33 | 8 |  |  | PP-1398 |  | Sprint 8 |  | Visualization Generation | MVP | 6
3.2.18.1 | Contex menu - Graph View |  | 3.1.18.1, 3.2.8.0 | 4 |  |  | 4 | Swatantra | [5 empty] | PP-1270 |  | Sprint 9 |  | Visualization Generation | MVP | 0
3.2.18.2 | Context menu - 2D Graph View |  | 3.1.18.2, 3.2.9.0 | 2 |  |  | 2 | [6 empty] | PP-1271 |  | Sprint 9 |  | Visualization Generation | MVP | 0
3.2.18.3 | Context menu - Map view |  | 3.1.18.3, 3.2.10.0 | 2 |  |  | 2 | [6 empty] | PP-1272 |  | Sprint 9 |  | Visualization Generation | MVP | 0
3.2.18.4 | Show details panel |  | 3.1.18.4, 3.2.18.0 | 8 |  |  | 8 | [6 empty] | PP-1273 |  | Sprint 9 |  | Visualization Generation | MVP | 0
3.2.19 | Others | [12 empty] | PP-1399 |  |  |  |  | MVP | 0
3.2.19.1 | Cleanup and finish of base filter page |  |  | 16 |  |  | 16 | Kamil | May 12, 2021 13:33:01 | May 17, 2021 13:24:41 | 15.5 |  |  | PP-1360 |  | Sprint 6 |  |  | MVP | 16
3.2.19.2 | Implement LegendPage and methods |  |  | 4 |  |  | 4 | Paulina | May 25, 2021 10:38:29 | May 26, 2021 06:05:50 | 4 |  |  | PP-1400 |  | Sprint 7 |  |  | MVP | 4
3.2.19.3 | Implement BenchmarkSettingsBasePage |  |  | 12 |  |  | 12 | Paulina | May 24, 2021 06:04:07 | May 25, 2021 10:06:14 | 8.5 |  |  | PP-1401 |  | Sprint 7 |  |  | MVP | 12
3.2.19.4 | Implement OrderSettings Page and methods |  |  | 8 |  |  | 5 | Paulina | May 24, 2021, 10:26 AM | May 25, 2021, 12:14 PM | 3 |  |  | PP-1422 |  | Sprint 7 |  |  | MVP | 5
4 | Unit tests analysis and implementation | [12 empty] | PP-683 |  | Sprint 9 |  |  | MVP | 0
4.1 | group_nodes method |  | BE: 1.1.12 |  |  | 40 | 40 | Monika | March 30, 2021, 3:03 PM | April 15, 2021, 8:29 AM | 24 | 874 | 28 | PP-574 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/140 | Sprint 4 | Started in Sprint 3 |  | MVP | 40
4.2 | calculate_benchmark method |  | BE: 1.11.7 |  |  | 40 | 20 | Monika | [5 empty] | PP-684 |  | Sprint 9 |  |  | MVP | 0
4.3 | single packed node on each side in calculate_benchmark method |  | BE: 1.14.11 |  |  | 40 | 10 | Monika | [5 empty] | PP-685 |  | Sprint 9 |  |  | MVP | 0
5 | Performance tests | [12 empty] | PP-688 |  | Sprint 9 |  |  | MVP | 0
5.1 | Backend | [12 empty] | PP-689 |  | Sprint 9 |  |  | MVP | 0
5.1.1 | Implement benchmark fixture | see design |  | 6 | 8 |  | 8 | Piotr | Jun 08, 2021 07:15:00 | Jun 16, 2021 11:29:21 | 7.5 |  |  | PP-1274 |  | Sprint 9 |  |  | MVP | 8
5.1.2 | Implement measuring method | see design |  | 8 | 8 |  | 8 | Piotr | [5 empty] | PP-1275 |  | Sprint 9 |  |  | MVP | 0
5.1.3 | Change existing tests to use measuring method, mark those tests with pytest | see design |  | 16 | 16 |  | 24 | Piotr | Jun 16, 2021 06:25:36 | Jun 21, 2021 09:12:45 | 12.5 |  |  | PP-1276 |  | Sprint 9 |  |  | MVP | 24
5.2 | Front End | [12 empty] | PP-690 |  | Sprint 9 |  |  | MVP | 0
5.2.1 | Implement measuring class | see design |  | 4 | 6 |  | 6 | [6 empty] | PP-1277 |  | Sprint 9 |  |  | MVP | 0
5.2.2 | Implement benchmark fixture | see design |  | 6 | 6 |  | 6 | [6 empty] | PP-1278 |  | Sprint 9 |  |  | MVP | 0
5.2.3 | Implement test measuring decorator | see design |  | 4 | 6 |  | 6 | [6 empty] | PP-1279 |  | Sprint 9 |  |  | MVP | 0
5.2.4 | Implement utils methods | see design |  | 4 | 6 |  | 6 | [6 empty] | PP-1280 |  | Sprint 9 |  |  | MVP | 0
5.2.5 | Implement performance test cases | see design | 3.2.4 - 3.2.10 | 16 | 24 |  | 24 | [6 empty] | PP-1281 |  | Sprint 10 |  |  | MVP | 0
6 | Automation of generating tests result | [12 empty] | PP-691 |  | Sprint 10 |  |  | MVP | 0
6.1 | Set up repository | Set up new project on gitlab |  | 4 | 4 |  | 4 |  | April 7, 2021, 10:01 AM | April 7, 2021, 10:50 AM | 3.5 |  |  | PP-692 | https://gitlab-01.itx.pl/p2-project/tests/p2-automated-tests-calculations | Sprint 4 |  |  | MVP | 4
6.2 | Implementing of merger dataset | Implementing class to merge datasets used in p2 |  | 8 | 8 |  | 8 |  | April 7, 2021, 11:21 AM | April 8, 2021, 9:03 AM | 7.67 |  |  | PP-693 |  | Sprint 4 |  |  | MVP | 8
6.3 | Implementing of auxiliary functions | Implementing of auxiliary functions for calculation |  | 8 | 8 |  | 8 |  | April 8, 2021, 10:40 AM | April 9, 2021, 8:48 AM | 6 |  |  | PP-694 | https://gitlab-01.itx.pl/p2-project/tests/p2-automated-tests-calculations/-/merge_requests/3 | Sprint 4 |  |  | MVP | 8
6.4 | Implementing of methods to generate json | Implementing of methods to generate json |  | 8 | 8 |  | 8 |  | April 9, 2021, 10:05 AM | April 12, 2021, 10:19 AM | 7 |  |  | PP-695 | https://gitlab-01.itx.pl/p2-project/tests/p2-automated-tests-calculations/-/merge_requests/4 | Sprint 4 |  |  | MVP | 8
6.5 | Implementing fixture to read expected results from json | Implementing fixture to read expected results from json in the FE tests |  | 8 |  |  | 8 | [6 empty] | PP-700 |  | Sprint 10 | Removed from sprint 4 - FE dependency |  | MVP | 0
6.6 | Implementing integration tests, which check calculation |  |  | 12 |  |  | 12 |  | April 12, 2021, 2:19 PM | April 13, 2021, 9:01 AM | 6 |  |  | PP-1001 | https://gitlab-01.itx.pl/p2-project/tests/p2-backend-tests/-/merge_requests/10/ | Sprint 4 | Added to sprint in Sprint 4 |  | MVP | 12
7 | research on reporting of skipped tests in regression suits and keeping a track of them | [12 empty] | PP-934 |  | Sprint 5 |  |  | MVP | 0
8 | Frontend test suite features | [12 empty] | PP-1639 |  |  |  |  | MVP | 0
8.1 | Write Readme | Write a Readme file with the instructions on how to: - Install and prepare the testing environment - Run the tests - Write new tests and page objects |  | 3 |  |  | 3 | Kamil | June 8, 2021, 3:35 PM | June 8, 2021, 3:36 PM | 2.5 |  |  | PP-1566 |  |  |  |  | MVP | 3
8.2 | Implement sending test reports by email |  |  | 10 |  |  | 10 | Kamil | Jun 14, 2021 07:30:25 | Jun 21, 2021 10:37:20 | 5 |  |  | PP-1567 |  |  |  |  | MVP | 10
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on E70: @awaz@ownedoutcomes.com Hi Artur, a clarification on planning: Was the 297h planned tasks for meant for the whole team including design (5 members with capacity 72h + 296h) or only for the development (4 members)? Where can we find the 72h tasks? @krupa@ownedoutcomes.com _Assigned to Artur Waz_ -Joslyn Huang Re: 297h planned tasks vs 368h QA capacity @krupa@ownedoutcomes.com -Joslyn Huang @joslyn@ownedoutcomes.com to clarify, we do not have all 5 people avaiable for tests implementation, as I mentioned on the email, 72h will be spent on planning. Designs (Kamil J, Piotr): Capacity: 72h Development (Monika, Paulina, Piotr, Swatantra): Capacity: 296h Planned tasks: 397h -Artur Waz @awaz@ownedoutcomes.com according to the sheet and what we agreed to the statistics, it's: Designs (Kamil J, Piotr): Capacity: 72h Development (Monika, Paulina, Piotr, Swatantra): Capacity: 296h Planned tasks: 297h I think the only descrepancy is we don't see the 72h being on the planned tasks. -Joslyn Huang
Note on B286: Reuse from 2D graph benchmark tests -Kamil Jabłoński
Note on B288: Reuse from 2D graph benchmark tests -Kamil Jabłoński
Note on B289: Reuse from 2D graph benchmark tests -Kamil Jabłoński
Note on B291: Reuse from 2D graph benchmark tests -Kamil Jabłoński
Note on B292: Reuse from 2D graph benchmark tests -Kamil Jabłoński
Note on B294: Reuse from 2D benchmark graph tests -Kamil Jabłoński
Note on B297: Estimations shorted because we assume that those tasks will be completed after 3.2.11 is done -Kamil Jabłoński

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions

## Planned availability
Date | People | Hrs | Cummulative |  | People | Hrs | Cummulative |  | People | Hrs | Cummulative
2021-04-12 | 4 | 30 | 30 | Sprint 4 | 4 | 26 | 26 | Sprint 4 | 4 | 26 | 26 | 0
2021-04-13 | 4 | 30 | 60 |  | 4 | 26 | 52 |  | 4 | 26 | 52 | 0
2021-04-14 | 4 | 30 | 90 |  | 4 | 26 | 78 |  | 4 | 26 | 78 | 0
2021-04-15 | 4 | 30 | 120 |  | 4 | 26 | 104 |  | 4 | 26 | 104 | 0
2021-04-16 | 4 | 30 | 150 |  | 4 | 26 | 130 |  | 4 | 26 | 130 | 0
2021-04-17 | 0 | 0 | 150 |  | 0 | 0 | 130 |  | 0 | 0 | 130 | 0
2021-04-18 | 0 | 0 | 150 |  | 0 | 0 | 130 |  | 0 | 0 | 130 | 0
2021-04-19 | 5 | 37.5 | 187.5 | sprint 5 | 5 | 32.5 | 162.5 | sprint 5 | 5 | 32.5 | 162.5 | 0
2021-04-20 | 5 | 37.5 | 225 |  | 5 | 32.5 | 195 |  | 5 | 32.5 | 195 | 0
2021-04-21 | 5 | 37.5 | 262.5 |  | 5 | 32.5 | 227.5 |  | 5 | 32.5 | 227.5 | 0
2021-04-22 | 5 | 37.5 | 300 |  | 5 | 32.5 | 260 |  | 5 | 32.5 | 260 | 0
2021-04-23 | 5 | 37.5 | 337.5 |  | 5 | 32.5 | 292.5 |  | 5 | 32.5 | 292.5 | 0
2021-04-24 | 0 | 0 | 337.5 |  | 0 | 0 | 292.5 |  | 0 | 0 | 292.5 | 0
2021-04-25 | 0 | 0 | 337.5 |  | 0 | 0 | 292.5 |  | 0 | 0 | 292.5 | 0
2021-04-26 | 5 | 37.5 | 375 |  | 5 | 32.5 | 325 |  | 5 | 32.5 | 325 | 0
2021-04-27 | 5 | 37.5 | 412.5 |  | 5 | 32.5 | 357.5 |  | 5 | 32.5 | 357.5 | 0
2021-04-28 | 5 | 37.5 | 450 |  | 5 | 32.5 | 390 |  | 5 | 32.5 | 390 | 0
2021-04-29 | 5 | 37.5 | 487.5 |  | 5 | 32.5 | 422.5 |  | 5 | 32.5 | 422.5 | 0
2021-04-30 | 5 | 37.5 | 525 |  | 5 | 32.5 | 455 |  | 5 | 32.5 | 455 | 0
2021-05-01 | 0 | 0 | 525 |  | 0 | 0 | 455 |  | 0 | 0 | 455 | 0
2021-05-02 | 0 | 0 | 525 |  | 0 | 0 | 455 |  | 0 | 0 | 455 | 0
2021-05-03 | 0 | 0 | 525 | sprint 6 | 0 | 0 | 455 | sprint 6 | 0 | 0 | 455 | 0
2021-05-04 | 5 | 37.5 | 562.5 |  | 5 | 32.5 | 487.5 |  | 5 | 32.5 | 487.5 | 0
2021-05-05 | 5 | 37.5 | 600 |  | 5 | 32.5 | 520 |  | 5 | 32.5 | 520 | 0
2021-05-06 | 5 | 37.5 | 637.5 |  | 5 | 32.5 | 552.5 |  | 5 | 32.5 | 552.5 | 0
2021-05-07 | 5 | 37.5 | 675 |  | 5 | 32.5 | 585 |  | 5 | 32.5 | 585 | 0
2021-05-08 | 0 | 0 | 675 |  | 0 | 0 | 585 |  | 0 | 0 | 585 | 0
2021-05-09 | 0 | 0 | 675 |  | 0 | 0 | 585 |  | 0 | 0 | 585 | 0
2021-05-10 | 5 | 37.5 | 712.5 |  | 5 | 32.5 | 617.5 |  | 5 | 32.5 | 617.5 | 0
2021-05-11 | 5 | 37.5 | 750 |  | 5 | 32.5 | 650 |  | 5 | 32.5 | 650 | 0
2021-05-12 | 5 | 37.5 | 787.5 |  | 5 | 32.5 | 682.5 |  | 5 | 32.5 | 682.5 | 0
2021-05-13 | 5 | 37.5 | 825 |  | 5 | 32.5 | 715 |  | 5 | 32.5 | 715 | 0
2021-05-14 | 5 | 37.5 | 862.5 |  | 5 | 32.5 | 747.5 |  | 5 | 32.5 | 747.5 | 0
2021-05-15 | 0 | 0 | 862.5 |  | 0 | 0 | 747.5 |  | 0 | 0 | 747.5 | 0
2021-05-16 | 0 | 0 | 862.5 |  | 0 | 0 | 747.5 |  | 0 | 0 | 747.5 | 0
2021-05-17 | 3 | 22.5 | 885 | sprint 7 | 5 | 32.5 | 780 | sprint 7 | 6 | 39 | 786.5 | 0
2021-05-18 | 3 | 22.5 | 907.5 |  | 5 | 32.5 | 812.5 |  | 6 | 39 | 825.5 | 0
2021-05-19 | 3 | 22.5 | 930 |  | 5 | 32.5 | 845 |  | 6 | 39 | 864.5 | 0
2021-05-20 | 3 | 22.5 | 952.5 |  | 5 | 32.5 | 877.5 |  | 5 | 32.5 | 897 | 0
2021-05-21 | 3 | 22.5 | 975 |  | 5 | 32.5 | 910 |  | 5 | 32.5 | 929.5 | 0
2021-05-22 | 0 | 0 | 975 |  | 0 | 0 | 910 |  | 0 | 0 | 929.5 | 0
2021-05-23 | 0 | 0 | 975 |  | 0 | 0 | 910 |  | 0 | 0 | 929.5 | 0
2021-05-24 | 3 | 22.5 | 997.5 |  | 5 | 32.5 | 942.5 |  | 5 | 32.5 | 962 | 0
2021-05-25 | 3 | 22.5 | 1020 |  | 5 | 32.5 | 975 |  | 5 | 32.5 | 994.5 | 0
2021-05-26 | 3 | 22.5 | 1042.5 |  | 5 | 32.5 | 1007.5 |  | 5 | 32.5 | 1027 | 0
2021-05-27 | 3 | 22.5 | 1065 |  | 5 | 32.5 | 1040 | Minimal plan finish date | 5 | 32.5 | 1059.5 | 0
2021-05-28 | 0 | 0 | 1065 |  | 5 | 32.5 | 1072.5 |  | 5 | 32.5 | 1092 | 0
2021-05-29 | 0 | 0 | 1065 |  | 0 | 0 | 1072.5 |  | 0 | 0 | 1092 | 0
2021-05-30 | 3 | 22.5 | 1087.5 |  | 0 | 0 | 1072.5 |  | 0 | 0 | 1092
2021-05-31 | 3 | 22.5 | 1110 |  | 5 | 32.5 | 1105 |  | 4 | 26 | 1118 |  | Minimal plan finish date
2021-06-01 | 3 | 22.5 | 1132.5 |  | 5 | 32.5 | 1137.5 |  | 4 | 26 | 1144
2021-06-02 | 3 | 22.5 | 1155 |  | 5 | 32.5 | 1170 | Faster plan finish date | 4 | 26 | 1170
2021-06-03 | 3 | 22.5 | 1177.5 |  | 5 | 32.5 | 1202.5 |  | 4 | 26 | 1196
2021-06-04 | 0 | 0 | 1177.5 |  | 5 | 32.5 | 1235 |  | 4 | 26 | 1222
2021-06-05 | 0 | 0 | 1177.5 |  | 0 | 0 | 1235 |  | 0 | 0 | 1222
2021-06-06 | 3 | 22.5 | 1200 | Minimal plan finish date | 0 | 0 | 1235 |  | 0 | 0 | 1222
2021-06-07 | 3 | 22.5 | 1222.5 |  | 5 | 32.5 | 1267.5 |  | 4 | 26 | 1248
2021-06-08 | 3 | 22.5 | 1245 |  | 5 | 32.5 | 1300 |  | 4 | 26 | 1274 |  | Faster plan finish date
2021-06-09 | 3 | 22.5 | 1267.5 |  | 5 | 32.5 | 1332.5 |  | 4 | 26 | 1300
2021-06-10 | 3 | 22.5 | 1290 |  | 5 | 32.5 | 1365 |  | 4 | 26 | 1326
2021-06-11 | 0 | 0 | 1290 |  | 5 | 32.5 | 1397.5 |  | 4 | 26 | 1352
2021-06-12 | 0 | 0 | 1290 |  | 0 | 0 | 1397.5 |  | 0 | 0 | 1352
2021-06-13 | 3 | 22.5 | 1312.5 |  | 0 | 0 | 1397.5 |  | 0 | 0 | 1352
2021-06-14 | 3 | 22.5 | 1335 |  | 5 | 32.5 | 1430 |  | 4 | 26 | 1378
2021-06-15 | 3 | 22.5 | 1357.5 | Faster plan finish date | 5 | 32.5 | 1462.5 |  | 4 | 26 | 1404
2021-06-16 | 3 | 22.5 | 1380 |  | 5 | 32.5 | 1495 |  | 4 | 26 | 1430
2021-06-17 | 3 | 22.5 | 1402.5 |  | 5 | 32.5 | 1527.5 |  | 4 | 26 | 1456
2021-06-18 | 0 | 0 | 1402.5 |  | 5 | 32.5 | 1560 |  | 4 | 26 | 1482
2021-06-19 | 0 | 0 | 1402.5 |  | 0 | 0 | 1560 |  | 0 | 0 | 1482
2021-06-20 | 3 | 22.5 | 1425 |  | 0 | 0 | 1560 | Current plan finish date | 0 | 0 | 1482
2021-06-21 | 3 | 22.5 | 1447.5 |  | 5 | 32.5 | 1592.5 |  | 4 | 26 | 1508
2021-06-22 | 3 | 22.5 | 1470 |  | 5 | 32.5 | 1625 |  | 4 | 26 | 1534
2021-06-23 | 3 | 22.5 | 1492.5 |  | 5 | 32.5 | 1657.5 |  | 4 | 26 | 1560
2021-06-24 | 3 | 22.5 | 1515 |  | 5 | 32.5 | 1690 |  | 4 | 26 | 1586
2021-06-25 | 0 | 0 | 1515 |  | 5 | 32.5 | 1722.5 |  | 4 | 26 | 1612
2021-06-26 | 0 | 0 | 1515 |  | 0 | 0 | 1722.5 |  | 0 | 0 | 1612
2021-06-27 | 3 | 22.5 | 1537.5 |  | 0 | 0 | 1722.5 |  | 0 | 0 | 1612
2021-06-28 | 3 | 22.5 | 1560 |  | 5 | 32.5 | 1755 |  | 4 | 26 | 1638
2021-06-29 | 3 | 22.5 | 1582.5 |  | 5 | 32.5 | 1787.5 |  | 4 | 26 | 1664
2021-06-30 | 3 | 22.5 | 1605 |  | 5 | 32.5 | 1820 |  | 4 | 26 | 1690
2021-07-01 | 3 | 22.5 | 1627.5 |  | 5 | 32.5 | 1852.5 |  | 4 | 26 | 1716
2021-07-02 | 0 | 0 | 1627.5 |  | 5 | 32.5 | 1885 |  | 4 | 26 | 1742
2021-07-03 | 0 | 0 | 1627.5 |  | 0 | 0 | 1885 |  | 0 | 0 | 1742
2021-07-04 | 3 | 22.5 | 1650 |  | 0 | 0 | 1885 |  | 0 | 0 | 1742 |  | Current plan finish date
2021-07-05 | 3 | 22.5 | 1672.5 |  | 5 | 32.5 | 1917.5 |  | 4 | 26 | 1768
2021-07-06 | 3 | 22.5 | 1695 |  | 5 | 32.5 | 1950 |  | 4 | 26 | 1794
2021-07-07 | 3 | 22.5 | 1717.5 |  | 5 | 32.5 | 1982.5 |  | 4 | 26 | 1820
2021-07-08 | 3 | 22.5 | 1740 |  | 5 | 32.5 | 2015 |  | 4 | 26 | 1846
2021-07-09 | 0 | 0 | 1740 |  | 5 | 32.5 | 2047.5 |  | 4 | 26 | 1872
2021-07-10 | 0 | 0 | 1740 |  | 0 | 0 | 2047.5 |  | 0 | 0 | 1872
2021-07-11 | 3 | 22.5 | 1762.5 |  | 0 | 0 | 2047.5 |  | 0 | 0 | 1872
2021-07-12 | 3 | 22.5 | 1785 |  | 5 | 32.5 | 2080 |  | 4 | 26 | 1898
2021-07-13 | 3 | 22.5 | 1807.5 |  | 5 | 32.5 | 2112.5 |  | 4 | 26 | 1924
2021-07-14 | 3 | 22.5 | 1830 | Current plan finish date | 5 | 32.5 | 2145 |  | 4 | 26 | 1950
2021-07-15 | 3 | 22.5 | 1852.5 |  | 5 | 32.5 | 2177.5 |  | 4 | 26 | 1976
2021-07-16 | 0 | 0 | 1852.5 |  | 5 | 32.5 | 2210 |  | 4 | 26 | 2002
2021-07-17 | 0 | 0 | 1852.5 |  | 0 | 0 | 2210 |  | 0 | 0 | 2002
2021-07-18 | 3 | 22.5 | 1875 |  | 0 | 0 | 2210 |  | 0 | 0 | 2002
2021-07-19 | 3 | 22.5 | 1897.5 |  | 5 | 32.5 | 2242.5 |  | 4 | 26 | 2028
2021-07-20 | 3 | 22.5 | 1920 |  | 5 | 32.5 | 2275 |  | 4 | 26 | 2054
2021-07-21 | 3 | 22.5 | 1942.5 |  | 5 | 32.5 | 2307.5 |  | 4 | 26 | 2080
2021-07-22 | 3 | 22.5 | 1965 |  | 5 | 32.5 | 2340 |  | 4 | 26 | 2106
2021-07-23 | 0 | 0 | 1965 |  | 5 | 32.5 | 2372.5 |  | 4 | 26 | 2132
2021-07-24 | 0 | 0 | 1965 |  | 0 | 0 | 2372.5 |  | 0 | 0 | 2132
2021-07-25 | 3 | 22.5 | 1987.5 |  | 0 | 0 | 2372.5 |  | 0 | 0 | 2132
2021-07-26 | 3 | 22.5 | 2010 |  | 5 | 32.5 | 2405 |  | 4 | 26 | 2158
2021-07-27 | 3 | 22.5 | 2032.5 |  | 5 | 32.5 | 2437.5 |  | 4 | 26 | 2184
2021-07-28 | 3 | 22.5 | 2055 |  | 5 | 32.5 | 2470 |  | 4 | 26 | 2210
2021-07-29 | 3 | 22.5 | 2077.5 |  | 5 | 32.5 | 2502.5 |  | 4 | 26 | 2236
2021-07-30 | 0 | 0 | 2077.5 |  | 5 | 32.5 | 2535 |  | 4 | 26 | 2262
2021-07-31 | 0 | 0 | 2077.5 |  | 0 | 0 | 2535 |  | 0 | 0 | 2262
2021-08-01 | 3 | 22.5 | 2100 |  | 0 | 0 | 2535 |  | 0 | 0 | 2262
2021-08-02 | 3 | 22.5 | 2122.5 |  | 5 | 32.5 | 2567.5 |  | 4 | 26 | 2288
2021-08-03 | 3 | 22.5 | 2145 |  | 5 | 32.5 | 2600 |  | 4 | 26 | 2314
2021-08-04 | 3 | 22.5 | 2167.5 |  | 5 | 32.5 | 2632.5 |  | 4 | 26 | 2340
2021-08-05 | 3 | 22.5 | 2190 |  | 5 | 32.5 | 2665 |  | 4 | 26 | 2366
2021-08-06 | 0 | 0 | 2190 |  | 5 | 32.5 | 2697.5 |  | 4 | 26 | 2392
2021-08-07 | 0 | 0 | 2190 |  | 0 | 0 | 2697.5 |  | 0 | 0 | 2392
2021-08-08 | 3 | 22.5 | 2212.5 |  | 0 | 0 | 2697.5 |  | 0 | 0 | 2392
2021-08-09 | 3 | 22.5 | 2235 |  | 5 | 32.5 | 2730 |  | 4 | 26 | 2418
2021-08-10 | 3 | 22.5 | 2257.5 |  | 5 | 32.5 | 2762.5 |  | 4 | 26 | 2444
2021-08-11 | 3 | 22.5 | 2280 |  | 5 | 32.5 | 2795 |  | 4 | 26 | 2470
2021-08-12 | 3 | 22.5 | 2302.5 |  | 5 | 32.5 | 2827.5 |  | 4 | 26 | 2496
2021-08-13 | 0 | 0 | 2302.5 |  | 5 | 32.5 | 2860 |  | 4 | 26 | 2522
2021-08-14 | 0 | 0 | 2302.5 |  | 0 | 0 | 2860 |  | 0 | 0 | 2522
2021-08-15 | 3 | 22.5 | 2325 |  | 0 | 0 | 2860 |  | 0 | 0 | 2522
2021-08-16 | 3 | 22.5 | 2347.5 |  | 5 | 32.5 | 2892.5 |  | 4 | 26 | 2548
2021-08-17 | 3 | 22.5 | 2370 |  | 5 | 32.5 | 2925 |  | 4 | 26 | 2574
2021-08-18 | 3 | 22.5 | 2392.5 |  | 5 | 32.5 | 2957.5 |  | 4 | 26 | 2600
2021-08-19 | 3 | 22.5 | 2415 |  | 5 | 32.5 | 2990 |  | 4 | 26 | 2626
2021-08-20 | 0 | 0 | 2415 |  | 5 | 32.5 | 3022.5 |  | 4 | 26 | 2652
2021-08-21 | 0 | 0 | 2415 |  | 0 | 0 | 3022.5 |  | 0 | 0 | 2652
2021-08-22 | 3 | 22.5 | 2437.5 |  | 0 | 0 | 3022.5 |  | 0 | 0 | 2652
2021-08-23 | 3 | 22.5 | 2460 |  | 5 | 32.5 | 3055 |  | 4 | 26 | 2678
2021-08-24 | 3 | 22.5 | 2482.5 |  | 5 | 32.5 | 3087.5 |  | 4 | 26 | 2704
2021-08-25 | 3 | 22.5 | 2505 |  | 5 | 32.5 | 3120 |  | 4 | 26 | 2730
2021-08-26 | 3 | 22.5 | 2527.5 |  | 5 | 32.5 | 3152.5 |  | 4 | 26 | 2756
2021-08-27 | 0 | 0 | 2527.5 |  | 5 | 32.5 | 3185 |  | 4 | 26 | 2782
2021-08-28 | 0 | 0 | 2527.5 |  | 0 | 0 | 3185 |  | 0 | 0 | 2782
|  | 0 |  |  |  | 0 | 3185 |  | 0 | 0 | 2782
|  | 0 |  |  |  | 0 | 3185 |  | 0 | 0 | 2782
|  | 0 |  |  |  | 0 |  |  |  |  | 2782
|  | 0 |  |  |  | 0 |  |  |  |  | 2782
|  | 0 | [8 empty] | 2782
|  | 0 | [8 empty] | 2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782
2782

## Estimations vs actual time spen
|  | Total time planned for category | Time esimated for closed tasks | Section completion based on estimations | Actual time spent on closed tasks | Estimation/Real time diference | Estimated time for remaining tasks | Estimations change if adjusted to the current time difference
2 | Integration tests | 433 | 310 | 71.59% | 272.5 | -12.1% | 123 | -14.879
3.1 | Changes in regression library | 602 | 150 | 24.92% | 188.5 | 25.67% | 452 | 116.0133
3.2 | Automating regression library test cases | 824 | 120 | 14.56% | 186 | 55% | 704 | 387.2 | Possible time gain due to adding dependencies tasks [h] | 60
4 | Unit tests | 70 | 40 | 57.14% | 23 | -42.5% | 30 | N/A
5 | Performance tests | 80 | 0 | 0% | 0 | N/A | 80 | N/A
6 | Automation of generated tests results | 48 | 40 | 83.33% | 30 | -25% | 8 | -2
| Totals | 2057 | 660 | 32.09% | 700 | 6.061% | 1397 | 486.3343
|  | Time esimated for closed tasks | Actual time spent on closed tasks | Estimation/Real time diference
| Kamil | 16 | 15.5 | -3.125%
| Piotr | 229 | 184 | -19.65%
| Monika | 102 | 115 | 12.75%
| Paulina | 226 | 199 | -11.95%
| Swatantra | 66 | 131 | 98.48%
| Bartek | 18 | 53 | 194.4% | <-- Bartek has left the company. No further conversations necessary
Note on I3: @kjablonski@ownedoutcomes.com this is also far ahead of schedule. Is it because we were super conservative in estimation? _Assigned to Kamil Jabłoński_ -Krupa Srinivas @krupa@ownedoutcomes.com actually this is the time begind the schedule, we would have to add 116h to final estimation based on currently finished tasks. -Artur Waz ah ok, thank you for clarifying. -Krupa Srinivas
Note on J4: @kjablonski@ownedoutcomes.com what does this mean? _Assigned to Kamil Jabłoński_ -Krupa Srinivas We can expect to finish the remaining tasks for automation category earlier by this amount of time. It is related to the dependencies tasks that we've created. I've left this information here as a note because we haven't decided to change the estmations in the tasks sheet yet. -Kamil Jabłoński
Note on M4: Time would be gained mostly on Benchmark tasks, Service Line Filter and Map/Graph/2D views automation. -Kamil Jabłoński
Note on I5: Estimations already adjusted -Kamil Jabłoński
Note on I6: No tasks completed as of yet -Kamil Jabłoński
Note on C8: 24 hour less caused by one task that had estimated time but shouldn't have -Kamil Jabłoński
Note on B12: @kjablonski@ownedoutcomes.com - can you add week to week updates here? _Assigned to Kamil Jabłoński_ -Krupa Srinivas
Note on E15: How can we help Monika gain some more speed? @kjablonski@ownedoutcomes.com _Assigned to Kamil Jabłoński_ -Krupa Srinivas Monika's getting consistently better. She was unfamilliar with the types of tasks we're doing in P2 (manual test cases and selenium) at first so I think that might be the main source of the visible delays. -Kamil Jabłoński
Note on E17: @kjablonski@ownedoutcomes.com how can we improve? Why is this team member taking so long when others are faster? What are we doing to help them get better? _Assigned to Kamil Jabłoński_ -Krupa Srinivas Right now we're letting Swatantra spend some more time on particular types of tasks so that he can more familliar with them and the way we need them to be completed. In the beggining he was often moved between different tasks categories he wasn't too familliar with. -Kamil Jabłoński

## Sheet4
| current plan | faster plan | minimal plan
estimated hours | 1418 | 1000 | 804
description | That's the original approach: - First the regression library is reworked and imrpoved according to the propositions from this document - Then, the regression library is automated in our new selenium suite based on pytest | Original approach with trade-offs: - We still do some rework on the regression library (e.g. consitent naming convention, mapping functionalities to the feature pruning document) but don't spend much time analiyzing whether a given functionality is covered well enough and adding tests to it. - We'll proceed with test automation similar to the first approach | Minimal approach - Abandon current regression library document (stop updating it) - Automate already existing tests with only the necessary updates and modifications (e.g. changes in labels tests, consistent naming convention, mapping functionalities to the pruning document), create extensive documentation of the automated test to generate reports similar to the ones already existing for the integration tests library link
pros | - All test scenarios would be mapped to p2 feature pruninng functionalities - The library structure would be more clean and related to p2 feature pruning document - We'll make that all functionalities from the pruning document are covered well | - Less time consuming approach, we could get the automated test suite up-and-running sooner - Test scenarios from the regression library would be mapped to the feature pruning document and we'll keep more detailed stats about the entire suite | - Faster to finish since we won't spend time working on the regression library document - Easy to maintain mapping between the library and automated tests since everyting would be stored in one place
cons | Reworking the regression library according to the the document will take aroun 600 hours to finish | - Quality of the existing regression test scenarios would only be slightly improved | - Quality of the existing regression test scenarios would be only slightly improved - Reports generated from the selenium tests suite are somewhat less formatted than those created in the google sheets by hand - In order to make changes in test cases documentation one would need to change it from the selenium tests repository
| Tab/category | Regression library rework | Automation | Total
Authentication & Authorization
| Authentication Module | 4 | 6 | 10
| Multi-tenancy | 4 | 4 | 8
| Password requirements | 2 | 2 | 4
| Change password | 4 | 8 | 12
| Email Notifications & New email templates | 4 | 8 | 12
Dataset Upload & Management
| Dataset upload | 4 | 6 | 10
| Dataset permissions | 4 | 4 | 8
| View datasets details | 4 | 5 | 9
| Delete Dataset | 2 | 3 | 5
| Export datasets statistics details as Excel file | 4 | 6 | 10
| Statistics preview of a dataset by entity type | 2 | 3 | 5
View Dashboard
| View Creation | 6 | 6 | 12
| View Management (delete, search, etc) + search by dataset + save view/new view | 8 | 10 | 18
| View duplication | 2 | 2 | 4
| View name editing | 2 | 2 | 4
Location Filter
| Location filter by states & FIPS & CBSA [2nd and 3rd panel] | 10 | 16 | 26
| Location filter by Radius map [2nd and 3rd panel] | 10 | 16 | 26
| Location filter switch between grayscale and terrain | 2 | 2 | 4
| Location filter applies to | 8 | 8 | 16
| Tooltips for location filters | 2 | 4 | 6
| Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features e.g. scrolling/zooming map] | 4 | 8 | 12
| Pagination of the Entity, Service Lines,..Filters | 2 | 4 | 6
| Filter search | 4 | 4 | 8
| Clear filters feature | 2 | 2 | 4
| Filters breadcrumb (tree structures) | 6 | 8 | 14
| Filters breadcrumb navigation to the selected layer | 2 | 4 | 6
Entity Filter
| Entity-post acute type filter & Entity-Hospital filter [2nd and 3rd panel] | 8 | 16 | 24
| Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] | 4 | 8 | 12
| Pagination of the Entity, Service Lines,..Filters | 4 | 4 | 8
| Filter search | 4 | 4 | 8
| Tooltips when hovering over filters | 2 | 4 | 6
| Clear filters feature | 2 | 2 | 4
| Filters breadcrumb (tree structures) for Service Line and Entity filters | 6 | 6 | 12
| Filters breadcrumb navigation to the selected layer | 2 | 4 | 6
Service Line filter
| Service line filter [SL, Episode, DRG levels - 2nd and 3rd panel] | 10 | 16 | 26
| Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] | 2 | 8 | 10
| Pagination of the Entity, Service Lines,..Filters | 4 | 4 | 8
| Filter search | 4 | 4 | 8
| Tooltips when hovering over filters | 2 | 4 | 6
| Clear filters feature | 2 | 2 | 4
| Filters breadcrumb (tree structures) for Service Line and Entity filters | 6 | 6 | 12
| Filters breadcrumb navigation to the selected layer | 2 | 4 | 6
LOB Filter
| LOB filter [2nd and 3rd panel] | 4 | 8 | 12
| Filters- additional selector (Spiral charts/Visualization Selector) on third panel of filters [only third-panel specific features] | 2 | 4 | 6
| Filter search | 2 | 2 | 4
| Tooltips when hovering over filters | 2 | 2 | 4
| Clear filters feature | 2 | 2 | 4
Graph View
| Loading the default view/report | 1 | 2 | 3
| Market share Graph + filters [check calculations results here] | 20 | 20 | 40
| Benchmark Graph + filters [general cases, calculations checked in benchmark tab] | 16 | 16 | 32
| Multi-layer Graph view (all navigation types checked in here) | 10 | 16 | 26
| Graph view maximum number of nodes display | 6 | 6 | 12
| Highlight a node for re-calculation | 6 | 6 | 12
| Orders settings | 4 | 8 | 12
| Legend for Graph [general tests only, check calculations along with graph + filters category, dynamic legend with navigation/multi-layer graph] | 4 | 4 | 8
| Custom error messages related to filter choice | 4 | 4 | 8
| Exit the view and warning popups | 1 | 2 | 3
| Navigation menu (switching between view types, market share and benchmark modes) | 2 | 2 | 4
Map View
| Market share Map + filters [check calculations results here] | 20 | 20 | 40
| Benchmark view Map + filters [general cases, calculations checked in benchmark tab] | 16 | 16 | 32
| Map view navigation | 6 | 16 | 22
| Opacity slider for map | 2 | 4 | 6
| Legend for Map [general tests only, check calculations along with graph + filters category] + dynamic legend | 4 | 4 | 8
| Custom error messages related to filter choice | 4 | 4 | 8
| Exit the view and warning popups | 1 | 2 | 3
2D Graph View
| 2D graph view + filters [general cases, calculations checked in benchmark tab] | 16 | 20 | 36
| 2D Navigation | 8 | 16 | 24
| Legend for 2D [general tests only, check calculations along with graph + filters category] + dynamic legend | 4 | 4 | 8
| Custom error messages related to filter choice | 4 | 4 | 8
| Exit the view and warning popups | 1 | 2 | 3
Benchmark Settings and calculations on Graph
| Benchmarking default settings for Graph and benchmark calculation | 1 | 2 | 3
| Benchmarking Measures | 6 | 8 | 14
| Benchmark standard level of aggregations | 6 | 8 | 14
| Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) | 4 | 4 | 8
| Benchmark metrics by percentile & average | 4 | 6 | 10
| Benchmark time range | 6 | 8 | 14
| Benchmark to LOB settings | 4 | 4 | 8
| Search function on benchmark settings | 4 | 6 | 10
| Benchmark calculations (all filters + various benchmark settings) | 24 | 24 | 48
Benchmark Settings and calculations on Map
| Benchmarking default settings for Map and benchmark calculation | 1 | 2 | 3
| Benchmarking Measures | 6 | 8 | 14
| Benchmark standard level of aggregations | 6 | 8 | 14
| Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) | 4 | 4 | 8
| Benchmark metrics by percentile & average | 4 | 6 | 10
| Benchmark time range | 6 | 8 | 14
| Benchmark to LOB settings | 4 | 4 | 8
| Search function on benchmark settings | 4 | 6 | 10
| Benchmark calculations (all filters + various benchmark settings) | 24 | 24 | 48
Benchmark Settings and calculations on 2D
| Benchmarking default settings for 2D and benchmark calculation | 1 | 2 | 3
| Benchmarking Measures | 6 | 8 | 14
| Benchmark standard level of aggregations | 6 | 8 | 14
| Benchmark additional Level of aggregations (Regional, State, FIPS, CBSA) | 4 | 4 | 8
| Benchmark metrics by percentile & average | 4 | 6 | 10
| Benchmark time range | 6 | 8 | 14
| Benchmark to LOB settings | 4 | 4 | 8
| Search function on benchmark settings | 4 | 6 | 10
| Benchmark calculations (all filters + various benchmark settings) | 24 | 24 | 48
Label settings
| Labels on Graph | 12 | 16 | 28
| Labels on Map | 6 | 8 | 14
| Labels on 2D Graph | 6 | 8 | 14
LDS suppression rule-11 (after implementation add LDS test cases to check CC11 )
| LDS suppression rule-11 | 38 | 44 | 82
| LDS rule-11 in screen floating message | 2 | 4 | 6
Save or export Visualization
| Export as PNG | 4 | 16 | 20
| Export the View as Excel | 8 | 16 | 24
System
| Inactivity countdown timer | 2 | 1 | 3
| View user manual | 1 | 1 | 2
| Customer support contact information icons | 1 | 1 | 2
| Versioning and copyright maintenance | 1 | 0 | 1
Show Details
| Contex menu - Graph View | 2 | 4 | 6
| Context menu - 2D Graph View | 1 | 2 | 3
| Context menu - Map view | 1 | 2 | 3
| Show details panel | 8 | 8 | 16
| Summary | 614 | 804 | 1418