## Description
Design document: | Dataset Manager Technical Design
Jira project: | P2 next gen (PP)
Jira label: | Authorization
Number of tasks: | 36
Number of reported bugs: | 0
Total planned development worktime [h]: | 114
Planned development worktime of finished tasks [h]: | 114
Current worktime spent [h]: | 125.002
Planned time to finish project [h]: | 0
Project completeness based on planned worktime [%]: | 100
Current worktime vs planned worktime [%]: | 109.6509 | > 100% - delay; < 100% - ahead
Last update
Number of updated tasks (during last update)

## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  |  | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment | Category | Version
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions
0 | Project configuration | Create a project from a template and add library requirements |  | 1.5 | 1 | 1 | 1 | Kamil | March 17, 2021, 11:15 AM | March 17, 2021, 12:46 PM | 1.5 | 911 | 0 | PP-458 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/commit/ac08f1f7e84a69a59f3c81703ec52026c9ed2afb | Sprint 2 |  | Dataset upload and management | MVP | 1
1 | Describing abstract classes | Describe abstract classes and helper classes (like classes in model.py) | 0 | 1 |  | 1 | 1 | Kamil | March 22, 2021, 10:11 AM | March 22, 2021, 2:56 PM | 4.5 | 196 | 87 | PP-485 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/2 | Sprint 3 | postponed from Sprint 2; Problem with actual time estimation, because of not updated jira | Dataset upload and management | MVP | 1
2 | DatasetStorage mock implementation | Implement mock implementation of DatasetStorage for use in tests (documentation). | 0, 1 | 2 | 2 | 4 | 4 | Kamil | March 17, 2021, 2:00 PM | March 17, 2021, 4:00 PM | 2 | 211 | 2 | PP-311 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/1 | Sprint 3 | postponed from Sprint 2; Problem with actual time estimation, because of not updated jira | Dataset upload and management | MVP | 4
3 | Access mock implementation | Implement mock implementation of Access for use in tests (documentation). | 0, 1 | 4 | 4 | 4 | 4 | Kamil | March 17, 2021, 4:00 PM | March 22, 2021, 9:17 AM | 20 | 1422 | 22 | PP-312 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/3 | Sprint 3 | postponed from Sprint 2; Problem with actual time estimation, because of not updated jira | Dataset upload and management | MVP | 4
4 | DatasetManager implementation | implement the final version of the class according to the documentation (only class with methods without graphql) | 2, 3 | [10 empty] | PP-313 |  | Sprint 3 |  | Dataset upload and management | MVP | 0
4.1 | Implement get() | implement method according to the documentation |  | 5 | 6 | 8 | 8 | Kamil | March 23, 2021, 9:12 AM | March 24, 2021, 8:08 PM | 2.286 | 72 | 1.4286 | PP-314 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/4 | Sprint 3 |  | Dataset upload and management | MVP | 8
4.2 | Implement share() | implement method according to the documentation |  | 1.5 | 1.5 | 2 | 2 | Kamil | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM | 2.286 | 72 | 1.4286 | PP-315 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/4 | Sprint 3 |  | Dataset upload and management | MVP | 2
4.3 | Implement unshare() | implement method according to the documentation |  | 1.5 | 1.5 | 2 | 2 | Kamil | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM | 2.286 | 72 | 1.4286 | PP-316 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/4 | Sprint 3 |  | Dataset upload and management | MVP | 2
4.4 | Implement register() | implement method according to the documentation |  | 1.5 | 1.5 | 2 | 2 | Kamil | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM | 2.286 | 72 | 1.4286 | PP-317 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/4 | Sprint 3 |  | Dataset upload and management | MVP | 2
4.5 | Implement remove() | implement method according to the documentation |  | 1.5 | 1.5 | 2 | 2 | Kamil | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM | 2.286 | 72 | 1.4286 | PP-318 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/4 | Sprint 3 |  | Dataset upload and management | MVP | 2
4.6 | Implement add_user() | implement method according to the documentation |  | 1.5 | 1.5 | 2 | 2 | Kamil | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM | 2.286 | 72 | 1.4286 | PP-486 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/4 | Sprint 3 |  | Dataset upload and management | MVP | 2
4.7 | Implement add_parameter() | implement method according to the documentation |  | 1.5 | 1.5 | 2 | 2 | Kamil | March 23, 2021, 10:12 AM | March 24, 2021, 8:08 PM | 2.286 | 72 | 1.4286 | PP-487 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/4 | Sprint 3 |  | Dataset upload and management | MVP | 2
5 | GraphQL server implementation |  | 4 | [10 empty] | PP-319 |  | Sprint 3 |  | Dataset upload and management | MVP | 0
5.1 | Create model | You have to create a model the chosen technology (graphene) and pass all the requiered objects to it. |  | 4 | 6 | 8 | 8 | Kamil | March 25, 2021, 8:30 AM | March 26, 2021, 9:04 AM | 1 | 81.625 | 0 | PP-320 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/5 | Sprint 3 |  | Dataset upload and management | MVP | 8
5.2 | Implement get() endpoint | create a graphql endpoint according to the documentation with filters | 5.1 | 5 | 6 | 8 | 8 | Kamil | March 25, 2021, 8:30 AM | March 26, 2021, 9:04 AM | 1 | 81.625 | 0 | PP-321 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/5 | Sprint 3 |  | Dataset upload and management | MVP | 8
5.3 | Implement share() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | 2 | Kamil | March 25, 2021, 8:30 AM | March 26, 2021, 9:04 AM | 1 | 81.625 | 0 | PP-322 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/5 | Sprint 3 |  | Dataset upload and management | MVP | 2
5.4 | Implement unshare() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | 2 | Kamil | March 25, 2021, 8:30 AM | March 26, 2021, 9:04 AM | 1 | 81.625 | 0 | PP-323 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/5 | Sprint 3 |  | Dataset upload and management | MVP | 2
5.5 | Implement register() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | 2 | Kamil | March 25, 2021, 8:30 AM | March 26, 2021, 9:04 AM | 1 | 81.625 | 0 | PP-324 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/5 | Sprint 3 |  | Dataset upload and management | MVP | 2
5.6 | Implement remove() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | 2 | Kamil | March 25, 2021, 8:30 AM | March 26, 2021, 9:04 AM | 1 | 81.625 | 0 | PP-325 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/5 | Sprint 3 |  | Dataset upload and management | MVP | 2
5.7 | Implement add_user() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | 2 | Kamil | March 25, 2021, 8:30 AM | March 26, 2021, 9:04 AM | 1 | 81.625 | 0 | PP-488 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/5 | Sprint 3 |  | Dataset upload and management | MVP | 2
5.8 | Implement add_parameter() endpoint | create a graphql endpoint according to the documentation | 5.1 | 2 | 2 | 2 | 2 | Kamil | March 25, 2021, 8:30 AM | March 26, 2021, 9:04 AM | 1 | 81.625 | 0 | PP-489 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/5 | Sprint 3 |  | Dataset upload and management | MVP | 2
6 | Access on SQLAlchemy implementation | create models in sqlalchemy and implement abstract methods from access class.Create a model according to sql queries | [11 empty] | PP-326 |  | Sprint 3 |  | Dataset upload and management | MVP | 0
6.1 | implement the model | create a model according to sql queries | 3 | 8 | 8 | 12 | 12 | Kamil | March 26, 2021, 2:36 PM | April 2, 2021, 1:02 AM | 36 | 1512 | 261 | PP-327 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/6 | Sprint 3 |  | Dataset upload and management | MVP | 12
6.2 | Integration with Auth0 | integration with Auth0 | 6.1 | 4 |  |  | 4 | Kamil | April 2, 2021, 1:02 AM | April 2, 2021, 1:02 AM | 4 | 145 | 1 | PP-544 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/7 | Sprint 3 |  | Dataset upload and management | MVP | 4
7 | Admin panel implementation | Implement the admin panel using the Flask-Admin library | 5 | 6 | 8 | 16 | [7 empty] | PP-490 |  |  |  | Dataset upload and management | MVP | 0
8 | Flask integration | Integrate the flask server with sqlalchemy and graphene | 5, 6 | 4 | 6 | 8 | 8 | Kamil | April 2, 2021, 2:23 PM | April 6, 2021, 4:52 PM | 8 | 106 | 1 | PP-491 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/8 | Sprint 4 |  | Dataset upload and management | MVP | 8
9 | DatasetStorage implementation | Implement implementation of DatasetStoage with selected warehouse (snowflake) | 2 | 4 | 4 | 8 | [7 empty] | PP-492 |  |  |  | Dataset upload and management | MVP | 0
10 | Add readme | Add instructions on how to initialize and how to start the server | 8 | 1 |  |  | 1 | Kamil | April 6, 2021, 10:38 PM | April 6, 2021, 11:20 PM | 1 | 36 | 16 | PP-619 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/9 | Sprint 4 |  | Dataset upload and management | MVP | 1
11 | Improve technical documentation | Adapt the technical documentation to the changes that were made during the implementation | 8 | 8 |  |  | 8 | Kamil | April 13, 2021, 3:08 PM | April 14, 2021, 11:15 AM | 5 |  |  | PP-620 | - | Sprint 4 |  | Dataset upload and management | MVP | 8
12 | Implement graphql client |  |  | 16 |  |  | 16 | Kamil | April 7, 2021, 2:44 PM | April 13, 2021, 2:02 PM | 12.5 | 569 | 207 | PP-701 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/16 | Sprint 4 |  | Dataset upload and management | MVP | 16
13 | Create a python library |  |  | 3 |  |  | 3 | Kamil | April 7, 2021, 2:44 PM |  | 2.5 | 129 | 43 | PP-702 | https://gitlab-01.itx.pl/p2-project/datasetmanager/-/merge_requests/10 | Sprint 4 |  | Dataset upload and management | MVP | 3
14 | Research about deploying flask server on production |  |  | 4 |  |  | 4 | Kamil | April 7, 2021, 2:44 PM | April 7, 2021, 2:45 PM | 4 |  |  | PP-703 | - | Sprint 4 |  | Dataset upload and management | MVP | 4
15 | Implement integration with AWS secrets manager | see P2 implementation / design for example, use app_config package | P2/4 | 5 | 5 | [8 empty] | PP-1543 |  |  |  | Dataset upload and management | 1 | 0
16 | Reimplement Access class to new design | [12 empty] | PP-1544 |  |  |  | Dataset upload and management | 1 | 0
16.1 | Reimplement AccessMock class to new design | Add a list if changes in the current transaction. Add new methods: commits and rollback |  | 6 | 8 | [8 empty] | PP-1534 |  |  |  | Dataset upload and management | 1 | 0
16.2 | Reimplement SQLAccess class to new design | Add new methods: commit and rollback. Change all db.session.commit() to db.session.flush() |  | 2 | 4 | [8 empty] | PP-1545 |  |  |  | Dataset upload and management | 1 | 0
17 | Reimplement DataManager class | Add the user to the flash session, add the commit and rollback method (and queries) |  | 4 | 4 | [8 empty] | PP-1546 |  |  |  | Dataset upload and management | 1 | 0
18 | Reimplement client class | Add new methods: commit and rollback and extra http header autocommit | 17 | 2 | 4 | [8 empty] | PP-1547 |  |  |  | Dataset upload and management | 1 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions