## Description
Design document: | Preferred Partners Backend v3
Jira project: | P2 next gen (PP)
Jira label: | P2_v3
Number of tasks: | 353
Number of reported bugs: | 54
BE + DM + Grouper
Total planned development worktime [h]: | 2264.5 | 3027.5
Planned development worktime of finished tasks [h]: | 2205.5 | 2960.5
Current worktime spent [h]: | 2436.6633 | 2998.2487
Planned time to finish project [h]: | 59 | 67
Planned availability (until 28 May) [h]: |  | 0
Project completeness based on planned worktime [%]: | 97.3946 | 97.787
Current worktime vs planned worktime [%]: | 110.4812 | 101.2751 | > 100% - delay; < 100% - ahead
Last update | Jun 25, 2021 08:56:00
Number of updated tasks (during last update) | 1

## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  |  | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment | Category | Version | Planned dates
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions | [6 empty] | Start | Finish
1 | Analytical API | [12 empty] | PP-226 |  | Sprint 7 |  | Visualization Generation | MVP |  |  | 0 | #DIV/0!
1.1 | caseSummaryCollection endpoint | This is the basic functionality with filtering but without: benchmarks, pagination or sorting, some response elements are not present in the outputs | [11 empty] | PP-247 |  | Sprint 5 |  | Visualization Generation | MVP |  |  | 0
1.1.1 | Implement Filter and derived classes - ColumnFilter, DistanceFilter |  |  | 3 | 4 | 4 | 4 | Michał | February 22, 2021, 5:13 PM | February 23, 2021, 12:08 PM | 8 | 570 | 0 | PP-227 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/2 | Sprint 1 | More time due to code analysis tool rejections. | Visualization Generation | MVP | February 22, 2021, 5:13 PM | February 23, 2021, 12:08 PM | 4
1.1.2 | Implement extract_filters for the CaseSummaryFilterInputType input |  | 1.1.1 | 16 | 20 | 24 | 24 | Maciej | February 23, 2021, 2:11 PM | March 1, 2021, 6:13 PM | 32 | 391 | 1 | PP-228 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/8 | Sprint 1 |  | Visualization Generation | MVP | February 23, 2021, 2:11 PM | March 1, 2021, 6:13 PM | 24
1.1.3 | Implement extract_filters for the CaseSummaryActionsInputType input |  | 1.1.1 | 4 | 4 | 6 | 6 | Aleksandra | March 4, 2021, 1:38 PM | March 11, 2021, 11:56 AM | 15 | 301 | 181 | PP-229 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/19 | Sprint 2 |  | Visualization Generation | MVP | March 4, 2021, 1:38 PM | March 11, 2021, 11:56 AM | 6 | TRUE
1.1.4 | Implement extract_filters for the RangeInputType input |  | 1.1.1 | 2 | 2 | 4 | 4 | Maciej | March 1, 2021, 12:13 PM | March 1, 2021, 6:13 PM | 4 | 391 | 1 | PP-230 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/8 | Sprint 1 |  | Visualization Generation | MVP | March 1, 2021, 12:13 PM | March 1, 2021, 6:13 PM | 4
1.1.5 | Implement filter_by method for pandas.DataFrame with the ColumnFilter |  | 1.1.1 | 4 | 4 | 6 | 6 | Michał | February 25, 2021, 5:46 PM | February 26, 2021, 4:25 PM | 7 | 86 | 18 | PP-231 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/6 | Sprint 1 | More time due to code review rejection. | Visualization Generation | MVP | February 25, 2021, 5:46 PM | February 26, 2021, 4:25 PM | 6
1.1.6 | Implement filter_by method for pandas.DataFrame with the DistanceFilter |  | 1.1.1 | 12 | 16 | 16 | 16 | Michał | February 26, 2021, 3:08 PM | March 1, 2021, 5:48 PM | 10 | 69 | 23 | PP-232 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/7 | Sprint 1 |  | Visualization Generation | MVP | February 26, 2021, 3:08 PM | March 1, 2021, 5:48 PM | 16
1.1.19 | Implement filter_by method for pandas.DataFrame with the RangeFilter |  | 1.1.1 | 2 |  | 4 | 4 | Maciej | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 2.5 | 77 | 13 | PP-307 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/11 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks. | Visualization Generation | MVP | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 4
1.1.7 | Implement Node, NodeTypeEnum and NodeSubTypeEnum classes, implement get_node_type_from_subtype method |  |  | 3 | 4 | 6 | 6 | Maciej | February 23, 2021, 1:06 PM | February 23, 2021, 1:42 PM | 3 | 98 | 0 | PP-233 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/3 | Sprint 1 | Forgot to change jira status at the beginning of the work on task. | Visualization Generation | MVP | February 23, 2021, 1:06 PM | February 23, 2021, 1:42 PM | 6
1.1.8 | Implement PandasProvider class (extending the AnalyticsProvider) | We should be able to pull data from files (available in the project) and join with entities_ac / entities_pac automatically / carelines |  | 8 | 12 | 16 | 16 | Michał | February 23, 2021, 12:12 PM | February 25, 2021, 3:43 PM | 19 | 130 | 0 | PP-234 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/4 | Sprint 1 | More time spend due to fixes after code review + code fixes after more rigorous code analysis tool was implemented. | Visualization Generation | MVP | February 23, 2021, 12:12 PM | February 25, 2021, 3:43 PM | 16
1.1.20 | Add computed column fiscal_date to PandasAnalyticalService | fiscal_date = fiscal_year * 10 + fiscal_quarter |  | 2 |  | 4 | 4 | Maciej | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 2.5 | 77 | 13 | PP-308 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/11 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks. | Visualization Generation | MVP | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 4
1.1.9 | Implement the PandasAnalyticalService find_nodes method | leave other methods unimplemented, all types of nodes should be supported | 1.1.8, 1.1.5, 1.1.6 | 16 | 20 | 24 | 24 | Michał | March 2, 2021, 10:32 AM | March 3, 2021, 05:45 PM | 16 | 120 | 6 | PP-235 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/13 | Sprint 1 |  | Visualization Generation | MVP | March 2, 2021, 10:32 AM | March 3, 2021, 05:45 PM | 24
1.1.10 | Implement AbstractGraphQuery class and make_abstract_graph_query method | for now only implement the methods get_nodes and get_filters, leave the others unimplemented | 1.1.1 - 1.1.9 | 3 | 4 | 4 | 4 | Aleksandra | March 9, 2021, 10:32 AM | March 11, 2021, 11:56 AM | 15 | 301 | 181 | PP-236 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/19 | Sprint 2 | postponed from Sprint 1 | Visualization Generation | MVP | March 9, 2021, 10:32 AM | March 11, 2021, 11:56 AM | 4 | TRUE
1.1.11 | Implement AbstractGraphModel class and the make_abstract_graph_model method | for now do not handle the sorting or pagination info | 1.1.10 | 3 | 4 | 4 | 4 | Aleksandra | March 9, 2021, 10:32 AM | March 11, 2021, 11:56 AM | 15 | 301 | 181 | PP-237 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/19 | Sprint 2 | postponed from Sprint 1 | Visualization Generation | MVP | March 9, 2021, 10:32 AM | March 11, 2021, 11:56 AM | 4 | TRUE
1.1.12 | Implement PandasAnalyticalService group_nodes method | All types of nodes should be supported | 1.1.8 | 32 | 40 | 48 | 48 | Maciej | March 4, 2021, 4:01 PM | March 16, 2021, 11:26PM | 64 | 707 | 345 | PP-238 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/29 | Sprint 2 | postponed from Sprint 1; finish delayed due to bug #1 | Visualization Generation | MVP | March 4, 2021, 4:01 PM | March 16, 2021, 11:26PM | 48
1.1.13 | Implement SummaryStatistics class and extract_node_statistics method | All types of nodes should be supported | 1.1.12 | 18 | 24 | 24 | 24 | Maciej | March 16, 2021, 12:04 PM | March 18, 2021, 1:43 PM | 18 | 347 | 7 | PP-239 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/49 | Sprint 2 | postponed from Sprint 1 | Visualization Generation | MVP | March 16, 2021, 12:04 PM | March 18, 2021, 1:43 PM | 24
1.1.14 | Implement extract_relation_statistics method | For now do not extract benchmark_value | 1.1.13 | 5 | 8 | 8 | 8 | Maciej | March 19, 2021, 11:34 AM | March 19, 2021, 4:26 PM | 5 | 195 | 46 | PP-240 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/57 | Sprint 2 |  | Visualization Generation | MVP | March 19, 2021, 11:34 AM | March 19, 2021, 4:26 PM | 8
1.1.15 | Implement PandasAnalyticalService get_entity_details method | Just pull matching data from entities data frames | 1.1.9 | 4 | 4 | 4 | 4 | Michał | March 8, 2021, 2:48 PM | March 9, 2021, 1:42 PM | 8 | 63 | 11 | PP-241 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/16 | Sprint 2 |  | Visualization Generation | MVP | March 8, 2021, 2:48 PM | March 9, 2021, 1:42 PM | 4
1.1.16 | Implement copy_summary_statistics method |  | 1.1.13 | 4 | 4 | 4 | 4 | Aleksandra | March 18, 2021, 5:55 PM | March 19, 2021, 12:55 PM | 4 | 530 | 0 | PP-242 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/54 | Sprint 2 |  | Visualization Generation | MVP | March 18, 2021, 5:55 PM | March 19, 2021, 12:55 PM | 4
1.1.24 | Implement copy_node_details method |  |  | 4 |  | 4 | 4 | Maciej | March 24, 2021, 9:21 AM | March 25, 2021, 3:55 PM | 10 | 152 | 22 | PP-502 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/75 | Sprint 3 | Added to sprint in Sprint 3 | Visualization Generation | MVP | March 24, 2021, 9:21 AM | March 25, 2021, 3:55 PM | 4 | TRUE
1.1.17 | Implement CaseSummaryQueryRunner class | For now ignore the groupingInfo, benchmarkValues, count and legendData responses, ignore benchmark Future argument | 1.1.1 - 1.1.16, 1.1.24, 1.1.25 | 28 | 32 | 32 | 32 | Maciej | March 22, 2021, 9:50 AM | March 31, 2021, 4:17 PM | 40 | 533 | 48 | PP-243 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/96 | Sprint 3 | postponed from Sprint 2 | Visualization Generation | MVP | March 22, 2021, 9:50 AM | March 31, 2021, 4:17 PM | 32
1.1.25 | Implement format_case_summary_element method |  |  | 4 |  | 4 | 4 | Maciej | March 30, 2021, 2:39 PM | March 30, 2021, 4:39 PM | 2 | 69 | 3 | PP-575 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/93 | Sprint 3 | Added to sprint in Sprint 3 | Visualization Generation | MVP | March 30, 2021, 2:39 PM | March 30, 2021, 4:39 PM | 4
1.1.18 | implement caseSummaryCollection endpoint |  | 1.1.17 | 4 | 4 | 4 | 4 | Maciej | April 1, 2021, 6:06 AM | April 1, 2021, 2:40 PM | 7.75 | 85 | 25 | PP-244 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/103 | Sprint 3 | Sprint 3 due to dependencies | Visualization Generation | MVP | April 1, 2021, 6:06 AM | April 1, 2021, 2:40 PM | 4
1.1.21 | Implement get_sql_filter for Node | should return python object | 1.1.7 | 5 |  | 8 | 8 | Maciej | March 3, 2021, 4:58 PM | March 4, 2021, 1:39 PM | 4 | 72 | 6 | PP-309 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/14 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks. | Visualization Generation | MVP | March 3, 2021, 4:58 PM | March 4, 2021, 1:39 PM | 8
1.1.22 | Implement get_sql_group_column for Node | should return python object | 1.1.7 | 4 |  | 6 | 6 | Maciej | March 3, 2021, 4:58 PM | March 4, 2021, 1:39 PM | 4 | 73 | 7 | PP-310 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/14 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks. | Visualization Generation | MVP | March 3, 2021, 4:58 PM | March 4, 2021, 1:39 PM | 6
1.1.23 | Implement get_sql_chilld_id column for Node |  | 1.1.7 | 4 |  | 4 | 4 | Maciej | March 9, 2021, 12:41 PM | March 9, 2021, 12:58 PM | 1 | 51 | 1 | PP-368 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/15 | Sprint 2 |  | Visualization Generation | MVP | March 9, 2021, 12:41 PM | March 9, 2021, 12:58 PM | 4
1.1.32 | Implement filter_by method for pandas.DataFrame with the MultiFilter | add MultiFilter class to the project, see design | 1.1.5 | 4 |  |  | 4 | Tomek We | April 22, 2021, 2:24 PM |  | 4.5 | 120 | 2 | PP-1294 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/170 | Sprint 5 |  | Visualization Generation | MVP |  |  | 4
1.1.29 | Improve extract_filters for CaseSummaryFilterInputType |  | 1.1.32 | 8 |  |  | 8 | Tomek We | Apr 23, 2021 08:59:32 | Apr 26, 2021 12:58:41 | 8 | 150 | 43 | PP-1295 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/177 | Sprint 5 |  | Visualization Generation | MVP |  |  | 8
1.1.30 | Improve extract_filters to properly handle entity filter | create MultiFilter instance, see design | 1.1.32 | 3.5 |  |  | 3.5 | Tomek We | Apr 26, 2021 13:34:24 | Apr 27, 2021 07:44:53 | 3 | 84 | 26 | PP-1296 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/180 | Sprint 5 |  | Visualization Generation | MVP |  |  | 3.5
1.1.31 | Improve extract_filters to properly handle service line filter | create MultiFilter intstance, see design | 1.1.32 | 3.5 |  |  | 3.5 | Tomek We | Apr 26, 2021 15:48:14 | Apr 27, 2021 15:10:46 | 6 | 105 | 79 | PP-1297 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/184 | Sprint 5 |  | Visualization Generation | MVP |  |  | 3.5
1.1.32 | Implement Node.external_id property, see design | Find in code all places where Node.id is being returned from backend and replace with external_id |  | 3 |  |  | 3 | Manoj | May 17, 2021, 9:45 AM | May 17, 2021, 12:27 PM | 3 | 26 | 16 | PP-1378 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/272 | Sprint 7 |  | Visualization Generation | MVP |  |  | 3
1.1.33 | Update make_abstract_graph_query method to support multi-layered graph queries | see design |  | 4 |  |  | 4 | Michał | May 26, 2021, 5:28 PM | May 27, 2021, 12:23 PM | 3.5 | 96 | 3 | PP-1507 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/325 | Sprint 7 |  | Visualization Generation | MVP |  |  | 4
1.1.34 | Updade Node.external_id property to match updated design | see design |  | 3.5 |  |  | 3.5 | Aleksandra | June 7, 2021, 3:20 PM | June 7, 2021, 3:20 PM | 2 | 61 | 7 | PP-1554 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/373 | Sprint 8 |  | Visualization Generation | MVP |  |  | 3.5
1.1.35 | Implement get_parent method | see design, use existing get_parent method from AbstractGraphQuery as the starting point |  | 3 |  |  | 3 | Manoj | Jun 23, 2021 06:13:26 | Jun 24, 2021 11:28:38 | 4.6667 |  |  | PP-1651 |  | Sprint 9 |  | Visualization Generation | MVP |  |  | 3
1.1.36 | Remove get_parent method from AbstractGraphQuery | refactor code to use only the newly implemented free get_parent method, update implementation of get_grouping_info and get_legend_data to comply with the design (None may be returned for parent Node) |  | 12 |  |  | 12 | Manoj | [5 empty] | PP-1652 |  | Sprint 9 |  | Visualization Generation | MVP |  |  | 0
1.1.37 | Add lateral_filter argument to find_child_nodes method | see design |  | 3 |  |  | 3 | Maciej | Jun 23, 2021 10:06:06 | Jun 23, 2021 15:17:13 | 4.5333 |  |  | PP-1662 |  | Sprint 9 |  | Visualization Generation | MVP |  |  | 3
1.1.38 | Pass lateral_filter argument to find_child_nodes for the market share graph queries | Filter should be constructed using get_lateral_filter, it should resolve issue PP-1641 | 1.1.37 | 4 |  |  | 4 | Maciej | [5 empty] | PP-1663 |  | Sprint 9 |  | Visualization Generation | MVP |  |  | 0
1.1.26 | groupingInfo in caseSummaryCollection result | [12 empty] | PP-1014 |  | Sprint 4 |  | Visualization Generation | MVP |  |  | 0
1.1.26.1 | Implement get_grouping_info method | see design |  | 5 | 6 |  | 5 | Tomek We | April 15, 2021, 11:30 AM | April 15, 2021, 6:03 PM | 7 | 131 | 27 | PP-1007 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/141 | Sprint 4 | Added to sprint in sprint 4 | Visualization Generation | MVP |  |  | 5
1.1.26.2 | Handle grouping_info argument in copy_node_details, pass grouping_info when calling this method | run get_grouping_info and then use the results | 1.1.26.1 | 3.5 | 3 |  | 3.5 | Tomek We | Apr 15, 2021 16:04:30 | Apr 19, 2021 14:30:08 | 6 | 179 | 70 | PP-1008 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/145 | Sprint 4 | Added to sprint in sprint 4 | Visualization Generation | MVP |  |  | 3.5
1.1.26.3 | Implement get_lateral_filter method | see design |  | 3 | 1 |  | 3 | Tomek We | May 27, 2021, 12:11 PM | May 27, 2021, 2:50 PM | 1.5 | 73 | 1 | PP-1508 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/327 | Sprint 7 |  | Visualization Generation | MVP |  |  | 3
1.1.26.4 | Refactor get_grouping_info method to match the latest design |  | 1.1.26.3 | 4 | 8 |  | 4 | Tomek We | May 27, 2021, 2:53 PM | May 31, 2021, 2:02 PM | 10.5 | 186 | 126 | PP-1509 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/339 | Sprint 8 |  | Visualization Generation | MVP |  |  | 4
1.1.27 | auto-expanding of nodes | [12 empty] | PP-1015 |  | Sprint 6 | Not so important so far, as well needs to discuss with FE as some modification will be required. | Visualization Generation | MVP |  |  | 0 | #DIV/0!
1.1.27.1 | Implement post_process_nodes method | make sure to use multiple threads when executing find_child_nodes, see design | 1.1.26 | 6 |  |  | 6 | Manoj | Apr 27, 2021 09:00:21 | Apr 28, 2021 09:56:17 | 10 | 42 | 1 | PP-1039 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/186 | Sprint 5 |  | Visualization Generation | MVP |  |  | 6
1.1.27.2 | Integrate post_process_nodes method with CaseSummaryQueryRunner | see design, add auto_expand flag to class constructor, pass auto_expand = False in legacy tests so that they pass | 1.1.27.1 | 4 |  |  | 4 | Manoj | Apr 28, 2021 11:39:20 | Apr 28, 2021 15:02:44 | 5 | 96 | 29 | PP-1040 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/187 | Sprint 5 |  | Visualization Generation | MVP |  |  | 4
1.1.27.3 | Implement find_expanded_child_nodes | Make sure to handle dry_run result (int), see design |  | 4 |  |  | 4 | Manoj | Apr 29, 2021 06:52:28 | Apr 29, 2021 13:18:27 | 4 | 54 | 1 | PP-1298 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/189 | Sprint 5 |  | Visualization Generation | MVP |  |  | 4
1.1.27.4 | Integrate find_expanded_child_nodes with caseSummaryCollection endpoint | just replace use of find_child_nodes with find_expanded_child_nodes, preserve existing unit tests |  | 3 |  |  | 3 | Manoj | Apr 29, 2021 15:01:54 | Apr 29, 2021 15:23:58 | 4 | 47 | 5 | PP-1299 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/191 | Sprint 5 |  | Visualization Generation | MVP |  |  | 3
1.1.27.5 | Implement is_hospital_node_included method |  |  | 2.5 |  |  | 2.5 | Manoj | Apr 30, 2021 11:30:45 | Apr 30, 2021 11:31:02 | 5 | 27 | 1 | PP-1300 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/192 | Sprint 5 |  | Visualization Generation | MVP |  |  | 2.5
1.1.27.6 | Add expand_hospital_node argument to find_expanded_child_nodes and integrate with caseSummaryCollection | Call is_hospital_node_included and pass the result to find_expanded_child_nodes |  | 3 |  |  | 3 | Manoj | Apr 30, 2021 14:49:38 | May 03, 2021 15:09:56 | 5 | 41 | 11 | PP-1301 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/193 | Sprint 6 |  | Visualization Generation | MVP |  |  | 3 | 1.6667
1.1.28 | Geography Selection Logic | see design | [11 empty] | PP-1041 |  | Sprint 6 |  | Filters - Geography (Location) filters | MVP |  |  | 0 | #DIV/0!
1.1.28.1 | Implement get_location_filter_level method | see design |  | 6 |  |  | 6 | Michał, Kamil C | April 22, 2021, 1:31 PM |  | 6 | 95 | 7 | PP-1042 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/175 https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/176/diffs | Sprint 5 |  | Filters - Geography (Location) filters | MVP |  |  | 6
1.1.28.2 | Modify extract_filters method to take LocationFilterLevel as argument and construct filters accordingy (using proper column aliases), update DistanceFilter class to keep the "level" property | refactor code and pass location_filter_level argument to all calls of extract_filter method, use get_location_filter_level to extract this information, modify PandasAnalyticalService and SQLAnalyticalService to generate proper column aliases | 1.1.28.1 | 16 |  |  | 16 | Michał | Apr 23, 2021 14:56:08 | Apr 29, 2021 06:25:59 | 16.5 | 187 | 32 | PP-1043 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/182 | Sprint 5 |  | Filters - Geography (Location) filters | MVP |  |  | 16
1.1.28.3 | Refactor PandasAnalyticalService filtering by DistanceFilter | Handle "level" property from the DistanceFilter, use proper columns for filtering |  | 8 |  |  | 8 | Manoj | Apr 26, 2021 12:27:10 | Apr 26, 2021 12:27:16 | 7 | 59 | 11 | PP-1044 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/178 | Sprint 5 |  | Filters - Geography (Location) filters | MVP |  |  | 8
1.1.28.4 | Refactor SQLAnalyticalService filtering by DistanceFilter | Handle "level" property from the DistanceFilter, use proper columns for filtering | 1.24 | 8 |  |  | 8 | Manoj | May 31, 2021 07:02:13 | May 31, 2021 14:46:10 | 8.1667 | 59 | 6 | PP-1045 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/340 | Sprint 8 |  | Filters - Geography (Location) filters | MVP |  |  | 8
1.2 | caseLocationDetails endpoint | For now we ignore the "state" output which is likely not used |  |  |  |  | 0 | [6 empty] | PP-248 |  | Sprint 3 |  | Filters - Geography (Location) filters | MVP |  |  | 0
1.2.1 | implement extract_filters method | The method takes CaseLocationOptionInputType as input, use already existing extract_filters method implementation for the nested types | 1.1.2 - 1.1.4 | 6 | 8 | 8 | 8 | Michał | March 17, 2021, 1:56 PM | March 17, 2021, 6:32 PM | 7 | 171 | 21 | PP-249 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/46 | Sprint 2 |  | Filters - Geography (Location) filters | MVP | March 17, 2021, 1:56 PM | March 17, 2021, 6:32 PM | 8
1.2.2 | implement get_entity_counts method in PandasAnalyticalService | use data frames provided in the examples, calculate statistics both for PACs and hospitals | 1.1.8, 1.2.1 | 20 | 24 | 24 | 24 | Michał | March 9, 2021, 4:58 PM | March 12, 2021, 4:14PM | 24 | 188 | 4 | PP-250 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/22 | Sprint 2 |  | Filters - Geography (Location) filters | MVP | March 9, 2021, 4:58 PM | March 12, 2021, 4:14PM | 24
1.2.3 | implement copy_location_details method |  |  | 8 | 12 | 16 | 16 | Michał | March 15, 2021, 1:07 PM | March 17, 2021, 3:59 PM | 18 | 137 | 6 | PP-251 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/35 | Sprint 2 |  | Filters - Geography (Location) filters | MVP | March 15, 2021, 1:07 PM | March 17, 2021, 3:59 PM | 16
1.2.4 | implement caseLocationDetails endpoint |  | 1.2.1 - 1.2.3 | 4 | 8 | 8 | 8 | Michał | March 17, 2021, 6:32 PM | March 19, 2021, 5:41 PM | 16 | 819 | 373 | PP-252 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/60 | Sprint 3 | postponed from Sprint 2 | Filters - Geography (Location) filters | MVP | March 17, 2021, 6:32 PM | March 19, 2021, 5:41 PM | 8
1.3 | caseLobCounts endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-253 |  | Sprint 2 |  | Filters - LOB filters | MVP |  |  | 0
1.3.1 | implement get_lob_statistics in PandasAnalyticalService |  | 1.1.8 | 4 | 4 | 4 | 4 | Aleksandra | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 1 | 60 | 4 | PP-254 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/21 | Sprint 2 |  | Filters - LOB filters | MVP | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 4
1.3.2 | implement copy_lob_statistics method |  |  | 3.5 | 4 | 2 | 2 | Aleksandra | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 1 | 60 | 4 | PP-255 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/21 | Sprint 2 |  | Filters - LOB filters | MVP | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 2
1.3.3 | Implement caseLobCounts endpoint | see design | 1.3.1, 1.3.2 | 1 | 2 | 4 | 4 | Aleksandra | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 1 | 60 | 4 | PP-256 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/21 | Sprint 2 |  | Filters - LOB filters | MVP | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 4
1.4 | getAvailableYears endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-257 |  | Sprint 2 |  | Visualization Generation | MVP |  |  | 0
1.4.1 | Implement get_all_years method in PandasAnalitycalService |  | 1.1.8 | 2 | 2 | 2 | 2 | Aleksandra | March 12, 2021, 1:52 PM | March 15, 2021, 11:25 AM | 2 | 50 | 13 | PP-258 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/25 | Sprint 2 |  | Visualization Generation | MVP | March 12, 2021, 1:52 PM | March 15, 2021, 11:25 AM | 2
1.4.2 | Implement get_row_range helper method for pandas DF |  |  | 1 | 2 | 4 | 4 | Aleksandra | March 12, 2021, 1:52 PM | March 15, 2021, 11:28 AM | 2 | 30 | 1 | PP-259 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/26 | Sprint 2 |  | Visualization Generation | MVP | March 12, 2021, 1:52 PM | March 15, 2021, 11:28 AM | 4
1.4.3 | Implement getAvailableYears endpoint | see design | 1.4.1, 1.4.2 | 1 | 2 | 4 | 4 | Aleksandra | March 12, 2021, 1:52 PM | March 15, 2021, 11:29 AM | 2 | 47 | 0 | PP-260 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/27 | Sprint 2 |  | Visualization Generation | MVP | March 12, 2021, 1:52 PM | March 15, 2021, 11:29 AM | 4
1.5 | getDateTimeStatsForListOfYears endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-261 |  | Sprint 2 |  | Visualization Generation | MVP |  |  | 0
1.5.1 | implement get_quarterly_statistics method in PandasAnalyticalService |  | 1.1.8 | 3 | 4 | 4 | 4 | Tomek We | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 5 | 67 | 7 | PP-262 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/23 | Sprint 2 |  | Visualization Generation | MVP | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 4
1.5.2 | implement copy_quarterly_statistics method |  |  | 2 | 2 | 2 | 2 | Tomek We | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 5 | 67 | 7 | PP-263 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/23 | Sprint 2 |  | Visualization Generation | MVP | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 2 | TRUE
1.5.3 | implement getDateTimeStatsForListOfYears endpoint | see design | 1.5.1, 1.5.2 | 2 | 2 | 4 | 4 | Tomek We | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 5 | 67 | 7 | PP-264 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/23 | Sprint 2 |  | Visualization Generation | MVP | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 4
1.5.4 | Handle None / empty year list as query argument | see design | 1.5.3 | 2 |  |  | 2 | Aleksandra | May 20, 2021, 5:42 PM | May 21, 2021, 11:01 AM | 0 |  |  | PP-1411 | - | Sprint 7 |  | Visualization Generation | MVP |  |  | 2
1.6 | implement filteredCareUnitTypes endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-265 |  | Sprint 2 |  | Visualization Generation | MVP |  |  | 0
1.6.1 | Implement get_careunit_statistics method in PandasAnalyticalService |  | 1.1.8 | 3 | 4 | 4 | 4 | Tomek We | March 5, 2021, 3:33 PM | March 10, 2021, 6:12 PM | 9 | 72 | 3 | PP-285 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/18 | Sprint 2 |  | Visualization Generation | MVP | March 5, 2021, 3:33 PM | March 10, 2021, 6:12 PM | 4 | TRUE
1.6.2 | Implement extract_careunit_statistics method |  |  | 2 | 2 | 4 | 4 | Tomek We | March 5, 2021, 3:33 PM | March 10, 2021, 6:12 PM | 9 | 72 | 3 | PP-286 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/18 | Sprint 2 |  | Visualization Generation | MVP | March 5, 2021, 3:33 PM | March 10, 2021, 6:12 PM | 4 | TRUE
1.6.3 | Implement filteredCareUnitTypes endpoint | see design | 1.6.1, 1.6.2 | 1 | 2 | 4 | 4 | Tomek We | March 9, 2021, 11:43 AM | March 10, 2021, 6:12 PM | 9 | 74 | 4 | PP-265 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/18 | Sprint 2 |  | Visualization Generation | MVP | March 9, 2021, 11:43 AM | March 10, 2021, 6:12 PM | 4 | TRUE
1.7 | implement getDatasetsInitialFilters | see design |  |  |  |  | 0 | [6 empty] | PP-288 |  | Sprint 1 |  | Visualization Generation | MVP |  |  | 0
1.7.1 | Implement get_diagnose_statistics method in PandasAnalyticalService |  | 1.1.8 | 3.5 | 4 | 4 | 4 | Aleksandra | February 25, 2021, 2:55 PM | March 4, 2021, 01:19 AM | 16 | 247 | 4 | PP-289 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/12 | Sprint 1 | Added during sprint, due to earlier finish of research tasks. | Visualization Generation | MVP | February 25, 2021, 2:55 PM | March 4, 2021, 01:19 AM | 4 | TRUE
1.7.2 | implement copy_diagnose_statistics method |  |  | 2 | 2 | 2 | 2 | Aleksandra | March 1, 2021, 5:02 PM | March 4, 2021, 01:19 AM | 16 | 247 | 4 | PP-290 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/12 | Sprint 1 | Added during sprint, due to earlier finish of research tasks. | Visualization Generation | MVP | March 1, 2021, 5:02 PM | March 4, 2021, 01:19 AM | 2 | TRUE
1.7.3 | implement getDatasetsInitialFilters endpoint | use existing queries / methods to populate data in the requested fields | 1.3, 1.4, 1.5, 1.6 | 6 | 6 | 4 | 4 | Aleksandra | March 1, 2021, 5:03 PM | March 4, 2021, 01:19 AM | 16 | 247 | 4 | PP-291 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/12 | Sprint 1 | Added during sprint, due to earlier finish of research tasks. Task to be finished - dependencies have to be implemented later. | Visualization Generation | MVP | March 1, 2021, 5:03 PM | March 4, 2021, 01:19 AM | 4 | TRUE
1.8 | filteredCareUnits endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-371 |  | Sprint 4 |  | Visualization Generation | MVP |  |  | 0
1.8.3 | Implement format_careunits method |  |  | 3.5 | 4 | 4 | 4 | Manoj | April 8, 2021, 5:11 PM | April 8, 2021, 5:11 PM | 5 | 40 | 3 | PP-375 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/115 | Sprint 4 |  | Visualization Generation | MVP | April 8, 2021, 5:11 PM | April 8, 2021, 5:11 PM | 4
1.8.4 | Implement filteredCareUnits endpoint |  | 1.6, 1.8.3, 1.13 | 8 | 4 | 10 | 10 | Manoj | April 8, 2021, 6:52 PM | April 9, 2021, 3:44 PM | 9 | 122 | 2 | PP-376 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/119 | Sprint 4 |  | Visualization Generation | MVP | April 8, 2021, 6:52 PM | April 9, 2021, 3:44 PM | 10
1.8.5 | Handle undefined careUnit type in filteredCareUnits | see design |  | 3.5 |  |  | 3.5 | Kamil C | May 17, 2021, 4:05 PM | May 17, 2021, 4:52 PM | 4.5 | 127 | 34 | PP-1387 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/276 | Sprint 7 |  | Visualization Generation | MVP |  |  | 3.5
1.9 | searchCareUnitAndDetail endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-377 |  | Sprint 5 |  | Visualization Generation | MVP |  |  | 0
1.9.1 | Implement make_hospital_node |  |  | 1 | 1 | 2 | 2 | Aleksandra | March 16, 2021, 5:07 PM | March 17, 2021, 2:11 PM | 3 | 21 | 0 | PP-378 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/44 | Sprint 2 | Added to sprint in Sprint 2 | Visualization Generation | MVP | March 16, 2021, 5:07 PM | March 17, 2021, 2:11 PM | 2
1.9.2 | Implement make_entity_node |  |  | 2.5 | 2 | 2 | 2 | Aleksandra | March 16, 2021, 5:07 PM | March 17, 2021, 2:11 PM | 3 | 21 | 0 | PP-379 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/44 | Sprint 2 | Added to sprint in Sprint 2 | Visualization Generation | MVP | March 16, 2021, 5:07 PM | March 17, 2021, 2:11 PM | 2
1.9.3 | Handle result_set argument in the group_nodes method (inside PandasAnalyticalService) | handle only SHORT and FULL GroupNodesResultSet values | 1.1.12 | 5 | 12 | 16 | 16 | Aleksandra | March 17, 2021, 5:44 PM | March 17, 2021, 8:03 PM | 2.5 | 107 | 26 | PP-380 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/47 | Sprint 2 | Added to sprint in Sprint 2 | Visualization Generation | MVP | March 17, 2021, 5:44 PM | March 17, 2021, 8:03 PM | 16
1.9.4 | Modify extract_node_statistics to extract full result | extract 60-day readmission statistics when available | 1.1.13 | 2.5 | 4 | 4 | 4 | Manoj | March 22, 2021, 5:34 PM | March 22, 2021, 4:16 PM | 4 | 65 | 6 | PP-381 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/61 | Sprint 3 | Problem with actual time estimation, because of not updated jira | Visualization Generation | MVP | March 22, 2021, 5:34 PM | March 22, 2021, 4:16 PM | 4
1.9.5 | Implement get_careunit_details method |  | 1.1.15, 1.9.4 | 4 | 4 | 6 | 6 | Manoj | March 22, 2021, 5:35 PM | March 22, 2021, 7:43 AM | 6 | 133 | 8 | PP-382 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/62 | Sprint 3 |  | Visualization Generation | MVP | March 22, 2021, 5:35 PM | March 22, 2021, 7:43 AM | 6
1.9.6 | Implement get_entity_address in PandasAnalyticalService | provide required datasets | 1.1.9 | 8 | 6 | 8 | 8 | Manoj | March 18, 2021, 8:14 AM | March 19, 2021, 4:28 PM | 16 | 41 | 1 | PP-383 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/58 | Sprint 3 | Problem with actual time estimation, because of not updated jira | Visualization Generation | MVP | March 18, 2021, 8:14 AM | March 19, 2021, 4:28 PM | 8
1.9.7 | Implement make_address method |  |  | 1 | 1 | 2 | 2 | Manoj | March 19, 2021, 4:55 PM | March 19, 2021, 4:43PM | 2 | 24 | 1 | PP-384 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/59 | Sprint 3 | Problem with actual time estimation, because of not updated jira | Visualization Generation | MVP | March 19, 2021, 4:55 PM | March 19, 2021, 4:43PM | 2
1.9.8 | Implement get_entity_quality in PandasAnalyticalService |  | 1.9.6 | 26 | 32 | 36 | 36 | Bartek | March 31, 2021, 3:15 PM | April 6, 2021, 8:52 AM | 16.5 | 403 | 6 | PP-385 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/106 | Sprint 4 | Sprint 3, sprint 4 | Visualization Generation | MVP | March 31, 2021, 3:15 PM | April 6, 2021, 8:52 AM | 36
1.9.9 | Implement make_quality method |  |  | 1 | 1 | 1 | 1 | Manoj | March 24, 2021, 2:00 PM | March 24, 2021, 10:24 AM | 1.66 | 11 | 1 | PP-386 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/70 | Sprint 3 | Problem with actual time estimation, because of not updated jira | Visualization Generation | MVP | March 24, 2021, 2:00 PM | March 24, 2021, 10:24 AM | 1
1.9.10 | Implement get_facility_details in PandasAnalyticalService |  | 1.9.6 | 18 | 16 | 24 | 24 | Bartek | April 6, 2021, 9:38 AM | April 6, 2021, 2:29 PM | 5 | 116 | 9 | PP-387 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/109 | Sprint 4 | Postponed from sprint 3 (lower priority) | Visualization Generation | MVP | April 6, 2021, 9:38 AM | April 6, 2021, 2:29 PM | 24
1.9.11 | Implement make_facility method |  |  | 1 | 1 | 2 | 2 | Manoj | March 24, 2021, 2:02 PM | March 24, 2021, 10:24 AM | 1.66 | 11 | 1 | PP-388 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/70 | Sprint 3 | Problem with actual time estimation, because of not updated jira | Visualization Generation | MVP | March 24, 2021, 2:02 PM | March 24, 2021, 10:24 AM | 2
1.9.12 | Implement get_entity_staffing in PandasAnalyticalService |  | 1.9.6 | 4 | 4 | 4 | 4 | Manoj | March 23, 2021, 5:03 PM | March 24, 2021, 10:31 AM | 4 | 33 | 0 | PP-389 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/71 | Sprint 3 |  | Visualization Generation | MVP | March 23, 2021, 5:03 PM | March 24, 2021, 10:31 AM | 4
1.9.13 | Implement make_staffing method |  |  | 1 | 1 | 2 | 2 | Manoj | March 23, 2021, 5:03 PM | March 24, 2021, 10:24 AM | 1.66 | 11 | 1 | PP-390 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/70 | Sprint 3 |  | Visualization Generation | MVP | March 23, 2021, 5:03 PM | March 24, 2021, 10:24 AM | 2
1.9.14 | Implement searchCareUnitAndDetail endpoint |  | 1.9.1 - 1.9.13 | 8 | 8 | 10 | 10 | Michał | April 6, 2021, 3:10 PM | April 22, 2021, 12:40 PM | 14.5 | 128 | 1 | PP-391 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/167 | Sprint 5 | Postponed from sprint 3 (lower priority), Postponed from Sprint 4 due to Bartek unavailability | Visualization Generation | MVP | April 6, 2021, 3:10 PM | 2021-04-16 | 10
1.10 | getDateTimesForYear endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-392 |  | Sprint 2 |  | Filters - Time filters | MVP |  |  | 0
1.10.1 | Implement find_fiscal_quarters method in PandasAnalyticalService |  | 1.1.9 | 3 | 2 | 8 | 8 | Bartek | March 16, 2021, 11:54 AM | March 17, 2021, 1:29 PM | 5 | 59 | 6 | PP-393 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/33 | Sprint 2 | Added to sprint in Sprint 2 | Filters - Time filters | MVP | March 16, 2021, 11:54 AM | March 17, 2021, 1:29 PM | 8
1.10.2 | Implement getDateTimesForYear endpoint |  | 1.10.1 | 3 | 2 | 4 | 4 | Bartek | March 16, 2021, 11:54 AM | March 17, 2021, 1:29 PM | 5 | 59 | 6 | PP-394 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/33 | Sprint 2 | Added to sprint in Sprint 2 | Filters - Time filters | MVP | March 16, 2021, 11:54 AM | March 17, 2021, 1:29 PM | 4
1.11 | Benchmark Calculation | see design |  |  |  |  | 0 | [6 empty] | PP-395 |  | Sprint 5 |  | Visualization Generation | MVP |  |  | 0
1.11.1 | Implement get_dataset_properties in the DatasetService | see DatasetService design | DM | 4 | 3 | 8 | 8 | Kamil C |  |  | 0 |  |  | PP-396 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/73 | Sprint 5 | Done already together with 1.15.1 | Visualization Generation | MVP |  |  | 8
1.11.2 | Implement set_dataset_properties in DatasetService |  | DM | 6 | 3 | 8 | 8 | Kamil C |  |  | 0 |  |  | PP-397 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/73 | Sprint 5 | Done already together with 1.15.1 | Visualization Generation | MVP |  |  | 8
1.11.3 | Implement find_datasets in DatasetService |  | DM | 4 | 4 | 4 | 4 | Kamil C |  |  | 0 |  |  | PP-398 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/73 | Sprint 5 | Done already together with 1.15.1 | Visualization Generation | MVP |  |  | 4
1.11.4 | Implement get_time_range in PandasAnalyticalService |  | 1.1.8 | 3 | 2 | 4 | 4 | Bartek | March 18, 2021, 12:36 PM | March 19, 2021, 12:25 PM | 8 | 33 | 3 | PP-399 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/50 | Sprint 2 | Added to sprint in Sprint 2 | Visualization Generation | MVP | March 18, 2021, 12:36 PM | March 19, 2021, 12:25 PM | 4
1.11.5 | Implement find_dataset_time_range | use mock DatasetService for tests |  | 4 | 3 | 4 | 4 | Bartek | March 19, 2021, 11:36 AM | March 22, 2021, 9:56 AM | 6 | 123 | 12 | PP-400 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/55 | Sprint 3 |  | Visualization Generation | MVP | March 19, 2021, 11:36 AM | March 22, 2021, 9:56 AM | 4
1.11.6 | Implement find_benchmark_datasets method | use mock DatasetService for tests | 1.11.4, 1.11.5 | 6 | 6 | 8 | 8 | Bartek | March 22, 2021, 10:24 AM | March 24, 2021, 4:18 PM | 20 | 153 | 44 | PP-401 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/63 | Sprint 3 | Require reimplementation due to misunderstanding of requirements: https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/63 | Visualization Generation | MVP | March 22, 2021, 10:24 AM | March 24, 2021, 4:18 PM | 8 | TRUE
1.11.7 | Implement calculate_benchmark method in PandasAnalyticalService | for now do not implement any special handling of AC_Entity / PAC_Entity nodes, do not handle packed nodes | 1.1.8 | 40 | 40 | 48 | 48 | Michał | March 19, 2021, 6:26 PM | April 9, 2021, 3:54 PM | 38.5 | 396 | 2 | PP-402 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/120 | Sprint 4 | Delayed significantly due to COVID | Visualization Generation | MVP | March 19, 2021, 6:26 PM | April 9, 2021, 3:54 PM | 48
1.11.8 | Implement get_service_line in PandasAnalyticalService |  | 1.1.8 | 3 | 3 | 4 | 4 | Bartek | March 23, 2021, 9:49 AM | March 24, 2021, 4:39 PM | 6 | 31 | 1 | PP-403 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/67 | Sprint 3 |  | Visualization Generation | MVP | March 23, 2021, 9:49 AM | March 24, 2021, 4:39 PM | 4
1.11.9 | Implement get_clinical_episode in PandasAnalyticalService |  | 1.1.8 | 3 | 3 | 4 | 4 | Bartek | March 23, 2021, 3:19 PM | March 24, 2021, 4:23PM | 4 | 25 | 2 | PP-404 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/68 | Sprint 3 |  | Visualization Generation | MVP | March 23, 2021, 3:19 PM | March 24, 2021, 4:23PM | 4
1.11.10 | Implement get_parent_node method |  | 1.11.8, 1.11.9 | 3 | 2 | 4 | 4 | Bartek | March 24, 2021, 2:54 PM | March 25, 2021, 11:27 PM | 4 | 95 | 9 | PP-405 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/74 | Sprint 3 |  | Visualization Generation | MVP | March 24, 2021, 2:54 PM | March 25, 2021, 11:27 PM | 4
1.11.11 | Handle parent nodes in calculate_benchmark method | see design | 1.11.7 | 12 | 8 | 16 | 16 | Michał | Apr 09, 2021 15:17:28 | Apr 13, 2021 18:10:14 | 21 | 235 | 95 | PP-406 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/129 | Sprint 4 | Postponed from sprint 3 (lower priority) | Visualization Generation | MVP | April 9, 2021, 5:17 PM | 2021-04-13 | 16
1.11.12 | Implement extract_time_range method | see design |  | 3.5 | 3 | 4 | 4 | Michał | March 24, 2021, 10:47 AM | March 24, 2021, 4:00 PM | 2 | 20 | 1 | PP-407 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/72 | Sprint 3 |  | Visualization Generation | MVP | March 24, 2021, 10:47 AM | March 24, 2021, 4:00 PM | 4
1.11.13 | Implement make_filter (from time range) method | see design | 1.11.12 | 1.5 | 3 | 4 | 4 | Michał | March 24, 2021, 10:47 AM | March 24, 2021, 4:00 PM | 2 | 20 | 1 | PP-408 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/72 | Sprint 4 | Postponed from sprint 3 (lower priority) | Visualization Generation | MVP | March 24, 2021, 10:47 AM | March 24, 2021, 4:00 PM | 4
1.11.14 | Extract benchmark_value in extract_relation_statistics method | see design | 1.1.14 | 6 | 8 | 16 | 16 | Michał | March 25, 2021, 9:55 AM | March 25, 2021, 3:55 PM | 6 | 40 | 0 | PP-409 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/78 | Sprint 3 |  | Visualization Generation | MVP | March 25, 2021, 9:55 AM | March 25, 2021, 3:55 PM | 16
1.11.15 | Handle benchmark future argument in CaseSummaryQueryRunner |  | 1.1.17 | 16 | 16 | 16 | 16 | Tomek We | April 8, 2021, 11:26 AM | April 9, 2021, 5:47 PM | 14 | 117 | 25 | PP-410 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/122 | Sprint 4 |  | Visualization Generation | MVP | April 8, 2021, 11:26 AM | April 9, 2021, 5:47 PM | 16
1.11.16 | Integrate benchmark calculations with the caseSummaryCollection query | see design | 1.11.4 - 1.11.15 | 24 | 24 | 32 | 32 | Kamil C | April 16, 2021, 9:47 AM | April 20, 2021, 2:20 PM | 14 | 229 | 71 | PP-411 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/154 | Sprint 5 | Started in sprint 4 | Visualization Generation | MVP |  |  | 32
1.11.17 | Implement handling of packed nodes in calculate_benchmark (use decompose_packed_nodes decorator) | see design, implement a unit test for this use case | 1.14.7, 1.14.11 | 6 |  | 8 | 8 | Manoj | April 21, 2021, 4:01 PM | April 21, 2021, 4:01 PM | 4 | 49 | 5 | PP-503 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/162 | Sprint 5 |  | Visualization Generation | MVP |  |  | 8
1.11.18 | Add source / destination to CaseSummaryType in format_relation_statistics | fix extract_relation_statistics to populate lhs_node and rhs_node in RelationStatistics, then use those members to populate CaseSummaryType in format_relation_statistics |  | 1.5 |  |  | 1.5 | Michał | April 14, 2021, 5:20 PM | April 14, 2021, 5:56 PM | 0.5 | 14 | 0 | PP-704 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/134 | Sprint 4 | Added to sprint in Sprint 4 | Visualization Generation | MVP |  |  | 1.5
1.11.19 | Implement percentile calculation rules for calculate_benchmark in PandasAnalyticalService | see design |  | 12 |  |  | 12 | Kamil C | May 25, 2021, 8:12 AM | June 9, 2021, 8:53 AM | 31 | 268 | 102 | PP-1452 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/388 | Sprint 8 |  | Visualization Generation | MVP |  |  | 12
1.11.20 | Implement percentile calculation rules for calculate_benchmark in SQLAnalyticalService | see pandas implementation for example | 1.11.19 | 8 |  |  | 8 | Kamil C | May 25, 2021, 8:12 AM | June 9, 2021, 8:53 AM | 0 |  |  | PP-1453 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/388 | Sprint 8 | Merged together with 1.11.19 | Visualization Generation | MVP |  |  | 8
1.11.21 | Implement extract_benchmark_filters method | see design |  | 3 |  |  | 3 | Aleksandra | June 9, 2021, 10:46 AM | June 9, 2021, 10:47 AM | 3 | 111 | 18 | PP-1550 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/390 | Sprint 8 |  | Visualization Generation | MVP |  |  | 3
1.11.22 | Integrate benchmark calculations with the caseSummaryCollectionMapView query | see design | 1.11.21 | 4 |  |  | 4 | Aleksandra | June 9, 2021, 11:35 AM | June 9, 2021, 11:35 AM | 1 | 10 | 4 | PP-1551 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/392 | Sprint 8 |  | Visualization Generation | MVP |  |  | 4
1.11.23 | Implement prepare_service_line_rule_filters method | see design |  | 3 |  |  | 3 | Aleksandra | June 8, 2021, 2:27 PM | June 8, 2021, 2:31 PM | 3.5 | 100 | 4 | PP-1552 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/385 | Sprint 8 |  | Visualization Generation | MVP |  |  | 3
1.11.24 | Integrate 5-service lines rule for benchmark calculation with the caseSummaryCollectionMapView query | see design | 1.11.22, 1.11.23 | 3 |  |  | 3 | Aleksandra | June 9, 2021, 11:51 AM | June 9, 2021, 11:51 AM | 1 | 1 | 0 | PP-1553 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/393 | Sprint 8 |  | Visualization Generation | MVP |  |  | 3
1.12 | Node Expand and Collapse | see design |  |  |  |  | 0 | [6 empty] | PP-460 |  | Sprint 5 |  | Visualization Navigation | MVP |  |  | 0
1.12.1 | Implement extract_action method | see design |  | 4 | 4 | 8 | 8 | Aleksandra | April 6, 2021, 3:21 PM | April 6, 2021, 3:21 PM | 6 | 158 | 3 | PP-461 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/110 | Sprint 4 | Moved from Sprint 5 | Visualization Navigation | MVP | April 6, 2021, 3:21 PM | April 6, 2021, 3:21 PM | 8
1.12.2 | Implement make_filter_from_node method | see design | 1.1.7, 1.1.21 - 1.1.23 | 4 | 4 | 8 |  |  |  |  | 0 |  |  | PP-462 |  | Sprint 5 | Abandoned - method already exists. | Visualization Navigation | MVP |  |  | 0
1.12.3 | Implement extract_filters method | extracting filters from list of actions | 1.12.1, 1.12.2 | 2 | 2 | 4 | 4 | Aleksandra | April 6, 2021, 3:45 PM | April 20, 2021, 9:32 AM | 3 | 678.6667 | 22 | PP-463 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/146 | Sprint 5 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/146 | Visualization Navigation | MVP | April 6, 2021, 3:45 PM | 2021-12-04 | 4
1.12.4 | Integrate expand / collapse functionality with the caseSummaryCollection query | see design | 1.1, 1.12.1 - 1.12.3 | 22 | 24 | 32 | 32 | Aleksandra | April 7, 2021, 7:52 PM | April 20, 2021, 9:32 AM | 44 | 678.6667 | 22 | PP-464 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/146 | Sprint 5 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/146 | Visualization Navigation | MVP |  |  | 32
1.13 | find_child_nodes | see design |  |  |  |  | 0 | [6 empty] | PP-465 |  | Sprint 3 |  | Visualization Navigation | MVP |  |  | 0
1.13.1 | Implement get_child_node_columns method |  |  | 3.5 | 4 | 4 | 4 | Tomek We | March 17, 2021, 6:53 PM | March 18, 2021, 12:32 PM | 4 | 128 | 28 | PP-454 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/48 | Sprint 2 | Added to sprint in Sprint 2 | Visualization Navigation | MVP | March 17, 2021, 6:53 PM | March 18, 2021, 12:32 PM | 4
1.13.2 | Implement find_child_nodes method in PandasAnalyticalService, for now without sorting | implement first version without sorting or handing other options (dry_run, pagination, match_prefix) | 1.13.1, 1.9.1 | 32 | 24 | 32 | 32 | Tomek We | March 18, 2021, 1:52 PM | March 18, 2021, 8:25 PM | 6.5 | 151 | 5 | PP-455 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/52 | Sprint 2 | Added to sprint in Sprint 2 | Visualization Navigation | MVP | March 18, 2021, 1:52 PM | March 18, 2021, 8:25 PM | 32
1.13.3 | Handle sorting by case_count in find_child_nodes, add case_count property in Node class | see design, also set case_count property in returned nodes, for now we can allow only sorting by 1 sort criteria | 1.13.2 | 8 | 4 | 12 | 12 | Tomek We | March 18, 2021, 7:36 PM | March 19, 2021, 12:10 PM | 5 | 95 | 3 | PP-456 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/53 | Sprint 2 | Added to sprint in Sprint 2 | Visualization Navigation | MVP | March 18, 2021, 7:36 PM | March 19, 2021, 12:10 PM | 12
1.13.4 | Handle sorting by options 2 - 7 in find_child_nodes | also handle sorting by multiple columns | 1.13.3 | 32 | 20 | 32 | 32 | Tomek We | March 22, 2021, 10:20 AM | March 23, 2021, 11:17 AM | 8 | 191 | 21 | PP-466 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/64 | Sprint 3 |  | Visualization Navigation | MVP | March 22, 2021, 10:20 AM | March 23, 2021, 11:17 AM | 32
1.13.5 | Handle sorting by rating in find_child_nodes |  | 1.13.4 | 6 | 8 | 10 | 10 | Tomek We | March 31, 2021, 5:17 PM | March 31, 2021, 6:40 PM | 1 | 34 | 1 | PP-467 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/98 | Sprint 3 |  | Visualization Navigation | MVP | March 31, 2021, 5:17 PM | March 31, 2021, 6:40 PM | 10
1.13.6 | Handle sorting by name in find_child_nodes |  | 1.13.4 | 24 | 24 | 32 | 32 | Tomek We | March 23, 2021, 11:20 AM | March 23, 2021, 12:22AM | 7 | 74 | 27 | PP-468 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/65, https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/69 | Sprint 3 | Planned in Sprint 4 | Visualization Navigation | MVP | March 23, 2021, 11:20 AM | March 23, 2021, 12:22AM | 32
1.13.7 | Handle pagination argument | Limit results to a specific page only | 1.13.2 | 3.5 | 4 | 4 | 4 | Tomek We | March 29, 2021, 3:28 PM | March 29, 2021, 4:20 PM | 1 | 39 | 1 | PP-469 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/90 | Sprint 3 |  | Visualization Navigation | MVP | March 29, 2021, 3:28 PM | March 29, 2021, 4:20 PM | 4
1.13.8 | Handle match_prefix argument |  | 1.13.6 | 8 | 4 | 8 | 8 | Tomek We | March 29, 2021, 12:34 PM | March 29, 2021, 1:22 PM | 1 | 31 | 0 | PP-470 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/88 | Sprint 3 | Planned in Sprint 4 | Visualization Navigation | MVP | March 29, 2021, 12:34 PM | March 29, 2021, 1:22 PM | 8
1.13.9 | Handle dry_run option | return int when dry_run = True | 1.13.2 | 8 | 4 | 8 | 8 | Michał | April 1, 2021, 12:31 PM | April 1, 2021, 2:07 PM | 2 | 48 | 7 | PP-471 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/102 | Sprint 3 |  | Visualization Navigation | MVP | April 1, 2021, 12:31 PM | April 1, 2021, 2:07 PM | 8
1.14 | Sorting and Pagination of Nodes | see design |  |  |  |  | 0 | [6 empty] | PP-472 |  | Sprint 5 |  | Visualization Navigation | MVP |  |  | 0
1.14.1 | Implement extract_sort_criteria method |  | 1.13.2 | 3 | 4 | 4 | 4 | Michał | March 25, 2021, 4:42 PM | March 26, 2021, 1:00 PM | 5 | 67 | 2 | PP-473 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/82 | Sprint 3 | Added to sprint in Sprint 3 | Visualization Navigation | MVP | March 25, 2021, 4:42 PM | March 26, 2021, 1:00 PM | 4
1.14.2 | Implement pack_nodes method, add is_packed() and unpack() methods to Node class | see design, make sure to check performance for ~40k nodes | 1.1.7 | 20 | 24 | 24 | 24 | Bartek | March 25, 2021, 12:45 PM | March 26, 2021, 9:20 AM | 8 | 90 | 12 | PP-474 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/79 | Sprint 3 | Added to sprint in Sprint 3 | Visualization Navigation | MVP | March 25, 2021, 12:45 PM | March 26, 2021, 9:20 AM | 24
1.14.3 | Implement extract_pagination method |  |  | 2 | 4 | 4 | 4 | Michał | March 26, 2021, 1:07 PM | March 26, 2021, 3:16 PM | 2 | 29 | 3 | PP-475 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/83 | Sprint 3 | Added to sprint in Sprint 3 | Visualization Navigation | MVP | March 26, 2021, 1:07 PM | March 26, 2021, 3:16 PM | 4
1.14.4 | Implement get_graph_orientation method |  |  | 3.5 | 4 | 4 | 4 | Michał | March 26, 2021, 5:53 PM | March 29, 2021, 9:17 AM | 4 | 245 | 6 | PP-476 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/86 | Sprint 3 | Added to sprint in Sprint 3 | Visualization Navigation | MVP | March 26, 2021, 5:53 PM | March 29, 2021, 9:17 AM | 4
1.14.5 | Implement extract_graph_pagination method |  | 1.14.3, 1.14.4 | 2 | 4 | 4 | 4 | Michał | March 29, 2021, 10:14 AM | March 29, 2021, 1:29 PM | 2.5 | 34 | 3 | PP-477 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/89 | Sprint 3 | Added to sprint in Sprint 3 | Visualization Navigation | MVP | March 29, 2021, 10:14 AM | March 29, 2021, 1:29 PM | 4
1.14.6 | Update group_nodes method in PandasAnalyticalService to allow a single packed node on either side (and up to 2 pack nodes in total) | see design | 1.14.2 | 24 | 32 | 32 | 32 | Maciej | March 26, 2021, 9:22 AM | April 2, 2021, 5:27 PM | 20.83 | 164 | 10 | PP-478 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/105 | Sprint 4 |  | Visualization Navigation | MVP | March 26, 2021, 9:22 AM | April 2, 2021, 5:27 PM | 32
1.14.11 | Handle single packed node on each side in calculate_benchmark method | see also 1.14.6 | 1.11.7, 1.14.6 | 12 | 20 | 26 | 12 | Manoj | April 16, 2021, 2:51 PM | April 19, 2021, 7:02 PM | 17.83 | 80 | 7 | PP-504 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/150 | Sprint 5 | Postponed, due to bug fixing: PP-1003 | Visualization Navigation | MVP | 2021-04-14 | 2021-04-16 | 12
1.14.7 | Implement decompose_packed_nodes decorator | Apply decorator to all group_nodes implementations (see design), make sure to run queries in parallel |  | 8 | 8 | 8 | 8 | Bartek | March 29, 2021, 3:01 PM | April 6, 2021, 1:01 PM | 7 | 134 | 8 | PP-479 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/92 | Sprint 4 |  | Visualization Navigation | MVP | March 29, 2021, 3:01 PM | April 6, 2021, 1:01 PM | 8
1.14.8 | Refactor make_abstract_graph_query to use find_child_nodes method | pass sorting criteria, see updated design, make sure to run lhs/rhs queries in parallel | 1.1.10, 1.13.3, 1.14.1 | 20 | 24 | 24 | 24 | Maciej | April 7, 2021, 3:41 PM | April 9, 2021, 1:28 PM | 22.58 | 176 | 65 | PP-480 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/118 | Sprint 4 |  | Visualization Navigation | MVP | April 7, 2021, 3:41 PM | April 9, 2021, 1:28 PM | 24
1.14.9 | Refactor AbstractGraphModel class and make_abstract_graph_model method to reflect design | make sure to pack nodes according to rules, see design | 1.14.1 - 1.14.5 | 12 | 16 | 16 | 16 | Michał | March 29, 2021, 2:21 PM | March 31, 2021, 6:16 PM | 16.5 | 235 | 66 | PP-481 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/97 | Sprint 3 | Added to sprint in Sprint 3 | Visualization Navigation | MVP | March 29, 2021, 2:21 PM | March 31, 2021, 6:16 PM | 16
1.14.12 | Implement make_abstract_graph_model special case to handle pagination (0,0) | see design | 1.14.9 | 1 |  |  | 1 | Maciej | April 6, 2021, 10:02 AM | April 6, 2021, 11:58 AM | 3.5 | 27 | 3 | PP-623 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/108 | Sprint 4 |  | Visualization Navigation | MVP | April 6, 2021, 10:02 AM | April 6, 2021, 11:58 AM | 1 | TRUE
1.14.10 | Update caseSummaryCollection endpoint to handle sorting and pagination | make sure sorting and pagination rules are processed, add unit tests for this functionality | 1.14.1 - 1.14.9 | 8 | 8 | 8 | 8 | Manoj | April 20, 2021, 5:01 PM | April 21, 2021, 10:30 AM | 8 | 97 | 10 | PP-482 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/156 | Sprint 5 | Postponed from Sprint 4 | Visualization Navigation | MVP | 2021-04-16 | 2021-04-19 | 8
1.14.13 | Update extract_node_statistics to handle packed nodes | update method to set rating = None for packed nodes, update failing tests | 1.1.13 | 2 |  |  | 2 | Manoj | April 23, 2021, 8:19 AM | April 23, 2021, 10:19 AM | 2.5 | 20 | 0 | PP-1302 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/172 | Sprint 5 |  | Visualization Navigation | MVP |  |  | 2
1.15 | allDatasets endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-483 |  | Sprint 4 |  | Dataset upload and management | MVP |  |  | 0
1.15.1 | define the DatasetDetails class |  |  | 2 | 1 | 4 | 4 | Tomek We | March 24, 2021, 5:51 PM | March 24, 2021, 6:08 PM | 1 | 15 | 0 | PP-505 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/73 | Sprint 3 | Added to sprint in Sprint 3 | Dataset upload and management | MVP | March 24, 2021, 5:51 PM | March 24, 2021, 6:08 PM | 4
1.15.2 | Implement get_all_datasets method in the DatasetService class | order by upload_time descending | DM | 12 | 12 | 16 | 16 | Kamil C | April 14, 2021, 12:02 PM | April 16, 2021, 8:47 AM | 10.5 | 118 | 0.5 | PP-484 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/139 | Sprint 4 | Moved from Sprint 5 | Dataset upload and management | MVP |  |  | 16
1.15.3 | Implement format_all_datasets_response method |  | 1.15.1 | 1.5 | 1 | 1 | 1 | Tomek We | March 25, 2021, 5:16 PM | March 25, 2021, 7:42 PM | 2.5 | 1024 | 871 | PP-506 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/80 | Sprint 3 | Added to sprint in Sprint 3 | Dataset upload and management | MVP | March 25, 2021, 5:16 PM | March 25, 2021, 7:42 PM | 1 | TRUE
1.15.4 | Implement DummyDatasetService | This is to run P2 application without the actual DM implementation yet, do not implement any unit tests for this class |  | 3.5 | 8 | 8 | 8 | Tomek We | March 25, 2021, 11:22 AM | March 25, 2021, 3:22 PM | 4 | 141 | 5 | PP-518 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/76 | Sprint 3 | Added to sprint in Sprint 3 | Dataset upload and management | MVP | March 25, 2021, 11:22 AM | March 25, 2021, 3:22 PM | 8
1.15.5 | Implement allDatasets endpoint | use DummyDatasetService for now | 1.15.3, 1.15.4 | 3 | 4 | 4 | 4 | Tomek We | March 26, 2021, 11:43 AM | March 26, 2021, 4:41 PM | 4 | 131 | 9 | PP-507 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/85 | Sprint 3 | Added to sprint in Sprint 3 | Dataset upload and management | MVP | March 26, 2021, 11:43 AM | March 26, 2021, 4:41 PM | 4
1.16 | getLdsDatasetsIds endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-508 |  | Sprint 3 |  | Dataset upload and management | MVP |  |  | 0
1.16.1 | Implement getLDSDatasetsIDs endpoint | use mock DatasetService for now |  | 3 | 4 | 4 | 4 | Tomek We | March 29, 2021, 10:23 AM | March 29, 2021, 11:14 AM | 1 | 37 | 3 | PP-509 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/87 | Sprint 3 | Added to sprint in Sprint 3 | Dataset upload and management | MVP | March 29, 2021, 10:23 AM | March 29, 2021, 11:14 AM | 4
1.17 | dataset endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-510 |  | Sprint 7 |  | Dataset upload and management | MVP |  |  | 0
1.17.1 | Implement get_datasets method in DatasetService | 1.15.2 | DM | 3.5 | 4 | 4 | 4 | Kamil C | April 14, 2021, 12:02 PM | April 16, 2021, 8:47 AM | 0 | 118 | 0.5 | PP-511 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/139 | Sprint 4 | Moved from Sprint 5, done together with 1.15.2 | Dataset upload and management | MVP |  |  | 4
1.17.2 | Implement get_pipeline_statistics method in DatasetService | connect to the Pipeline Server | O2Grouper | 24 | 24 | 24 | 24 | Manoj | May 25, 2021 11:48:02 | May 27, 2021 05:54:50 | 14.5 | 122 | 3 | PP-512 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/320 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 24
1.17.3 | Implement dataset endpoint |  | 1.17.1, 1.17.2 | 4 | 8 | 8 | 8 | Manoj | May 26, 2021 11:02:02 | May 27, 2021 11:03:57 | 6.5833 | 70 | 1 | PP-513 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/323 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 8
1.18 | caseStatistics endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-514 |  | Sprint 5 |  | Visualization Generation | MVP |  |  | 0
1.18.1 | Implement get_case_statistics in PandasAnalyticalService | Handle sorting and limitation of results | 1.1.8 | 24 | 24 | 32 | 32 | Maciej | April 9, 2021, 4:01 PM | April 19, 2021, 2:48 PM | 32 | 327 | 24 | PP-519 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/147 | Sprint 5 | Started in Sprint 4 | Visualization Generation | MVP | April 9, 2021, 4:01 PM | 2021-04-15 | 32
1.18.2 | Implement get_serviceline_benchmarks in PandasAnalyticalService | similar to 1.19.2 | 1.1.8 | 12 | 8 | 16 | 16 | Manoj | Apr 13, 2021 09:16:40 | Apr 15, 2021 06:14:18 | 15.7 | 45 | 4 | PP-520 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/135 | Sprint 4 |  | Visualization Generation | MVP | 2021-04-13 | 2021-04-15 | 16
1.18.3 | Implement join_serviceline_benchmarks | similar to 1.19.3 |  | 3 | 3 | 4 | 4 | Manoj | April 12, 2021, 1:20 PM | April 12, 2021, 1:21 PM | 5 | 76 | 1 | PP-521 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/126 | Sprint 4 |  | Visualization Generation | MVP | April 12, 2021, 1:20 PM | 2021-04-12 | 4
1.18.4 | Implement format_case_statistics | Prepare synthetic data frames for unit tests (without and with benchmark values) |  | 5 | 3 | 8 | 8 | Manoj | April 12, 2021, 4:55 PM | April 12, 2021, 4:55 PM | 5 | 147 | 4 | PP-522 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/127 | Sprint 4 |  | Visualization Generation | MVP | 2021-04-12 | 2021-04-13 | 8
1.18.5 | Implement caseStatistics endpoint | see design, make sure to run queries in parallel | 1.18.1 - 1.18.4, 1.21 | 17 | 12 | 20 | 20 | Maciej | April 20, 2021, 11:06 AM | April 21, 2021, 4:13 PM | 13.33 | 236 | 78 | PP-523 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/159 | Sprint 5 | Postponed from Sprint 4 | Visualization Generation | MVP |  |  | 20
1.19 | caseSummaryCollectionMapView endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-515 |  | Sprint 5 |  | Visualization Generation | MVP |  |  | 0
1.19.1 | Implement get_map_view_entity_statistics in PandasAnalyticalService |  | 1.1.8 | 16 | 16 | 20 | 20 | Michał | April 14, 2021, 6:14 PM | April 19, 2021, 1:45 PM | 14.5 | 111 | 6 | PP-524 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/148 | Sprint 5 | Started in Sprint 4 | Visualization Generation | MVP |  |  | 20
1.19.2 | Implement get_careunit_benchmarks in PandasAnalyticalService |  | 1.1.8 | 14 | 12 | 20 | 20 | Kamil C | April 20, 2021, 2:33 PM | April 21, 2021, 5:02 PM | 7 | 70 | 4 | PP-525 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/161 | Sprint 5 |  | Visualization Generation | MVP |  |  | 20
1.19.3 | Implement join_careunit_benchmarks | Prepare sythetic data frames for the unit test |  | 3 | 3 | 4 | 4 | Kamil C, Manoj | April 14, 2021, 5:14 PM | April 15, 2021, 2:36 PM | 9 | 166 | 94 | PP-526 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/168 https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/169 | Sprint 5 |  | Visualization Generation | MVP |  |  | 4 | TRUE
1.19.4 | Implement format_entity_statistics | Prepare synthetic data frames for unit tests (without and with benchmark values) |  | 4 | 3 | 4 | 4 | Manoj | April 15, 2021, 5:11 PM | April 16, 2021, 9:24 AM | 7 | 117 | 3 | PP-527 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/142 | Sprint 5 |  | Visualization Generation | MVP |  |  | 4
1.19.5 | Implement caseSummaryCollectionMapView endpoint | see design, make sure to run queries in parallel | 1.19.1 - 1.19.4 | 16 | 12 | 12 | 12 | Kamil C | Apr 23, 2021 06:10:35 | Apr 26, 2021 14:50:34 | 9 | 181 | 15 | PP-528 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/173 | Sprint 5 |  | Visualization Generation | MVP |  |  | 12
1.20 | Error Handling | see design |  |  |  |  | 0 | [6 empty] | PP-529 |  | Sprint 7 |  | System | MVP |  |  | 0
1.20.1 | Define ApplicationError base class and app_error_class decorator | just copy from the design and add unit tests |  | 3 |  | 2 | 2 | Manoj | May 18, 2021 13:06:03 | May 19, 2021 07:56:04 | 3.5 | 92 | 0 | PP-530 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/283 | Sprint 7 |  | System | MVP |  |  | 2
1.20.2 | Review application's code, find all raise statements and throw proper errors | Declare proper exception classes, define error variables, use DatasetNotFound as a model example, place all errors in the errors.py module | 1.1 - 1.19 | 28 |  | 36 | 36 | Manoj | May 24, 2021 06:03:32 | May 24, 2021 07:15:33 | 23.1667 | 1045 | 182 | PP-531 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/307 | Sprint 7 |  | System | MVP |  |  | 36
1.20.3 | Implement @handle_errors decorator and apply to all graph-ql endpoints (resolve_ methods) |  | 1.20.1 | 3 |  |  | 3 | Manoj | May 24, 2021 07:41:28 | May 24, 2021 11:01:20 | 3.0833 | 112 | 37 | PP-1421 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/310 | Sprint 7 |  | System | MVP |  |  | 3
1.20.4 | Add list of error codes and descriptions to technical design | This task is development driven |  | 6 |  | 4 | 4 | Manoj | May 24, 2021 07:20:15 | May 25, 2021 07:42:57 | 3.25 |  |  | PP-532 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/310 | Sprint 7 | Merged together with 1.20.3 | System | MVP |  |  | 4
1.21 | Backend Configuration | see design |  |  |  |  | 0 | [6 empty] | PP-533 |  | Sprint 4 |  | System | MVP |  |  | 0
1.21.1 | Implement AppConfig singleton | Define ConfigVariables and defaults, validate configuration on first access to AppConfig |  | 12.5 |  | 16 | 12.5 | Tomek We | April 12, 2021, 12:16 PM | April 12, 2021, 5:40 PM | 7 | 233 | 22 | PP-534 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/128 | Sprint 4 | Added to sprint in Sprint 4 | System | MVP | April 12, 2021, 12:16 PM | 14/04/2021 | 12.5
1.21.2 | Extend AppConfig, add additional configuratoin varialbes in compliance with the design | add variables: DB_ENGINE, DB_NAME, DB_USER, DB_PASS, DB_HOST, DB_PORT, FILE_US_COUNTY_2018_GEO, FILE_US_GEO_JSON_2018, FILE_ENCODING, AUTH0_API_PATH, AUTH0_CLIENT_ID, AUTH0_CLIENT_SECRET, AUTH0_AUDIENCE |  | 3 |  |  | 3 | Manoj | May 27, 2021 11:06:52 | May 31, 2021 13:45:22 | 3 | 70 | 45 | PP-1423 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/326 | Sprint 7 |  | System | MVP |  |  | 3
1.21.3 | Handle BACKEND_TYPE=MEMSQL, see design | Current implementation uses undocumented variable IN_MEMORY_DB but we should use BACKEND_TYPE instead |  | 3 |  |  | 3 | Manoj | May 28, 2021 08:21:26 | May 31, 2021 08:29:10 | 3.25 | 5 | 10 | PP-1424 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/337 | Sprint 7 |  | System | MVP |  |  | 3
1.21.4 | Validate AWS_ variables, adjust variable names to latest design | Either AWS_SECRET_KEY_ID or AWS_SESSION_TOKEN should be set in RELEASE mode |  | 1.5 |  |  | 1.5 | Manoj | May 28, 2021 05:56:29 | May 31, 2021 11:13:55 | 2.4167 | 33 | 19 | PP-1425 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/338 | Sprint 7 |  | System | MVP |  |  | 1.5
1.21.5 | Add DJANGO_SECRET_KEY variable to configuration | Generate random value when DEPLOYMENT_TYPE=DEBUG, remove hard-coded SECRET_KEY value from P2Backend.settings and use the one from configuration |  | 3.5 |  |  | 3.5 | Manoj | May 28, 2021 05:56:09 | May 31, 2021 08:07:37 | 3.8333 | 15 | 6 | PP-1426 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/334 | Sprint 7 |  | System | MVP |  |  | 3.5
1.21.6 | Set CORS_ORIGIN_ALLOW_ALL = True in django settings | Update djano configuration, see P2-v2 implementation as example |  | 2 |  |  | 2 | Adrian Z | June 4, 2021, 9:33 AM | June 4, 2021, 9:41 AM | 1 | 16 | 0 | PP-1533 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/358 | Sprint 8 |  | System | MVP |  |  | 2
1.22 | Data Suppression (LDS-11 rule) | see design |  |  |  |  | 0 | [6 empty] | PP-537 |  | Sprint 7 |  | LDS suppression rule-11 | MVP |  |  | 0
1.22.1 | Implement get_aggregation_level method | see design |  | 3 | 2 |  | 3 | Aleksandra | May 24, 2021 06:03:51 | May 25, 2021 09:17:12 | 2.5 | 48 | 1 | PP-1016 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/315 | Sprint 7 |  | LDS suppression rule-11 | MVP |  |  | 3
1.22.2 | Add LDS_SUPPRESSION_ENABLED flag to AppConfig | allow False only in DEBUG deployment mode |  | 2 | 2 |  | 2 | Aleksandra | May 24, 2021 12:40:56 | May 25, 2021 09:17:30 | 4 | 81 | 2 | PP-1017 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/316 | Sprint 7 |  | LDS suppression rule-11 | MVP |  |  | 2
1.22.3 | Handle __lds_suppress_aggregation_level member in select_from_relations method from SQLAnalyticalService | implement suppression logic, read tutorial | 1.22.2, 1.24.6 | 28 | 32 |  | 28 | Aleksandra | May 24, 2021 17:30:50 | May 27, 2021 14:40:19 | 29.5 | 132 | 60 | PP-1018 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/330 | Sprint 7 |  | LDS suppression rule-11 | MVP |  |  | 28
1.22.4 | Modify open method in SQLAnalyticsProvider | pass lds_tables argument to SQLAnalyticalService and forward lds_suppress_aggregation_level, see design | 1.24.9 | 3 | 2 |  | 3 | Tomek We | May 26, 2021 09:49:26 | May 26, 2021 15:27:31 | 2 |  |  | PP-1019 | - | Sprint 7 | Already implemented | LDS suppression rule-11 | MVP |  |  | 3
1.22.5 | Integrate LDS suppression rules with the caseSummaryCollection endpoint | use get_aggregation_level method and pass its result to open in the AnalyticsProvider, implement unit tests to check if proper aggregation level is passed for various queries, check LDS_SUPPRESSION_ENABLED flag |  | 6 | 4 |  | 6 | Maciej | May 31, 2021 14:51:31 | Jun 07, 2021 13:58:00 | 23.4167 | 194 | 152 | PP-1020 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/370 | Sprint 8 |  | LDS suppression rule-11 | MVP |  |  | 6 | TRUE
1.22.6 | Integrate with other endpoints | Review all places where the method "open" from AnalyticsProvider is being called, pass lds_suppress_aggregation_level argument where it makes sense |  | 12 | 12 |  | 12 | Manoj | Jun 01, 2021 05:03:52 | Jun 01, 2021 14:05:49 | 8 | 34 | 11 | PP-1021 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/342 | Sprint 8 |  | LDS suppression rule-11 | MVP |  |  | 12
1.22.7 | Implement is_suppressed method in SQLAnalyticalService | define new method in AnalyticalService base class, always return False from the PandasAnalyticalService |  | 1.5 | 2 |  | 1.5 | Aleksandra | May 27, 2021 13:15:43 | May 27, 2021 13:46:34 | 1 | 66 | 0 | PP-1022 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/328 | Sprint 7 |  | LDS suppression rule-11 | MVP |  |  | 1.5
1.22.8 | Return isSuppressed flag in caseSummaryCollection result | see design |  | 3 | 4 |  | 3 | Maciej | Jun 07, 2021 13:56:47 | Jun 07, 2021 13:58:22 | 0.51667 | 194 | 152 | PP-1023 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/370 | Sprint 8 |  | LDS suppression rule-11 | MVP |  |  | 3
1.23 | User Dataset Upload | see design | [11 empty] | PP-538 |  | Sprint 7 |  | Dataset upload and management | MVP |  |  | 0
1.23.16 | Add PIPELINE_SERVER_URL variable to AppConfig | only required in RELEASE deployments | 1.21 | 1 |  |  | 1 | Kamil C | Apr 26, 2021 07:56:13 | Apr 26, 2021 14:50:02 | 1 | 9 | 3 | PP-1024 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/176 | Sprint 5 |  | Dataset upload and management | MVP |  |  | 1
1.23.1 | Implement add_uploaded_file in Repository class | see design, define repository data model (use Django), add Repository instance to context (available to endpoint resolvers) | 1.23.16 | 10 |  |  | 10 | Kamil C | Apr 26, 2021 09:17:30 | Apr 27, 2021 12:08:14 | 10 | 223 | 3 | PP-942 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/179 | Sprint 5 |  | Dataset upload and management | MVP |  |  | 10
1.23.2 | Implement set_error method in Repository class |  | 1.23.1 | 1.5 |  |  | 1.5 | Kamil C | Apr 27, 2021 11:41:01 | Apr 27, 2021 12:07:47 | 0 |  |  | PP-943 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/179 | Sprint 5 | Done and reported with 1.23.1 | Dataset upload and management | MVP |  |  | 1.5
1.23.3 | Implement set_s3_url method in Repository class |  | 1.23.1 | 1.5 |  |  | 1.5 | Kamil C | Apr 27, 2021 11:41:08 | Apr 27, 2021 12:09:07 | 0 |  |  | PP-944 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/179 | Sprint 5 | Done and reported with 1.23.1 | Dataset upload and management | MVP |  |  | 1.5
1.23.4 | Implement set_pipeline_id in Repository class |  | 1.23.1 | 1.5 |  |  | 1.5 | Kamil C | Apr 27, 2021 11:41:15 | Apr 27, 2021 12:08:47 | 0 |  |  | PP-945 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/179 | Sprint 5 | Done and reported with 1.23.1 | Dataset upload and management | MVP |  |  | 1.5
1.23.5 | Implement AppProcessPool class | just copy code from the design |  | 1 |  |  | 1 | Kamil C | Apr 27, 2021 11:53:00 | Apr 27, 2021 13:18:28 | 1 | 19 | 0 | PP-1025 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/181 | Sprint 5 |  | Dataset upload and management | MVP |  |  | 1
1.23.6.1 | Implement parse_aws_host_region method | see design |  | 2 |  |  | 2 | Kamil C | Apr 27, 2021 14:22:42 | Apr 28, 2021 09:43:50 | 1 | 76 | 0.5 | PP-1284 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/183 | Sprint 5 |  | Dataset upload and management | MVP |  |  | 2
1.23.6.2 | Implement generate_aws_gateway_header method | just copy code from example notebook |  | 1 |  |  | 1 | Kamil C | Apr 27, 2021 14:22:14 | Apr 28, 2021 09:43:21 | 0.5 | 76 | 0.5 | PP-1285 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/183 | Sprint 5 |  | Dataset upload and management | MVP |  |  | 1
1.23.6 | Implement start_o2_grouper method | see design | 1.21, 1.23.6.1 - 2 | 3 |  |  | 3 | Kamil C | Apr 29, 2021 13:33:46 | May 04, 2021 14:12:44 | 7.5 | 214 | 149 | PP-1026 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/201 | Sprint 6 |  | Dataset upload and management | MVP |  |  | 3 | 2.5
1.23.7 | Implement upload_to_s3_and_start_o2_grouper method | see design | 1.23.1 - 1.23.6 | 3.5 |  |  | 3.5 | Kamil C | May 04, 2021 13:31:54 | May 05, 2021 07:35:02 | 2 | 37 | 7 | PP-1027 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/204 | Sprint 6 |  | Dataset upload and management | MVP |  |  | 3.5 | 0.57143
1.23.8 | Implement sendfile/upload_file endpoint | copy from P2 v2 backend, run upload_to_s3_and_start_o2_grouper form in a separate process task and return immediately | 1.23.7 | 10 |  |  | 10 | Kamil C | May 05, 2021 06:45:29 | May 06, 2021 09:15:11 | 8.5 | 237 | 63 | PP-1028 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/216 | Sprint 6 |  | Dataset upload and management | MVP |  |  | 10 | 0.85
1.23.9 | Implement has_s3_put_object_permission method | see design | 1.21 | 3 |  |  | 3 | Kamil C | May 19, 2021 08:20:39 | May 19, 2021 08:53:59 | 1.5833 | 155 | 125 | PP-1029 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/284 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 3
1.23.10 | Validate s3:PutObject permission on start-up (in RELEASE deployment mode only) |  | 1.23.9 | 2.5 |  |  | 2.5 | Kamil C | May 19, 2021 10:44:32 | May 19, 2021 11:25:38 | 2 | 24 | 2 | PP-1030 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/291 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 2.5
1.23.11 | Implement get_user_uploaded_files method in Repository class | see design | 1.23.1 | 3 |  |  | 3 | Kamil C | May 19, 2021 10:58:08 | May 19, 2021 13:09:32 | 1.5833 | 47 | 2 | PP-1031 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/292 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 3
1.23.12 | Update format_all_datasets_response method to take into account upload_status field in DatasetDetails (Validation, Failed or Finished) |  |  | 3 |  |  | 3 | Kamil C | May 19, 2021 12:51:49 | May 21, 2021 10:49:04 | 1.0833 | 11 | 9 | PP-1032 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/302 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 3
1.23.13 | Update allDatasets endpoint to include currently processed and failed processing files | see design | 1.23.11 | 4.5 |  |  | 4.5 | Kamil C | May 21, 2021 11:19:02 | May 21, 2021 12:53:07 | 2 | 87 | 12 | PP-1033 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/304 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 4.5
1.23.14 | Implement get_uploaded_file in Repository | see design | 1.23.1 | 3 |  |  | 3 | Kamil C | May 19, 2021 14:26:07 | May 20, 2021 08:42:53 | 1.5833 | 32 | 1 | PP-1034 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/293 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 3
1.23.15 | Update get_datasets method in DatasetService | handle uploaded file ids, see design | 1.23.14, 1.17.2 | 6 | 6 |  | 6 | Kamil C, Adrian Z | Jun 16, 2021 10:46:01 | Jun 17, 2021 10:00:35 | 6.5 |  |  | PP-1035 |  | Sprint 9 |  | Dataset upload and management | MVP |  |  | 6
1.23.16 | Update boto3 client usage | Review boto3.client usage, remove AWS connection arguments since they will be found automatically in the environment variables. See tutorial (#5) | 1.21.4 | 1 | 1 |  | 1 | Kamil C | May 21, 2021, 4:08 PM | May 21, 2021, 4:10 PM | 1 | 19 | 10 | PP-1379 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/305 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 1
1.23.17 | Update has_s3_permissions method to match design | Previous name was has_s3_put_object_permission |  | 1 | 1 |  | 1 | Kamil C | May 24, 2021, 1:34 PM | May 24, 2021, 1:57 PM | 0.75 | 10 | 15 | PP-1427 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/309 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 1
1.23.18 | Implement remove_old_files method, see design | Run method with each file upload |  | 3 | 3 |  | 3 | Kamil C | May 24, 2021, 1:34 PM | May 24, 2021, 1:57 PM | 1 | 16 | 0 | PP-1428 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/311 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 3
1.23.19 | Implement find_files method in Repository class | see design |  | 2 | 2 |  | 2 | Kamil C | May 24, 2021 16:31:36 | May 26, 2021 08:47:38 | 1.5 | 49 | 16 | PP-1429 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/314 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 2
1.23.20 | Implement cleanup_s3_buckets method | see design, run method with every user file upload | 1.17.2, 1.23.19 | 6 | 6 |  | 6 | Adrian Z | Jun 17, 2021 08:20:09 | Jun 17, 2021 13:00:49 | 4.3333 |  |  | PP-1430 |  | Sprint 9 |  | Dataset upload and management | MVP |  |  | 6
1.24 | Snowflake Integration | see design | [11 empty] | PP-539 |  | Sprint 7 |  | Visualization Generation | MVP |  |  | 0
1.24.1 | Implement SQLConnectionFactory and SQLConnection | implement connect and close methods, define and use connection configuration variables | 1.21.1 | 8 | 6 |  | 8 | Aleksandra | April 20, 2021, 10:34 AM | April 20, 2021, 6:49 PM | 13.5 | 182 | 3 | PP-946 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/155 | Sprint 5 |  | Visualization Generation | MVP |  |  | 8
1.24.2 | Implement get_sql_column method | see design |  | 2.5 | 2 |  | 2.5 | Aleksandra | Apr 20, 2021 16:54:31 | Apr 21, 2021 11:28:51 | 3 | 55 | 0 | PP-947 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/158 | Sprint 5 |  | Visualization Generation | MVP |  |  | 2.5
1.24.3 | Implement make_sql_filter (for ColumnFilter) method | see design | 1.24.2 | 4 | 4 |  | 4 | Aleksandra | Apr 21, 2021 11:29:31 | Apr 21, 2021 14:51:31 | 1 | 37 | 3 | PP-948 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/163 | Sprint 5 |  | Visualization Generation | MVP |  |  | 4
1.24.4 | Implement make_sql_filter (for RangeFilter) method | make sure to handle special "fiscal_date" column name | 1.24.2 | 4 | 4 |  | 4 | Aleksandra | Apr 21, 2021 14:52:43 | Apr 21, 2021 16:41:49 | 5 | 84 | 10 | PP-949 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/166 | Sprint 5 |  | Visualization Generation | MVP |  |  | 4
1.24.5 | Implement make_sql_distance_filter method | or_ combine from AC and PAC entities |  | 4 | 4 |  | 4 | Aleksandra, Maciej | April 21, 2021, 5:49 PM |  | 9 | 58 | 3 | PP-950 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/174 | Sprint 5 | Aleksandra started, because of unavailability, Maciej took care of task | Visualization Generation | MVP |  |  | 4 | TRUE
1.24.6 | Implement select_from_relations in SQLAnalyticalService | define SQLAnalyticalService class, handle unions, joined tables and additional columns, raise error from unimplemented interface methods, ignore lds_suppress_aggregation_level argument | 1.24.3 - 1.24.5 | 14 | 12 |  | 14 | Maciej | Apr 23, 2021 14:04:13 | Apr 29, 2021 10:43:12 | 28.1667 | 404 | 46 | PP-951 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/188 | Sprint 5 |  | Visualization Generation | MVP |  |  | 14 | TRUE
1.24.7 | Implement DataCommons class | see design, implement validation of all datasets | 1.24.1 | 18 | 12 |  | 18 | Michał | Apr 27, 2021 13:29:25 | May 05, 2021 10:27:12 | 30.6667 | 479 | 38 | PP-952 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/208 | Sprint 6 |  | Visualization Generation | MVP |  |  | 18 | 1.7037
1.24.8 | Implement get_dataset_details method in DatasetService | see design | DM, 1.17.2 | 12 |  |  | 12 | Kamil C | Apr 26, 2021 12:58:02 | May 12, 2021 13:52:09 | 2 | 83 | 14 | PP-953 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/246 | Sprint 6 |  | Visualization Generation | MVP |  |  | 12 | 0.16667
1.24.9 | Implement SQLAnalyticsProvider | see design, always query DatasetService, make sure to cache Tables, use mocked DatasetService for tests | 1.24.1 | 12 | 12 |  | 12 | Kamil C | Apr 27, 2021 06:47:47 | May 14, 2021 09:00:26 | 34 | 219 | 99 | PP-954 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/259 | Sprint 6 |  | Visualization Generation | MVP |  |  | 12 | 2.8333
1.24.10 | Handle backend type selection from configuration | Check BACKEND_TYPE configuration variable to create either PandasAnalyticsProvider and mocked DatasetService or SQLAnalyticsProvider and real DatasetService | 1.24.1 - 1.24.7, 1.24.9 | 10 | 6 |  | 10 | Kamil C | May 06, 2021 08:56:07 | May 07, 2021 12:17:03 | 9 | 50 | 15 | PP-955 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/219 | Sprint 6 |  | Visualization Generation | MVP |  |  | 10 | 0.9
1.24.11 | Implement find_child_nodes in SQLAnalyticalService | handle all arguments, use pandas implementation as example | 1.13, 1.24.6 | 24 | 16 |  | 24 | Manoj, Maciej | May 07, 2021 06:45:40 | May 12, 2021 03:55:36 | 43.8333 | 511 | 219 | PP-956 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/267 | Sprint 6 |  | Visualization Generation | MVP |  |  | 24 | 1.8264
1.24.12 | Implement group_nodes in SQLAnalyticalService | see pandas implementation as example | 1.14.6, 1.24.6 | 32 | 32 |  | 32 | Maciej | Apr 29, 2021 12:20:11 | May 12, 2021 08:05:42 | 46.6667 | 750 | 475 | PP-957 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/244 | Sprint 6 |  | Visualization Generation | MVP |  |  | 32 | 1.4583
1.24.13 | Implement get_entity_details in SQLAnalyticalService |  | 1.24.6 | 3 | 3 |  | 3 | Manoj | Apr 29, 2021 11:24:19 | May 13, 2021 03:44:44 | 4 | 60 | 41 | PP-958 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/251 https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/231 | Sprint 6 |  | Visualization Generation | MVP |  |  | 3 | 1.3333
1.24.14 | Implement get_entity_counts in SQLAnalyticalService |  | 1.24.6 | 12 | 8 |  | 12 | Manoj | May 12, 2021 15:17:53 | May 13, 2021 11:49:06 | 9 | 89 | 83 | PP-959 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/256 | Sprint 6 |  | Visualization Generation | MVP |  |  | 12 | 0.75
1.24.15 | Implement get_lob_statistics in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | Manoj | May 13, 2021 12:34:09 | May 14, 2021 02:05:39 | 3 | 21 | 1 | PP-960 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/258 | Sprint 6 |  | Visualization Generation | MVP |  |  | 3 | 1
1.24.16 | Implement get_quarterly_statistics in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | Manoj | May 03, 2021 15:08:37 | May 03, 2021 15:08:42 | 8 | 30 | 1 | PP-961 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/194 | Sprint 6 |  | Visualization Generation | MVP |  |  | 3 | 2.6667
1.24.17 | Implement get_careunit_statistics in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | Manoj | May 04, 2021 11:07:27 | May 04, 2021 11:07:32 | 3.5 | 12 | 2 | PP-962 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/200 | Sprint 6 |  | Visualization Generation | MVP |  |  | 3 | 1.1667
1.24.18 | Implement get_diagnose_statistics in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | Manoj | May 04, 2021 15:18:20 | May 05, 2021 06:55:05 | 4 | 72 | 2 | PP-963 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/205 | Sprint 6 |  | Visualization Generation | MVP |  |  | 3 | 1.3333
1.24.19 | Implement find_fiscal_quarters in SQLAnalyticalService |  | 1.24.6 | 2 | 2 |  | 2 | Manoj | May 05, 2021 08:39:27 | May 05, 2021 09:50:21 | 2.5 | 25 | 1 | PP-964 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/206 | Sprint 6 |  | Visualization Generation | MVP |  |  | 2 | 1.25
1.24.20 | Implement get_time_range in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | Manoj | May 05, 2021 09:54:17 | May 05, 2021 13:56:11 | 4.5 | 34 | 1 | PP-965 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/211 | Sprint 6 |  | Visualization Generation | MVP |  |  | 3 | 1.5
1.24.21 | Implement calculate_benchmark in SQLAnalyticalService | see pandas implementation as example | 1.11.7, 1.24.6 | 32 | 32 |  | 32 | Aleksandra | May 04, 2021 07:51:01 | May 11, 2021 13:24:32 | 39 | 594 | 247 | PP-966 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/228 | Sprint 6 |  | Visualization Generation | MVP |  |  | 32 | 1.2188
1.24.22 | Implement get_entity_address in SQLAnalyticalService |  | 1.24.6 | 4 | 2 |  | 4 | Tomek We | May 12, 2021 15:41:54 | May 13, 2021 15:16:08 | 6.5 | 78 | 1 | PP-967 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/257 | Sprint 6 |  | Visualization Generation | MVP |  |  | 4 | 1.625
1.24.23 | Implement get_entity_quality in SQLAnalyticalService |  | 1.24.6 | 6 | 8 |  | 6 | Tomek We | May 13, 2021 14:50:16 | May 17, 2021 09:28:27 | 7.5 | 249 | 229 | PP-968 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/269 | Sprint 7 |  | Visualization Generation | MVP |  |  | 6
1.24.24 | Implement get_facility_details in SQLAnalyticalService |  | 1.24.6 | 6 | 8 |  | 6 | Tomek We | May 18, 2021 14:11:14 | May 21, 2021 07:43:30 | 12.5 | 318 | 127 | PP-969 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/298 | Sprint 7 |  | Visualization Generation | MVP |  |  | 6 | TRUE
1.24.25 | Implement get_entity_staffing in SQLAnalyticalService |  | 1.24.6 | 4 | 2 |  | 4 | Tomek We | May 21, 2021 10:57:57 | May 27, 2021 09:30:00 | 5.5 | 87 | 81 | PP-970 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/306 | Sprint 7 |  | Visualization Generation | MVP |  |  | 4
1.24.32 | Implement get_service_unit_ids method in DataCommons | see design, make sure to cache results | 1.24.7 | 4 | 4 |  | 4 | Michał | May 05, 2021 11:46:40 | May 06, 2021 07:36:36 | 3.5 | 35 | 15 | PP-971 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/214 | Sprint 6 |  | Visualization Generation | MVP |  |  | 4 | 0.875
1.24.33 | Implement get_service_line in SQLAnalyticalService | use get_service_unit_ids and resolve the ID mapping from its result | 1.24.6 | 1.5 | 1.5 |  | 1.5 | Michał | May 06, 2021 12:25:26 | May 12, 2021 07:24:49 | 1 | 44 | 10 | PP-972 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/220 | Sprint 6 |  | Visualization Generation | MVP |  |  | 1.5 | 0.66667
1.24.34 | Implement get_clinical_episode in SQLAnalyticalService | use get_service_unit_ids and resolve the ID mapping from its result | 1.24.6 | 1.5 | 1.5 |  | 1.5 | Michał | May 06, 2021 14:02:43 | May 07, 2021 08:53:22 | 0.5 | 18 | 3 | PP-973 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/222 | Sprint 6 |  | Visualization Generation | MVP |  |  | 1.5 | 0.33333
1.24.35 | Implement get_map_view_entity_statistics in SQLAnalyticalService | see pandas implementation as example | 1.19.1, 1.24.6 | 12 | 14 |  | 12 | Michał | May 13, 2021 10:52:38 | May 14, 2021 15:28:42 | 14.5 | 139 | 14 | PP-974 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/268 | Sprint 7 |  | Visualization Generation | MVP |  |  | 12
1.24.36 | Implement get_case_statistics in SQLAnalyticalService | see pandas implementation as example | 1.18.1, 1.24.6 | 12 | 12 |  | 12 | Michał | May 31, 2021 08:48:11 | Jun 02, 2021 13:42:36 | 19 |  |  | PP-975 |  | Sprint 8 |  | Visualization Generation | MVP |  |  | 12
1.24.37 | Implement get_serviceline_benchmarks in SQLAnalyticalService | see pandas implementation as example | 1.18.2, 1.24.6 | 12 | 8 |  | 12 | Aleksandra | May 05, 2021 13:47:43 | May 21, 2021 08:32:42 | 6.5 | 226 | 32 | PP-976 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/300 | Sprint 7 |  | Visualization Generation | MVP |  |  | 12
1.24.38 | Implement get_careunit_benchmarks in SQLAnalyticalService | see pandas and 1.24.30 implementation as example | 1.24.6 | 12 | 8 |  | 12 | Tomek We | May 24, 2021 09:04:16 | May 24, 2021 16:06:55 | 4 | 77 | 54 | PP-977 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/313 | Sprint 7 |  | Visualization Generation | MVP |  |  | 12
1.24.39 | Implement get_all_service_line_ids in SQLAnalyticalService | use get_service_unit_ids method result from DataCommons | 1.24.32 | 2.5 | 2 |  | 2.5 | Aleksandra | May 14, 2021 08:53:59 | May 19, 2021 10:54:29 | 5 | 13 | 4 | PP-978 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/285 | Sprint 7 |  | Visualization Generation | MVP |  |  | 2.5
1.24.40 | Implement get_unique_drgs in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | Aleksandra | May 17, 2021 09:23:55 | May 19, 2021 11:16:02 | 5 | 53 | 3 | PP-979 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/286 | Sprint 7 |  | Visualization Generation | MVP |  |  | 3
1.24.41 | Extend make_sql_filter method to take list_size_limit argument | see design, refactor all usages and pass this argument from SNOWFLAKE_LIST_SIZE_LIMIT config variable | 1.24.3 | 4.5 |  |  | 4.5 | Aleksandra | May 19, 2021 10:55:12 | May 19, 2021 10:55:17 | 2 | 57 | 8 | PP-1286 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/287 | Sprint 7 |  | Visualization Generation | MVP |  |  | 4.5
1.24.42 | Extend SQLConnection and SQLConnectionFactory to manage a connection pool | We should cache 1 connection per thread |  | 6 |  |  | 6 | Aleksandra | May 20, 2021, 10:26 AM | May 20, 2021, 10:26 AM | 1 | 41 | 26 | PP-1409 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/288 | Sprint 7 |  | Visualization Generation | MVP |  |  | 6
1.25 | ServiceLine API | see design | [11 empty] | PP-540 |  | Sprint 5 |  | Filters - Service Line filters | MVP |  |  | 0
1.25.1 | Handle parent_node = None for service line nodes in find_child_nodes_method | implement unit test to cover this case | 1.13 | 3 |  |  | 3 | Tomek We | April 13, 2021, 6:09 PM | April 14, 2021, 11:48 AM | 2 | 18 | 2 | PP-980 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/131 | Sprint 4 | Added to sprint in Sprint 4 | Filters - Service Line filters | MVP |  |  | 3
1.25.2 | Implement filteredServiceLines, filteredClinicalEpisodes and filteredDRGs endpoints | see design | 1.25.1 | 12 |  |  | 12 | Tomek We | April 13, 2021, 3:06 PM | April 14, 2021, 5:14 PM | 9.5 | 692 | 19 | PP-981 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/132 | Sprint 4 | Added to sprint in Sprint 4 | Filters - Service Line filters | MVP |  |  | 12
1.25.4 | Implement searchAllDiagnose endpoint | see design | 1.25.1 | 10 |  |  | 10 | Manoj | Apr 22, 2021 15:19:20 | Apr 22, 2021 15:19:34 | 8.5 | 87 | 1 | PP-580 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/171 | Sprint 5 |  | Filters - Service Line filters | MVP |  |  | 10
1.26 | Location API | Move code and data from existing P2v2 implementation to P2v3 | [11 empty] | PP-542 |  | Sprint 4 |  | Filters - Geography (Location) filters | MVP |  |  | 0
1.26.1 | Move allUSStates endpoint | Copy data to postgres, move django model from P2v2 |  | 2.5 |  | 4 | 4 | Manoj | April 2, 2021, 4:02 PM | April 6, 2021, 11:09 AM | 10 | 368 | 78 | PP-543 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/111 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | April 2, 2021, 4:02 PM | April 6, 2021, 11:09 AM | 4 | TRUE
1.26.2 | Move usState endpoint | Copy data to postgres, move django model from P2v2 |  | 2.5 |  | 4 | 4 | Manoj | April 5, 2021, 3:23 PM | April 6, 2021, 11:09 AM | 2 |  |  | PP-584 | - | Sprint 4 |  | Filters - Geography (Location) filters | MVP | April 5, 2021, 3:23 PM |  | 4
1.26.3 | Move searchUsLocation endpoint | Copy data to postgres, move django model from P2v2 |  | 6 |  | 4 | 4 | Manoj | April 5, 2021, 3:23 PM | April 6, 2021, 11:09 AM | 2 |  |  | PP-585 | - | Sprint 4 |  | Filters - Geography (Location) filters | MVP | April 5, 2021, 3:23 PM |  | 4
1.26.4 | Move usStateGeoAll endpoint | Copy .json file, make the path configurable | 1.21.1 | 4 |  | 4 | 4 | Manoj | April 1, 2021, 4:58 PM | April 6, 2021, 11:09 AM | 4 | 60 | 1 | PP-586 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/99 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | April 1, 2021, 4:58 PM |  | 4
1.26.5 | Move usCountyGeoForState endpoint | Copy .json file, make the path configurable | 1.21.1 | 4 |  | 4 | 4 | Manoj | April 1, 2021, 4:59 PM | April 6, 2021, 11:09 AM | 3 | 60 | 1 | PP-587 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/99 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | April 1, 2021, 4:59 PM |  | 4
1.26.6 | Move usStateGeoSearch | Copy data to postgres, move django model from P2v2 |  | 3.5 |  | 4 | 4 | Manoj | April 5, 2021, 3:24 PM | April 6, 2021, 11:09 AM | 2 |  |  | PP-588 | - | Sprint 4 |  | Filters - Geography (Location) filters | MVP | April 5, 2021, 3:24 PM |  | 4
1.26.7 | Move usCountyGeoAll endpoint | Copy data to postgres, move django model from P2v2 |  | 2 |  | 4 | 4 | Manoj | April 5, 2021, 3:25 PM | April 6, 2021, 11:09 AM | 2 |  |  | PP-589 | - | Sprint 4 |  | Filters - Geography (Location) filters | MVP | April 5, 2021, 3:25 PM |  | 4
1.26.8 | Move locationByRadialLocation endpoint | Copy .json file, make the path configurable | 1.21.1 | 8 |  | 4 | 4 | Manoj | April 1, 2021, 5:00 PM | April 6, 2021, 11:09 AM | 4 | 117 | 0 | PP-590 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/104 | Sprint 4 |  | Filters - Geography (Location) filters | MVP | April 1, 2021, 5:00 PM |  | 4
1.27 | Legend Data calculations | see design | [11 empty] | PP-982 |  | Sprint 7 |  | Visualization Legend | MVP |  |  | 0
1.27.1 | Implement get_legend_data_statistics | see design, prepare unit tests for all combinations of nodes used in the application | 1.1.12 | 22 | 22 |  | 22 | Tomek We | Apr 20, 2021 11:32:38 | May 04, 2021 13:52:28 | 35 | 807 | 0 | PP-983 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/202 | Sprint 6 |  | Visualization Legend | MVP |  |  | 22 | 1.5909
1.27.2 | Implement get_top_parent method | see design |  | 3 | 2 |  | 3 | Tomek We | May 04, 2021 13:44:12 | May 04, 2021 13:53:44 | 0.5 | 26 | 1 | PP-1306 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/203 | Sprint 6 |  | Visualization Legend | MVP |  |  | 3 | 0.16667
1.27.3 | Implement get_all_service_line_ids in PandasAnalyticalService |  | 1.1 | 2 | 2 |  | 2 | Tomek We | Apr 20, 2021 07:38:30 | Apr 20, 2021 09:23:06 | 0.25 | 18 | 0 | PP-985 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/152 | Sprint 6 |  | Visualization Legend | MVP |  |  | 2 | 0.125
1.27.6 | Implement calculate_legend_data method | see design, avoid unnecessary base value calculations | 1.27.1 - 1.27.3, 1.29 | 4 | 6 |  | 4 | Tomek We | May 04, 2021 14:37:12 | May 06, 2021 07:29:24 | 4 | 199 | 6 | PP-988 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/213 | Sprint 6 |  | Visualization Legend | MVP |  |  | 4 | 1
1.27.7 | Implement format_legend_data method |  |  | 2 | 2 |  | 2 | Tomek We | May 05, 2021 15:47:05 | May 07, 2021 10:46:22 | 1 | 75 | 2 | PP-989 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/215 | Sprint 6 |  | Visualization Legend | MVP |  |  | 2 | 0.5
1.27.8 | Integrate legend data calculation with the caseSummaryCollection endpoint | make sure to pass action_filters separately, for lhs_parent / rhs_parent pass whatever is passed to find_child_nodes | 1.27.6 , 1.27.7 | 8 | 8 |  | 8 | Tomek We | May 06, 2021 09:06:47 | May 12, 2021 07:48:02 | 16 | 476 | 28 | PP-990 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/229 | Sprint 6 |  | Visualization Legend | MVP |  |  | 8 | 2
1.27.9 | Implement legendData endpoint | see design, make sure to reuse code from caseSummaryCollection, avoid code duplication | 1.27.1 - 1.27.8 | 8 | 8 |  | 8 | Tomek We | May 11, 2021 09:51:53 | May 11, 2021 13:12:46 | 3.5 | 334 | 36 | PP-1307 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/233 | Sprint 6 |  | Visualization Legend | MVP |  |  | 8 | 0.4375
1.27.10 | Implement get_unique_drgs in PandasAnalyticalService | integrate with get_legend_data_statistics | 1.27.1 | 4 |  |  | 4 | Tomek We | May 5, 2021, 11:43 AM | May 5, 2021, 12:12 PM | 0.5 | 16 | 8 | PP-1315 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/207 | Sprint 6 |  | Visualization Legend | MVP |  |  | 4 | 0.125
1.27.11 | Implement support for Hospital / service unit graph type | cases include combinations of None or (CareUnit, Hospital) and (ServiceUnit, *) |  | 3 |  |  | 3 | Tomek We | May 20, 2021, 3:04 PM | May 21, 2021, 10:50 AM | 3.0833 | 188 | 6 | PP-1415 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/301 | Sprint 7 |  | Visualization Legend | MVP |  |  | 3
1.27.12 | Remove legendData support from caseSummaryCollection |  | FE integration with legendData endpoint | 3 | 2 | [8 empty] | PP-1308 |  |  |  | Visualization Legend | 1 |  |  | 0
1.27.13 | Implement count_nodes in PandasAnalyticalService | see design |  | 6 |  |  | 6 | Manoj | June 2, 2021, 9:35 AM | June 2, 2021, 2:48 PM | 6 | 83 | 3 | PP-1523 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/348 | Sprint 8 |  | Visualization Legend | MVP |  |  | 6
1.27.14 | Implement count_nodes in SQLAnalyticalService | see design |  | 6 |  |  | 6 | Manoj | June 2, 2021, 9:35 AM | June 3, 2021, 10:06 AM | 6.5 | 95 | 48 | PP-1524 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/352 | Sprint 8 |  | Visualization Legend | MVP |  |  | 6
1.27.15 | Update get_legend_data_statistics to match the latest design |  | 1.27.13, 1.27.14 | 6 |  |  | 6 | Tomek We | June 7, 2021, 11:39 AM | June 8, 2021, 3:00 PM | 11.5 | 157 | 318 | PP-1525 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/commit/5dd76287d8535a02a1515d71644045a6bd7546eb | Sprint 8 |  | Visualization Legend | MVP |  |  | 6
1.27.16 | Update count_nodes method to take lateral_filter argument | pass lateral_filter when calculating legend data, see design | 1.27.15 | 4 |  |  |  | Tomek We | [5 empty] | PP-1555 |  |  |  | Visualization Legend | MVP |  |  | 0
1.28 | Miscellaneous | approx est. ~40h |  |  |  |  | 40 | [6 empty] | PP-991 |  |  |  | System | MVP |  |  | 0
1.28.3 | LRU-cache (performance) | [12 empty] | PP-994 |  |  |  | System | 1 |  |  | 0
1.28.4 | Redis cache (performance) | [12 empty] | PP-995 |  |  |  | System | 1 |  |  | 0
1.28.5 | Flexible dataset IDs | [12 empty] | PP-996 |  |  |  | System | 1 |  |  | 0
1.28.6 | Review requirements.txt and remove unnecessary packages | cleanup task |  | 3 | 3 | 3 | 3 | [6 empty] | PP-1309 |  | Sprint 9 |  | System | MVP |  |  | 0
1.29 | Multithreading | see design | [11 empty] | PP-997 |  | Sprint 4 |  | System | MVP |  |  | 0
1.29.1 | Implement AppThreads singleton class | just copy from design | 1.21 | 1 |  |  | 1 | Maciej | April 8, 2021, 9:41 PM | April 8, 2021, 1:28 PM | 0.5 |  |  | PP-998 | - | Sprint 4 | Done, no task in jira | System | MVP |  |  | 1
1.29.2 | Refactor code to use AppThreads singleton | instead of creating ad-hoc ThreadPoolExecutors, modify decompose_packed_nodes, find_child_nodes and possibly other methods | 1.29.1 | 3 |  |  | 3 | Michał | April 14, 2021, 2:56 PM | April 14, 2021, 5:18 PM | 1.5 | 14 | 14 | PP-999 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/133 | Sprint 4 |  | System | MVP |  |  | 3
1.30 | Deleting Datasets | see design | [11 empty] | PP-1287 |  | Sprint 7 |  | Dataset upload and management | MVP |  |  | 0
1.30.1 | Implement drop_dataset method in DatasetService | see design | DM | 4 |  |  | 4 | Manoj | May 17, 2021 10:29:50 | May 17, 2021 13:59:44 | 3.5 | 35 | 0 | PP-1288 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/275 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 4
1.30.2 | Implement drop_all method in SQLAnalyticalService | Add this method to AnalyticalService base class and to PandasAnalyticalService (where it does nothing) | 1.24 | 3 |  |  | 3 | Manoj | May 17, 2021 14:01:18 | May 18, 2021 06:10:10 | 3 | 39 | 0 | PP-1289 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/277 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 3
1.30.3 | Implement DropDataset mutation | Move mutation definition from the P2v2 backed code, see design | 1.30.1, 1.30.2 | 5 |  |  | 5 | Manoj | May 18, 2021 06:11:48 | May 18, 2021 14:53:55 | 6 | 44 | 4 | PP-1290 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/289 | Sprint 7 |  | Dataset upload and management | MVP |  |  | 5
1.31 | Multiple benchmark calculation (tasks 1.31.1 - 1.31.5 must be merged in a single commit) | see design | [11 empty] | PP-1431 |  | Sprint 7 |  | Visualization Generation | MVP |  |  | 0
1.31.1 | Rafactor RelationStatistics to match design | benchmark_values field is now a list |  | 1.5 | 1.5 |  | 1.5 | Michał | May 17, 2021 12:54:23 | May 31, 2021 13:31:40 | 4 | 119.2 | 16.8 | PP-1381 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/295 | Sprint 7 |  | Visualization Generation | MVP |  |  | 1.5 | TRUE
1.31.2 | Refactor extract_relation_statistics to match design | benchmark_dfs argument is now a list |  | 1 | 1 |  | 1 | Michał | May 18, 2021 10:18:07 | May 31, 2021 13:32:03 | 0.5 | 119.2 | 16.8 | PP-1382 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/295 | Sprint 7 |  | Visualization Generation | MVP |  |  | 1
1.31.3 | Refactor format_case_summary_element to match design | benchmark_info argument is now a tuple list |  | 2 | 2 |  | 2 | Michał | May 18, 2021 14:20:14 | May 31, 2021 13:32:41 | 1 | 119.2 | 16.8 | PP-1383 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/295 | Sprint 7 |  | Visualization Generation | MVP |  |  | 2
1.31.4 | Refactor CaseSummaryQueryRunner to match design | benchmark argument is now a list of Futures |  | 2 | 2 |  | 2 | Michał | May 18, 2021 15:12:51 | May 31, 2021 13:33:26 | 1.5 | 119.2 | 16.8 | PP-1384 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/295 | Sprint 7 |  | Visualization Generation | MVP |  |  | 2
1.31.5 | Refactor caseSummaryStatistics to handle calculation of multiple benchmark values | see design |  | 4 | 4 |  | 4 | Michał | May 18, 2021, 5:13 PM | May 19, 2021, 5:53 PM | 11 | 119.2 | 16.8 | PP-1385 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/295 | Sprint 7 |  | Visualization Generation | MVP |  |  | 4 | TRUE
1.31.6 | Implement extract_filters method (from benchmark) | see design |  | 3 |  |  | 3 | Michał | May 27, 2021, 1:28 PM | May 27, 2021, 3:59 PM | 3.16 |  |  | PP-1510 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/325/diffs | Sprint 7 | merged together with 1.31.6 | Visualization Generation | MVP |  |  | 3
1.31.7 | Implement extract_parents method (from benchmark) | see design |  | 2 |  |  | 2 | Michał | May 27, 2021, 3:20 PM | May 27, 2021, 6:04 PM | 4.25 | 196 | 130 | PP-1511 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/331 | Sprint 7 |  | Visualization Generation | MVP |  |  | 2
1.31.8 | Update make_abstract_graph_query method to match the design.Use extract_filters / extract_parents from benchmark | see design | 1.31.6, 1.31.7 | 4 |  |  | 4 | Michał | May 28, 2021, 11:18 AM | May 28, 2021, 2:44 PM | 5 | 582 | 338 | PP-1512 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/335 | Sprint 7 |  | Visualization Generation | MVP |  |  | 4
1.31.9 | Handle maxLength argument in unGroupRange, update implementation to match latest design | see design |  | 2.5 |  |  | 2.5 | Michał | May 28, 2021, 4:13 PM | May 28, 2021, 5:48 PM | 2.16 | 52 | 9 | PP-1513 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/336 | Sprint 7 |  | Visualization Generation | MVP |  |  | 2.5
3 | Report View Management | [12 empty] | PP-356 |  | Sprint 6 | Design not detailed enough to estimate by reviewer/PM | View Dashboard | MVP |  |  | 0 | #DIV/0!
3.0 | Environment Setup | Setu development environment including DJangoand PGSql |  |  |  |  | 20 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 20 | 147 | 0 | PP-357 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 20
3.1 | Define schema.py | Class that defines graphQL queries, endpoints and object structure. Python file will have definition of following ojects. Developer can refer existing P2BE code at p2backend\ReportView\schema.py file. |  |  |  |  | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-358 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.2 | Define reportview_api.py | Class that has actual implementation for all end points. Developer can refer p2backend\BigSense\Reportview\reportview_api.py file from existing P2BE code |  |  |  |  | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-359 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.3 | Define model.py | Class that defines the Entity Relation of report view as per OLTP database(Postgres) |  |  |  |  | 4 | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-360 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4
3.4 | Implementing Endpoints | This implementation will have a resolve method in schema.py and corresponding method in reportview_api.py file |  |  |  |  | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-361 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.4.1 | ReportView | [5 empty] | 4 | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-362 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4
3.4.2 | ReportViews | [5 empty] | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-363 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.4.3 | SearchReportViews | [5 empty] | 4 | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-364 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4
3.4.4 | CreateReportView | [5 empty] | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-365 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.4.5 | UpdateReportView | [5 empty] | 4 | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-366 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4
3.4.6 | DeleteReportView | [5 empty] | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-367 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | View Dashboard | MVP | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.5 | [BE] Extract user details from Auth0 token |  |  | 8 |  |  | 8 | Manoj, Kamil C | March 25, 2021, 9:52 AM | April 9, 2021, 9:15 AM | 12 | 252 | 5 | PP-516 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/116 | Sprint 4 | Added to sprint in Sprint 3, Postponed from Sprint 3 | View Dashboard | MVP | March 25, 2021, 9:52 AM | April 9, 2021, 9:15 AM | 8
3.6 | [BE] Modify Report view endpoints to use user details from Auth0 token |  | 3.5 | 12 |  |  | 12 | Manoj | May 06, 2021 07:18:33 | May 06, 2021 13:58:06 | 7 | 50 | 16 | PP-517 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/221 | Sprint 6 | Postponed from Sprint 3 | View Dashboard | MVP |  |  | 12 | 0.58333
3.7 | Integrate analytical endpoints with django | Integrate endpoints with django. To be seen under https://p2v3.ownedoutcomes.com/backend/graphql/ url. List:caseLocationDetails endpoint caseLobCounts endpoint getAvailableYears endpoint getDateTimeStatsForListOfYears endpoint filteredCareUnitTypes endpoint getDatasetsInitialFilters getDateTimesForYear endpoint allDatasets endpoint getLDSDatasetsIDs endpoint |  | 8 |  | 8 | 8 | Tomek We | March 29, 2021, 4:09 PM | March 31, 2021, 3:44 PM | 16 | 88 | 482 | PP-567 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/94 https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/95 | Sprint 3 | Added to sprint in Sprint 3 | System | MVP | March 29, 2021, 4:09 PM | March 31, 2021, 3:44 PM | 8
3.8 | Implement mock for users endpoint | Implement user query that returns always same user { user { id name emailId __typename } id could be the same as in query: { ReportViews { viewList { owner { id emailId } } } } |  |  |  | 2 | 2 | Manoj | April 1, 2021, 12:40 PM | April 1, 2021, 12:40 PM | 0.5 | 45 | 1 | PP-615 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/101 | Sprint 3 | Added to sprint in Sprint 3 | Authentication & Authorization | MVP | April 1, 2021, 12:40 PM | April 1, 2021, 12:40 PM | 2
3.9 | Code cleanup in unit tests |  |  | 1 |  |  | 1 | Michał | April 9, 2021, 4:02 PM | April 9, 2021, 5:01 PM | 1 | 844 | 812 | PP-939 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/121 | Sprint 4 | Added to sprint in Sprint 4 | System | MVP |  |  | 1
4 | Integration with AWS Secrets Manager | see design | [11 empty] | PP-1432 |  | Sprint 8 |  | System | 1 |  |  | 0
4.1 | Create app_config package project | use python package project template |  | 3 |  |  | 3 | Adrian Z | May 31, 2021 10:01:25 | Jun 01, 2021 10:09:36 | 2 |  |  | PP-1433 | https://gitlab-01.itx.pl/p2/appconfig/-/merge_requests/1 | Sprint 8 | Merged together with 4.3 | System | MVP |  |  | 3
4.2 | Set up CI/CD pipelines for the app_config package | deploy release version to nexus |  | 3 |  |  | 3 | Adrian Z | May 31, 2021 13:47:12 | Jun 01, 2021 10:09:44 | 2 |  |  | PP-1434 | https://gitlab-01.itx.pl/p2/appconfig/-/merge_requests/1 | Sprint 8 | Merged together with 4.3 | System | MVP |  |  | 3
4.3 | Implement parse_aws_url and is_secret_url methods |  | 4.1 - 4.2 | 2.5 |  |  | 2.5 | Adrian Z | Jun 01, 2021 06:52:17 | Jun 01, 2021 10:09:12 | 2.3333 | 972 | 1 | PP-1435 | https://gitlab-01.itx.pl/p2/appconfig/-/merge_requests/1 | Sprint 8 |  | System | MVP |  |  | 2.5
4.4 | Implement get_secret method |  |  | 2 |  |  | 2 | Adrian Z | Jun 01, 2021 09:56:14 | Jun 02, 2021 09:59:20 | 2.1667 |  |  | PP-1436 | - | Sprint 8 | Merged together with 4.3 | System | MVP |  |  | 2
4.5 | Implement AppConfigBase class for derving AppConfig in applications | refactor existing code, isolate AppBaseConfig class accepting config variables and validation function, which can be used across projects | 4.1 - 4.2 | 8 |  |  | 8 | Adrian Z | Jun 01, 2021 12:53:40 | Jun 02, 2021 09:59:19 | 5.75 | 208 | 15 | PP-1437 | https://gitlab-01.itx.pl/p2/appconfig/-/merge_requests/2 | Sprint 8 |  | System | MVP |  |  | 8
4.6 | Handle secret url variables in AppConfigBase | Should test is_secret_url with all variables and resolve secret variables from provided urls using get_secret method | 4.4, 4.5 | 8 |  |  | 8 | Adrian Z | Jun 07, 2021 08:54:27 | Jun 09, 2021 12:38:02 | 0 |  |  | PP-1438 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/378 | Sprint 8 | Merged together with 4.7 | System | MVP |  |  | 8
4.7 | Refactor AppConfig in p2 backend to be derived from AppConfigBase | use newly created app_config library | 4.1 - 4.6 | 6 |  |  | 6 | Adrian Z | Jun 07, 2021 08:58:01 | Jun 08, 2021 08:02:26 | 5.6667 | 165 | 171 | PP-1439 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/378 | Sprint 8 |  | System | MVP |  |  | 6
5 | System Administration Scripts | see design | [11 empty] | PP-1440 |  |  |  | System | 1 |  |  | 0
5.1 | Implement copy_share method | simply use the one from the tutorial |  | 2 | 2 |  |  | Manoj | June 7, 2021, 10:21 AM | June 7, 2021, 3:27 PM | 2.5 |  |  | PP-1441 |  | Sprint 8 |  | System | 1 |  |  | 0 | TRUE
5.2 | Implement validate_schema method | only validatte compliance with the p2-relations schema, try reusing code from SQLAnalyticsProvider |  | 3.5 | 4 |  |  | Manoj | June 7, 2021, 10:22 AM | June 8, 2021, 11:29 AM | 4.5 |  |  | PP-1442 |  | Sprint 8 |  | System | 1 |  |  | 0
5.3 | Implement copy_lds_datasets method |  | 5.1, 5.2 | 10 | 10 |  |  | Manoj | June 8, 2021, 11:35 AM | June 9, 2021, 1:05 PM | 9.75 |  |  | PP-1443 |  | Sprint 8 |  | System | 1 |  |  | 0 | TRUE
5.4 | Implement p2-admin.py script | pull variables using modified AppConfig, implement --help for commands | 4 | 5 | 5 |  |  | Manoj | June 9, 2021, 2:15 PM | 10, 2021, 9:47 AM | 5.3 |  |  | PP-1444 |  | Sprint 8 |  | System | 1 |  |  | 0 | TRUE
5.5 | Implement copy_share command in p2-admin script | simply pass arguments to copy_share method, add help | 5.4 | 3.5 | 4 |  |  | Manoj | June 10, 2021, 9:11 AM | June 10, 2021, 4:22 PM | 4 |  |  | PP-1445 |  | Sprint 8 |  | System | 1 |  |  | 0 | TRUE
5.6 | Implement copy_lds_datasets command | simply pass arguments to copy_lds_datasets, add help | 5.4 | 4 | 4 |  |  | Manoj | June 10, 2021, 1:01 PM | June 11, 2021, 1:08 PM | 4 |  |  | PP-1446 |  | Sprint 8 |  | System | 1 |  |  | 0 | TRUE
5.7 | Implement validate_schema command | simply pass arguments to validate_schema add help | 5.4 | 2 | 2 |  |  | Manoj | June 10, 2021, 1:00 PM | June 11, 2021, 10:37 AM | 2 |  |  | PP-1447 |  | Sprint 8 |  | System | 1 |  |  | 0 | TRUE
5.8 | Implement publish_dataset command | validate if matching p2-relations schema | 5.4 | 3.5 | 4 |  |  | Manoj | June 11, 2021, 10:13 AM | June 11, 2021, 4:39 PM | 4 |  |  | PP-1448 |  | Sprint 8 |  | System | 1 |  |  | 0 | TRUE
5.9 | Implement find_datasets method |  |  | 2 | 2 |  |  | Manoj |  |  | 1.25 |  |  | PP-1449 |  | Sprint 9 |  | System | 1 |  |  | 0 | TRUE
5.10 | Implement drop_dataset command | make sure to unregister dataset from reportviews, use DeleteDataset mutation as example | 5.4, 5.9 | 4 | 4 |  |  | Manoj |  |  | 4.5 |  |  | PP-1450 |  | Sprint 9 |  | System | 1 |  |  | 0 | TRUE
6 | Testing | [12 empty] | PP-1653 |  |  |  | System | 1 |  |  | 0
6.1 | Prepare snowflake database for integration tests | copy identical data as currently used in the unit tests |  | 2.5 | [9 empty] | PP-1654 |  |  |  | System | 1 |  |  | 0
6.2 | Prepare dataset manager for integration tests | configure a test tenant with access to test datasets |  | 2.5 | [9 empty] | PP-1655 |  |  |  | System | 1 |  |  | 0
6.3 | Implement integration mode execution for tests | see design, handle mode, user and password arguments, prepare test fixtures (analytical service, dataset service) connecting to real instances, no refactoring of tests yet |  | 12 | [9 empty] | PP-1656 |  |  |  | System | 1 |  |  | 0
6.4 | Refactor all unit tests to support integration mode | where applicable, implement integration mode for test cases, run test cases to make sure they pass in integration mode | 6.1 - 6.3 | 18 | [9 empty] | PP-1657 |  |  |  | System | 1 |  |  | 0
6.5 | Set up CI/CD pipeline to run tests in integration mode |  | 6.4 | 4 | [9 empty] | PP-1658 |  |  |  | System | 1 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on Q132: @awaz@ownedoutcomes.com This PP-461 task 'Implement extract_action method' was completed in Feb. It does not seem to be planned in sprint 5. cc: @krupa@ownedoutcomes.com _Assigned to Artur Waz_ -Joslyn Huang @joslyn@ownedoutcomes.com sorry Joslyn, but I'm not getting it. The development started at April 6, 2021, 3:21 PM. The task itself was created March 19, 2021, 10:11 AM. cc: @krupa@ownedoutcomes.com _Reassigned to Joslyn Huang_ -Artur Waz @awaz@ownedoutcomes.com The fields are updated now. Earlier, the "actual start date" was 2021/02/21, and the "actual end date" was "2021/02/22". And I saw it's already code complete and marked as closed and merged the request (highlighted in green in the excel sheet per your process). So that's why I asked why the planning would be in sprint 5. Thanks for updating the fields now. Can you confirm the green highlight on the excel again? cc @krupa@ownedoutcomes.com _Reassigned to Artur Waz_ -Joslyn Huang

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Problem with missing DRGs | Problem found during writing unit test. The issue was with type of join of DRG table in already finished implementation. | Maciej, Michał, Ola | March 12, 2021, 8:00 AM | March 15, 2021, 2:10 PM | 20 | 28 | 30 |  | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/28 | Issue delayed finish of group nodes task (1.1.12)
2 | Cannot retrieve stateSummary from caseLocationDetails query | To reproduce: Get into: https://p2v3.ownedoutcomes.com/backend/graphql/ Send query: { caseLocationDetails ( datasets: [{id: "0"}] options: null ) { fipsSummary { id } cbsaSummary { id } stateSummary { id name postalAbbreviation entitySummary { entityType totalCount } } } } Fastest way to reproduce: https://p2v3.ownedoutcomes.com/backend/graphql/#query={ caseLocationDetails ( datasets%3A [{id%3A "0"}] options%3A null ) { fipsSummary { id } cbsaSummary { id } stateSummary { id name postalAbbreviation entitySummary { entityType totalCount } } } } Response: { "errors": [ { "message": "Syntax Error GraphQL (4:14) Unexpected Name \"null\"\n\n3: datasets: [{id: \"0\"}]\n4: options: null\n ^\n5: ) {\n", "locations": [ { "line": 4, "column": 14 } ] } ] } | Michał | April 1, 2021, 9:56 AM | April 1, 2021, 12:00 PM | 1.75 | 63 | 3 | PP-616 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/100 |  | lack related task
3 | caseSummaryCollection pagination issue | Problem while sending query similar to one used in rc.bigsense.ai environment. To reproduce: 1. go into https://p2v3.ownedoutcomes.com/backend/graphql/ 2. send query and variables attached: 3. in response you will see only null values | Maciej | April 7, 2021, 12:12 PM | April 7, 2021, 12:12 PM | 5.5 | 6 | 10 | PP-622 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/112 |  | lack related task
4 | Cannot create a report view | To reproduce: 1. Go to https://p2v3.ownedoutcomes.com/p2/ 2. Click Login button 3. Login: test@test.com Password: 123 4. Go to https://p2v3.ownedoutcomes.com/p2/view-list 5. Try to create a report view. 6. You will receive 400 response from backend (request and response provided below): Request:{"operationName":null,"variables":{"id":"new","name":"245345","isTerrain":false,"orders":[{"isAscending":false,"orderName":"Case_count"}],"labelOption":{"isActive":true,"labels":["Alphabet","Case_count","Star_rating","D90_rr_per_instance"]},"benchmark":{"isEnable":false,"options":[{"aggregationLevel":"National","measure":"D90_rr_per_instance"},{"aggregationLevel":"National","measure":"D90_episode_cost_per_patient"}],"serviceLine":{"id":"","name":""},"clinicalEpisodes":[],"drgs":[],"careUnitType":{"type":""},"metric":{"isAverage":true,"percent":50},"times":{"includedTimes":{"timeRanges":[{"fromTime":{"quarter":"","year":""},"toTime":{"quarter":"","year":""}}]}}},"count":{"casesCount":{"minimumSelectedCount":0,"maximumSelectedCount":0},"entitiesCount":{"minimumSelectedCount":0,"maximumSelectedCount":0}},"threshold":{"isEnabled":false,"details":[]}},"query":"query ($name: String!, $ownerId: ID!, $ownerName: String, $ownerEmail: String, $reportViewType: String, $filters: FilterInputType, $datasets: [DatasetsInputType], $isTerrain: Boolean, $orders: [OrderInputType], $labelOption: LabelOptionInputType, $benchmark: BenchmarkOptionInputType, $count: ReportViewCountInputType) {\n CreateReportView(name: $name, owner: {id: $ownerId, name: $ownerName, emailId: $ownerEmail}, reportViewType: $reportViewType, filters: $filters, datasets: $datasets, isTerrain: $isTerrain, orders: $orders, labelOption: $labelOption, benchmark: $benchmark, count: $count) {\n status\n id\n message\n __typename\n }\n}\n"}Response:{"errors":[{"message":"Variable \"$ownerId\" of required type \"ID!\" was not provided.","locations":[{"line":1,"column":24}]}]} | Manoj, Chandan | May 12, 2021, 6:35 AM | May 13, 2021, 8:27 AM | 5 |  |  | PP-1002 |  |  | lack related task
5 | Cannot get into report view | To reproduce: 1. Go to https://p2v3.ownedoutcomes.com/p2/ 2. Click Login button 3. Login: test@test.com Password: 123 4. Go to https://p2v3.ownedoutcomes.com/p2/view-list 5. Select any report view 6. You will see a blank screen (problem with respones from backend (below you will see a request and a response): Request:{"operationName":null,"variables":{"datasets":[{"id":null}],"filteredCareUnitTypes":true,"filteredServiceLines":true,"getAvailableYears":true,"getDateTimeStatsForListOfYears":true,"caseLobCounts":true},"query":"query ($datasets: [DatasetsInputType]!, $filteredCareUnitTypes: Boolean, $filteredServiceLines: Boolean, $getAvailableYears: Boolean, $getDateTimeStatsForListOfYears: Boolean, $caseLobCounts: Boolean) {\n getDatasetsInitialFilters(datasets: $datasets, filteredCareUnitTypes: $filteredCareUnitTypes, filteredServiceLines: $filteredServiceLines, getAvailableYears: $getAvailableYears, getDateTimeStatsForListOfYears: $getDateTimeStatsForListOfYears, caseLobCounts: $caseLobCounts) {\n filteredCareUnitTypes {\n id\n name\n numberOfCases\n __typename\n }\n filteredServiceLines {\n id\n name\n numberOfCases\n __typename\n }\n getAvailableYears\n getDateTimeStatsForListOfYears {\n year\n quarterStats {\n quarter\n caseCount\n entityCount\n __typename\n }\n __typename\n }\n caseLobCounts {\n id\n name\n numberOfCases\n __typename\n }\n __typename\n }\n}\n"}Response:{"errors":[{"message":"int() argument must be a string, a bytes-like object or a number, not 'NoneType'","locations":[{"line":2,"column":3}],"path":["getDatasetsInitialFilters"]}],"data":{"getDatasetsInitialFilters":null}} | Tomek We | April 13, 2021, 11:52 AM | April 21, 2021, 3:18 PM | 7 |  |  | PP-1003 | - |  | lack related task
6 | Replace GraphQL objects with dicts |  | Aleksandra | April 15, 2021, 10:37 AM | April 16, 2021, 10:57 AM | 7 | 13 | 19 | PP-1038 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/144
7 | CaseSummaryCollection - can't generate default graph |  | Maciej | April 14, 2021, 11:32 AM | April 15, 2021, 2:37 PM | 16.5 | 372 | 132 | PP-1004 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/138 |  | lack related task
8 | Node IDs not returned from caseSummaryCollection |  | Maciej | April 21, 2021, 11:03 AM | April 21, 2021, 11:03 AM | 0.5 | 3 | 4 | PP-1293 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/157 |  | lack related task
9 | decompose_packed_nodes decorator doesn't support positional arguments | [7 empty] | PP-1303 |  | Moderate priority
10 | get_entity_quality and get_facility_details returns nonuniform null values |  | Michał | April 21, 2021, 1:33 PM | April 21, 2021, 2:02 PM | 0.5 | 21 | 18 | PP-1304 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/160 |  | lack related task
11 | get_careunit_details doesn't properly populate fields with GraphQL objects |  | Michał | April 21, 2021, 2:05 PM | April 22, 2021, 11:49 AM | 5 | 55 | 21 | PP-1305 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/165 |  | lack related task
12 | Discprepancies between datasets in Snowflake, local testing files, and technical design document. |  | Michał | May 6, 2021, 12:24 PM | May 6, 2021, 1:53 PM | 3.5 |  |  | PP-1320 |  |  | lack related task
13 | searchCareUnitAndDetail - 'NoneType' object has no attribute 'number_of_patients' |  | Kamil C | May 7, 2021, 11:39 AM | May 7, 2021, 1:55 PM | 3 |  |  | PP-1317
14 | searchCareUnitAndDetail returns Null values for quality and facility fields |  | Kamil C | May 7, 2021, 2:18 PM | May 11, 2021, 1:15 PM | 16.5 |  |  | PP-1316
15 | getDatasetsInitialFilters - filteredServiceLines |  | Michał | May 10, 2021, 3:46 PM | May 11, 2021, 4:01 PM | 2.5 |  |  | PP-1314 |  |  | lack related task
16 | caseSummaryCollection - Collapse node |  | Aleksandra | May 11, 2021, 4:26 PM | May 13, 2021, 11:56 AM | 18 |  |  | PP-1313
17 | NoneType' object has no attribute 'lower' |  | Michał | May 7, 2021, 10:57 AM | May 7, 2021, 2:57 PM | 6 |  |  | PP-1312 |  |  | lack related task
18 | caseSummaryCollection - exclude FIPS/CBSA does not work |  | Michał, Tomek We | April 26, 2021, 4:40 PM | May 10, 2021, 3:10 PM | 11 |  |  | PP-1292
19 | CaseSummaryCollection - problem with some cbsa/fips in included location filters |  | Tomek We | April 26, 2021, 4:39 PM | April 26, 2021, 4:39 PM | 2 |  |  | PP-1291 | - |  | lack related task
20 | FilteredDrgs not filtering properly on clinicalEpisodes |  | Kamil C | May 11, 2021, 2:04 PM | May 11, 2021, 4:58 PM | 4 |  |  | PP-1283
21 | Incorrect typenames in UsState and SearchUsLocation |  | Manoj | April 15, 2021, 11:40 AM | April 15, 2021, 11:40 AM | 2 | 125 | 43 | PP-1037 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/136 |  | lack related task
22 | allDatasets - incorrect format of 'fromTime' and 'toTime' fileds | [7 empty] | PP-1005 |  | Moderate priority
23 | caseLocationDetails returns wrong states for Fips and Cbsa |  | Tomek We | May 11, 2021, 3:14 PM | May 12, 2021, 4:35 PM | 8 |  |  | PP-938 |  |  | lack related task
24 | filteredCareUnitTypes throws error on location filters |  | Tomek We | May 17, 2021, 3:29 PM | May 17, 2021, 3:46 PM | 0.5 |  |  | PP-696 |  |  | lack related task
25 | Null datasets in ReportView query |  | Michal | May 11, 2021, 4:03 PM | May 12, 2021, 5:17 PM | 10.5 |  |  | PP-686 |  |  | lack related task
26 | [group nodes][unit test] Node "Home" is not found if group rhs_nodes contains: 'SNF', 'HHA', 'LTCH', 'IRF', 'Home' |  | Maciej | April 15, 2021, 3:16 PM | April 15, 2021, 3:16 PM | 0 |  |  | PP-617 | - | Fixed together with bug PP-1004
27 | API gives error :: getDatasetsInitialFilters & getLdsDatasetsIds |  | Kamil C | May 12, 2021, 9:40 AM | May 12, 2021, 10:35 AM | 3.5 |  |  | PP-1353 |  |  | lack related task
28 | caseSummaryCollection - including Geography and Entity filters at the same time |  | Tomek We | May 17, 2021, 5:10 PM | May 18, 2021, 3:50 PM | 7.16 |  |  | PP-1388 |  |  | lack related task
29 | Incorrect token passing in DatasetManager |  | Kamil C | April 13, 2021, 9:51 AM | April 13, 2021, 10:43 AM | 6 |  |  | PP-1000 |  |  | lack related task
30 | Diagnoses episodes and carelines invalid join |  | Maciej L | May 10, 2021, 4:49 PM | May 10, 2021, 4:49 PM | 4.5 |  |  | PP-1352 |  |  | lack related task
31 | caseSummaryCollection - empty strings in timeRanges are not handled properly |  | Michal | May 12, 2021, 5:27 PM | May 12, 2021, 6:02 PM | 0.5 |  |  | PP-1355 |  |  | lack related task
32 | Unable to run parameterized pandas/SQL tests fixture due to SQLite integration method |  | Maciej L | May 12, 2021, 11:52 AM | May 12, 2021, 11:52 AM | 4 |  |  | PP-1356 |  |  | lack related task
33 | select_from_relations in sql_analytical_service.py doesn't work with table aliases |  | Maciej L | May 12, 2021, 1:33 PM | May 12, 2021, 1:33 PM | 0 |  |  | PP-1359 | -
34 | caseSummaryCollection - expand |  | Aleksandra | May 13, 2021, 6:42 PM | May 20, 2021, 10:38 AM | 6 |  |  | PP-1361
35 | API(filteredCareUnits) response mismatch with current version |  | Kamil C | May 14, 2021, 10:37 AM | May 14, 2021, 11:31 AM | 1 |  |  | PP-1363 |  |  | lack related task
36 | filteredClinicalEpisodes - serviceLine field return Null |  |  | May 14, 2021, 9:54 AM | May 14, 2021, 9:54 AM | 0 |  |  | PP-1364 |  | bug rejected
37 | caseSummaryCollection - No RHS rule for ungrouping found for value 'serviceLine' |  | Michal | May 14, 2021, 2:40 PM | May 14, 2021, 2:40 PM | 2.5 |  |  | PP-1365 |  |  | lack related task
38 | caseSummaryCollectionMapView - some fields are returned as Null |  | Kamil C | May 17, 2021, 1:04 PM | May 21, 2021, 9:45 AM | 10.5 |  |  | PP-1366 |  |  | lack related task
39 | caseSummaryCollection - orders field should ignore null |  | Tomek We | May 17, 2021, 10:59 AM | May 17, 2021, 12:23 PM | 3.5 |  |  | PP-1367 |  |  | lack related task
40 | [BE] API filteredCareUnits error |  | Kamil C | May 17, 2021, 4:05 PM | May 19, 2021, 12:11 PM | 7.5 |  |  | PP-1368 |  |  | lack related task
41 | caseSummaryCollection - include Home |  | Piotr O | May 24, 2021, 1:54 PM | May 24, 2021, 1:55 PM | 0.5 |  |  | PP-1386 | -
42 | caseSummaryCollection - groupingInfo should returned number of nodes for packed nodes |  | Kamil C | May 18, 2021, 1:44 PM | May 18, 2021, 1:58 PM | 1.5 | 5 | 2 | PP-1391 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/279
43 | caseSummaryCollection - cost - should return 0 value instead of null |  | Kamil C | May 18, 2021, 2:44 PM | May 18, 2021, 2:44 PM | 1 |  |  | PP-1404
44 | Datasets determined BenchmarkLevel.NATIONAL doesn't match actual query demand |  | Michal | May 20, 2021, 2:39 PM | May 21, 2021, 1:22 PM | 6.5 |  |  | PP-1410
45 | CaseSummaryCollection - (None, NodeType(type=<NodeTypeEnum.ServiceUnit: 3>, subtype=None)) |  | Tomek We | May 20, 2021, 3:06 PM | May 21, 2021, 10:54 AM | 2 |  |  | PP-1412
46 | caseSummaryCollection - expand to clinicalEpisode level |  | Piotr O | May 20, 2021, 11:19 AM | May 20, 2021, 11:19 AM | 0 |  |  | PP-1413 | - | bug rejected
47 | 2d Graph - caseSummaryCollection incorrect response |  | Michal | May 21, 2021, 1:37 PM |  |  |  |  | PP-1418
48 | UpdateReportView doesn't work |  | Tomek We | May 24, 2021, 3:06 PM | May 25, 2021, 2:15 PM | 5 |  |  | PP-1419
49 | caseSummaryCollectionMapView - benchmark causes error "string index out of range" |  | Kamil C | May 24, 2021, 9:07 AM | May 24, 2021, 10:08 AM | 1.5 |  |  | PP-1420
50 | [BE] Incorrect attribute setting for caseSummaryCollection API for Benchmark graph | [7 empty] | PP-1454
51 | caseSummaryCollection - incorrect benchmark values for episode level |  | Tomek We, Michal | May 25, 2021, 2:40 PM |  |  |  |  | PP-1498
52 | Graph View - individual (auto-expanded) nodes don't have connections | [7 empty] | PP-1500
53 | Market Share Graph :: Filters doesn't applied correctly |  | Kamil C | May 26, 2021, 11:17 AM |  |  |  |  | PP-1501 |  |  | lack related task
54 | Mismatch between source/destination in query and response in benchmarks |  | Michal | May 25, 2021, 2:05 PM |  |  |  |  | PP-1499
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73

## Planned availability
Date | Devs | Hrs | Cummulative
2021-04-12 | 7 | 52.5 | 52.5 | Sprint 4 | 56 | 0
2021-04-13 | 7 | 42 | 94.5 | Sprint 4 | 56 | 0
2021-04-14 | 7 | 42 | 136.5 | Sprint 4 | 56 | 0
2021-04-15 | 7 | 42 | 178.5 | Sprint 4 | 56 | 0
2021-04-16 | 7 | 42 | 220.5 | Sprint 4 | 56 | 0
2021-04-17 | 0 | 0 | 220.5 |  | 0 | 0
2021-04-18 | 0 | 0 | 220.5 |  | 0 | 0
2021-04-19 | 8 | 48 | 268.5 | Sprint 5 | 64 | 0
2021-04-20 | 8 | 48 | 316.5 | Sprint 5 | 64 | 0
2021-04-21 | 8 | 48 | 364.5 | Sprint 5 | 64 | 0
2021-04-22 | 8 | 48 | 412.5 | Sprint 5 | 64 | 0 | ds | group | be | Daily update (today)
2021-04-23 | 8 | 48 | 460.5 | Sprint 5 | 64 | 0 | 114 | 649 | 2264.5 | 3027.5
2021-04-24 | 0 | 0 | 460.5 |  | 0 | 0 | 114 | 641 | 2205.5 | 2960.5
2021-04-25 | 0 | 0 | 460.5 |  | 0 | 0 | 125.002 | 436.5833 | 2436.6633 | 2998.2487
2021-04-26 | 8 | 48 | 508.5 | Sprint 5 | 64 | 0 | 0 | 8 | 59 | 67
2021-04-27 | 8 | 48 | 556.5 | Sprint 5 | 64 | 0 |  |  | 0 | 0
2021-04-28 | 8 | 48 | 604.5 | Sprint 5 | 64 | 0 | 100 | 98.7673 | 97.3946 | 97.787
2021-04-29 | 8 | 48 | 652.5 | Sprint 5 | 64 | 0 | 109.6509 | 68.1097 | 110.4812 | 101.2751
2021-04-30 | 8 | 48 | 700.5 | Sprint 5 | 64 | 0
2021-05-01 | 0 | 0 | 700.5 |  | 0 | 0
2021-05-02 | 0 | 0 | 700.5 |  | 0 | 0
2021-05-03 | 1 | 6 | 706.5 | Sprint 6 | 8 | 0
2021-05-04 | 6 | 36 | 742.5 | Sprint 6 | 48 | 0
2021-05-05 | 6 | 36 | 778.5 | Sprint 6 | 48 | 0
2021-05-06 | 6 | 36 | 814.5 | Sprint 6 | 48 | 0
2021-05-07 | 6 | 36 | 850.5 | Sprint 6 | 48 | 0
2021-05-08 | 0 | 0 | 850.5 |  | 0 | 0
2021-05-09 | 0 | 0 | 850.5 |  | 0 | 0
2021-05-10 | 6 | 36 | 886.5 | Sprint 6 | 48 | 0
2021-05-11 | 6 | 36 | 922.5 | Sprint 6 | 48 | 0
2021-05-12 | 6 | 36 | 958.5 | Sprint 6 | 48 | 0
2021-05-13 | 6 | 36 | 994.5 | Sprint 6 | 48 | 0
2021-05-14 | 6 | 36 | 1030.5 | Sprint 6 | 48 | 0
2021-05-15 | 0 | 0 | 1030.5 |  | 0 | 0
2021-05-16 | 0 | 0 | 1030.5 |  | 0 | 0
2021-05-17 | 4 | 24 | 1054.5 | Sprint 7 | 32 | 0
2021-05-18 | 4 | 24 | 1078.5 | Sprint 7 | 32 | 0
2021-05-19 | 4 | 24 | 1102.5 | Sprint 7 | 32 | 0
2021-05-20 | 4 | 24 | 1126.5 | Sprint 7 | 32 | 0
2021-05-21 | 4 | 24 | 1150.5 | Sprint 7 | 32 | 0
2021-05-22 | 0 | 0 | 1150.5 |  | 0 | 0
2021-05-23 | 0 | 0 | 1150.5 |  | 0 | 0
2021-05-24 | 5 | 30 | 1180.5 | Sprint 7 | 40 | 0
2021-05-25 | 5 | 30 | 1210.5 | Sprint 7 | 40 | 0
2021-05-26 | 5 | 30 | 1240.5 | Sprint 7 | 40 | 0
2021-05-27 | 5 | 30 | 1270.5 | Sprint 7 | 40 | 0
2021-05-28 | 5 | 30 | 1300.5 | Sprint 7 | 40 | 0
2021-05-29 | 0 | 0 | 1300.5
2021-05-30 | 0 | 0 | 1300.5
2021-05-31 | 6 | 36 | 1336.5
2021-06-01 | 6 | 36 | 1372.5
2021-06-02 | 6 | 36 | 1408.5
2021-06-03 | 6 | 36 | 1444.5
2021-06-04 | 6 | 36 | 1480.5
2021-06-05 | 0 | 0 | 1480.5
2021-06-06 | 0 | 0 | 1480.5
2021-06-07 | 6 | 36 | 1516.5
2021-06-08 | 6 | 36 | 1552.5
2021-06-09 | 6 | 36 | 1588.5
2021-06-10 | 6 | 36 | 1624.5
2021-06-11 | 6 | 36 | 1660.5
2021-06-12 | 0 | 0 | 1660.5
2021-06-13 | 0 | 0 | 1660.5
2021-06-14 | 6 | 36 | 1696.5
2021-06-15 | 6 | 36 | 1732.5
2021-06-16 | 6 | 36 | 1768.5
2021-06-17 | 6 | 36 | 1804.5
2021-06-18 | 6 | 36 | 1840.5

## Sheet4
Backend |  |  | QA |  |  | Front End
Sprint 5 | Sprint 6 | Sprint 7 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 5 | Sprint 6 | Sprint 7
73 % | 85 % | 90 % | 21 % | 26 % | 51 % | 62 % | 71 % | 91.75 %
2021-05-28 | 2021-06-08 | 2021-06-08 | 2021-07-09 | 2021-08-02 | 2021-08-02 | 2021-06-15 | 2021-06-15 | 2021-06-15
2 808 h | 2 869 h | 2 970 h | 2 081 h | 2 081 h | 2 057 h | 1 281 h | 1 281 h | 1 281 h
741 h | 466 h | 219 h | 1 636 h | 1 540 h | 1 032 h | 574 h | 352 h | 107 h
| BE | QA | FE
Sprint 5 | 73 | 21 | 62
Sprint 6 | 85 | 26 | 71
Sprint 7 | 90 | 51 | 91
Front End Sprint 6: Bugs statistics; Front End Sprint 7: Yesterday |  |  | Today
Front End Sprint 6: Open; Front End Sprint 7: 15 |  |  | 15
Front End Sprint 6: Ongoing; Front End Sprint 7: 11 |  |  | 11
Front End Sprint 6: Closed; Front End Sprint 7: 52 |  |  | 52
Front End Sprint 6: Time spent on bugs; Front End Sprint 7: 343 h |  |  | 343 h
[9 empty] | QA | FE | BE | QA | FE | bar: Front End Sprint 7
Front End Sprint 7: 283 h | 32 h | 28 h | 283 h | 32 h | 28 h