## Sheet1
Design document: https://docs.google.com/document/d/1B5RlsVSZdiuKTVAqhrn7xClewqhzrxhliUZd_yIHUBg/edit?usp=sharing
WBS | Name | Description | Depends on | Estimated development time [h] |  |  | Estimated testing time [h] |  | Developer | Actual development time [h] | Commit changes |  | Estimated code documentation time [h] | Jira ID | Commit ID | Comment
|  |  |  | Designer (Wojtek) | Reviewer (Michal) | PM (Artur) | Tester (Piotr) | PM (Artur) |  |  | Insertions | Deletions
1 | Implementing TagQueryAPI | Implement TagQueryAPI class and functions makeIterator / AND / OR / ORX / AND_NOT. Should be added to the BigSense project. |  | 16 | 20 |  |  |  |  | 32 |  |  |  | BNAP-1301
2 | Implement AdminPanelTags class | Make sure to include all tags mentioned in the design. Add class to AdminPanel's resources. |  | 8 | 8 |  |  |  |  | 8 | 173 | 5 |  | BNAP-1302 |  | it took ~1h to compile the project
3 | AdminPanelAPI refactoring |  | 1 - 2 | [10 empty] | BNAP-1303
3.1 | implement access validation methods | canView, canEdit, canCreate, canDelete, isSuperAdmin | 1 - 2 | 8 | 8 |  | 8 |  |  | 10 | 259 | 50 |  | BNAP-1308
3.2 | implement PermissionType enum and translation | rename PermissionType to OldPermissionType and add function to translate from OldPermissionType to PermissionType | 1 - 2 | 4 | 4 |  | 2 |  |  | 0.5 | 41 | 2 |  | BNAP-1309
3.3 | refactor 78 methods marked as "A" in the design document | Im most cases the refactoring only required to verify permission using the new methods added in 3.1 or changing the method name (and marking old name as depracated), Make sure permission checks are verified in unit tests | 3.1 | 24 | 40 |  | 24 |  |  | 18 |  |  |  | BNAP-1310
3.4 | refactor 30 methods marked as "T" | Methods require integration with the ObjectBook (either adding or removing tags) | 3.1 | 24 | 40 |  | 16 |  |  | 55 | 432 | 240 |  | BNAP-1311
3.5 | refactor add_new_organization |  | 3.1 + 4 | 4 | 4 |  | 2 |  |  | 1 | 3 | 2 |  | BNAP-1312
3.6 | refactor add_role_for_org and add_role |  | 3.1 + 4 | 4 | 4 |  | 4 |  |  | 2 | 9 | 5 |  | BNAP-1313
3.7 | refactor get_member_permissions |  | 3.1 + 4 | 4 | 4 |  | 4 |  |  | 3 |  |  |  | BNAP-1314
3.8 | refactor add_new_application and delete_application |  | 3.1 + 4, 3.16 | 4 | 4 |  | 4 |  |  | 8 | 81 | 111 |  | BNAP-1315 |  | Added more dependencies 28 Dec.
3.9 | refactor add_new_action method |  | 3.1 + 4 | 4 | 4 |  | 4 |  |  | 28 |  |  |  | BNAP-1316
3.10 | refactor remove_action_scope / remove_all_action_scopes |  | 3.1 + 3.19 + 4, 3.16 | 4 | 4 |  | 4 |  |  | 8 | 297 | 5 |  | BNAP-1317 |  | Added more dependencies 28 Dec.
3.11 | refactor add_role_allowed_actions / remove_role_allowed_actions |  | 3.1 + 4, 3.16 | 4 | 4 |  | 4 | [6 empty] | BNAP-1318 |  | Added more dependencies 28 Dec.
3.12 | is_member_allowed | handle the additional input arguments | 3.1 + 4 + 3.16 | 4 | 4 |  | 2 | [6 empty] | BNAP-1319
3.13 | initialize_default_actions_for_super_org |  | 3.1 + 4 + 3.9 | 6 | 4 |  | 2 | [6 empty] | BNAP-1320 |  | Added more dependencies 30 Dec.
3.14 | refactor 16 methods marked as "D" in the design document | Either completely remove method or rename / mark as deprecated / forward to other method | 3.1 - 3.13, 3.16 | 4 | 8 |  | 8 | [6 empty] | BNAP-1321 |  | Added more dependencies 28 Dec.
3.15 | implement get_admin_roles |  | 3.1 + 4 | 2 | 2 |  | 2 |  |  | 0.75 | 26 | 0 |  | BNAP-1322
3.16 | implement extend_role / extend_role_scope |  | 3.1 + 3.19 + 4 | 6 | 8 |  | 4 |  |  | 40 |  |  |  | BNAP-1323 |  | Added more dependencies 28 Dec.
3.17 | implement remove_permission_from_role / remove_scope_from_role |  | 3.1 + 3.19 + 4, 3.16 | 4 | 4 |  | 4 | [6 empty] | BNAP-1324 |  | Added more dependencies 28 Dec.
3.18 | Implement get_applications |  | 3.1 + 4 | 2 | 2 |  | 2 |  |  | 0.5 | 18 | 0 |  | BNAP-1325
3.19 | Implement VPermissionWithScope / o_permission_with_scope |  | 3.1 + 4 | 6 | 6 | 6 | 4 |  |  | 8 |  |  |  | BNAP-1353 |  | Task added 22 Dec.
3.20 | Refactor ObjectFrameFactory to use fields from the modified data model classes | Newly added or modified fields need integration with the ObjectFrame interface | 3.1 + 4 | 12 |  | 12 | 8 |  |  | 6 |  |  |  | BNAP-1355 |  | Task added 28 Dec.
4 | Refactoring of the Data Model | [12 empty] | BNAP-1304
4.1 | Refactor VAction / o_action / VActoinExtension / o_action_extension classes | make sure to make copy of the deprecated models |  | 4 | 4 |  |  |  |  | 8 | 1452 | 996 |  | BNAP-1326
4.2 | Refactor VRole / o_role classes |  |  | 2 | 4 |  |  |  |  | 4 | 89 | 270 |  | BNAP-1327
4.3 | Refactor VOrganization / VOrganizationManager / o_ogranization / o_organization_manager classes | make sure to make copy of the deprecated models (VOldOrganization) |  | 3 | 6 |  |  |  |  | 4 | 1655 | 59 |  | BNAP-1328
4.4 | Refactor VUser / o_user classes |  |  | 2 | 4 |  |  |  |  | 4 | 44 | 96 |  | BNAP-1329
4.5 | Refactor VApplication / o_application classes |  |  | 2 | 4 |  |  |  |  | 4 | 32 | 244 |  | BNAP-1330
5 | Migration |  | 3 - 4 | [10 empty] | BNAP-1305
5.1 | Impemented migrateTags method in all classes |  | 3 - 4 | 12 | 16 | [8 empty] | BNAP-1331
5.2 | Implement clearUnusedFields method in all deprecated classes, make copy of the deprecated models |  | 3 - 4 | 4 | 4 |  |  |  |  | 4 |  |  |  | BNAP-1332
5.3 | Implement setDefaults method in migrated classes |  | 3 - 4 | 3 | 4 |  |  |  |  | 4 |  |  |  | BNAP-1333
5.4 | Implement creation of system permissions |  | 3 - 4 | 4 | 4 | [8 empty] | BNAP-1334
5.5 | Implement creation of the Super Admin role |  | 3 - 4 | 2 | 4 | [8 empty] | BNAP-1335
5.6 | Implement creation of the Application Level Admin Role |  | 3 - 4 | 4 | 4 | [8 empty] | BNAP-1336
5.7 | Implement migration function | use all available methods to perform the migration | 5.1 - 5.6 | 4 | 4 | [8 empty] | BNAP-1337
6 | Fix unit tests
7 | QA review
7.1 | Permission access test | [5 empty] | 16 | [6 empty] | BNAP-1384
7.2 | Organization access test | [5 empty] | 12 | [6 empty] | BNAP-1385
7.3 | Application access test | [5 empty] | 12 | [6 empty] | BNAP-1386
7.4 | Member access test | [5 empty] | 12 | [6 empty] | BNAP-1387
7.5 | Role access test | [5 empty] | 12 | [6 empty] | BNAP-1388
7.5 | User access test | [5 empty] | 12 | [6 empty] | BNAP-1389
Total time
Reported bugs (QA)
1 | BIG-3114 | Migration problem (after merging 2) | [7 empty] | 2
2 | BNAP-1391
3 | BNAP-1394